SOP 9.4.310 – Manage General Contractor Communications

Department: Project Management / Contract Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.4.270 - Manage Project Communications; 9.4.275 - Manage Internal Communications; 9.4.280 - Manage External Communications; 9.4.285 - Manage Client/Owner Communications; 9.4.290 - Manage Subcontractor Communications
Reference: GSL Project Manager Procedures – Communication

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To manage communications with the General Contractor (GC) to ensure coordination, contractual compliance, and documentation of all directives.

Scope

This SOP applies to Project Managers, Field Supervisors, and Site Administrators.
All GC communications must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Serves as the single point of contact with the GC. |
| Field Supervisor | Communicates field conditions to PM for escalation. |
| Site Administrator | Logs and organizes all GC communications. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Contract correspondence templates

- Meeting agenda and logs

Procedure

- Route all GC communications through the Project Manager.

- Document coordination meetings and directives in minutes.

- Confirm verbal instructions in writing.

- Track GC directives and responses.

- File all records per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| GC Communication Log | Site Administrator | Per SOP 190A |
| Meeting Minutes | PM | Per SOP 190A |
| GC Directives | PM | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of GC communications routed through PM | 100% |
| Directives confirmed in writing within 24 hrs | 100% |
| Logs maintained and audited monthly | 100% |

References

- GSL Project Manager Procedures – Communication

- SOP 9.41.190A – Document Filing Standards

Appendix

- GC Communication Log Template

- Directive Tracking Form