SOP 9.4.320 – Update Project Schedule

Department: Project Management / Scheduling
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.2.110 - Develop Project Schedule; 9.4.315 - Develop Project Schedule; 9.4.325 - Monitor Schedule Performance; 9.4.330 - Develop Schedule Recovery Plans; 9.4.335 - Prepare Lookahead Schedules; 9.4.340 - Manage Resource-Loaded Schedules; 9.4.345 - Conduct Schedule Review Meetings; 9.4.350 - Manage Schedule Change Requests
Reference: GSL Project Manager Procedures – Scheduling

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To update the project schedule regularly, reflecting actual progress, changes, and delays, ensuring alignment with field execution.

Scope

This SOP applies to Project Managers, Superintendents, and Site Administrators.
All schedule updates must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Updates schedule with progress and changes. |
| Superintendent | Provides weekly field progress and manpower updates. |
| Site Administrator | Files updated schedules. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Current project schedule

- Field progress reports

Procedure

- Collect weekly field progress from Superintendent.

- Input progress into scheduling software.

- Update logic ties and forecasted dates.

- Review changes with project team.

- File updated schedule per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Updated Project Schedule | Project Manager | Per SOP 190A |
| Progress Narrative | PM | Per SOP 190A |
| Lookahead Schedule | Superintendent | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Weekly schedule updates completed | 100% |
| Forecast reflects actual field progress | ≥95% |
| Updated schedule filed within 24 hrs | 100% |

References

- GSL Project Manager Procedures – Scheduling

- SOP 9.41.190A – Document Filing Standards

Appendix

- Progress Update Template

- Lookahead Example