SOP 9.4.325 – Monitor Schedule Performance

Department: Project Management / Scheduling
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.2.110 - Develop Project Schedule; 9.4.315 - Develop Project Schedule; 9.4.320 - Update Project Schedule; 9.4.330 - Develop Schedule Recovery Plans; 9.4.335 - Prepare Lookahead Schedules; 9.4.340 - Manage Resource-Loaded Schedules; 9.4.345 - Conduct Schedule Review Meetings; 9.4.350 - Manage Schedule Change Requests
Reference: GSL Project Manager Procedures – Scheduling

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To monitor schedule performance by comparing baseline, updated schedules, and actual field progress to identify variances and risks.

Scope

This SOP applies to Project Managers, Superintendents, and Branch Managers.
All schedule performance reports must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Prepares performance reports and identifies variances. |
| Superintendent | Provides progress verification and field insights. |
| Branch Manager | Reviews schedule performance during audits. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Baseline and updated schedules

- Performance tracking reports

Procedure

- Compare updated schedule against baseline.

- Identify critical path slippage or delays.

- Track manpower and productivity versus plan.

- Document variance analysis in report.

- File performance reports per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Schedule Performance Report | Project Manager | Per SOP 190A |
| Variance Log | PM | Per SOP 190A |
| Audit Review Notes | Branch Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Performance monitored weekly | 100% |
| Variances documented in reports | 100% |
| Corrective actions identified within 1 week | ≥95% |

References

- GSL Project Manager Procedures – Scheduling

- SOP 9.41.190A – Document Filing Standards

Appendix

- Performance Report Template

- Variance Log Example