SOP 9.4.425 – Manage Job Cost Reports

Department: Project Management / Accounting
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.2.090 - Develop Labor Budget; 9.4.400 - Monitor Project Costs; 9.4.405 - Manage Cost Forecasts; 9.4.410 - Manage Cost Codes; 9.4.415 - Manage Committed Costs; 9.4.420 - Manage Actual Costs; 9.4.430 - Manage Profit Projections; 9.4.435 - Manage Cost-to-Complete
Reference: GSL Project Manager Procedures – Cost Management

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.5 Accounting

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To prepare and distribute job cost reports that compare actual and committed costs to the budget, ensuring management visibility of project financial status.

Scope

This SOP applies to Project Managers, Accounting, and Branch Managers.
All job cost reports must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Reviews and analyzes job cost reports for accuracy. |
| Accounting | Generates reports from financial system. |
| Branch Manager | Reviews reports for financial performance oversight. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Budget, commitment, and actual cost records

- Financial reporting system

Procedure

- Accounting generates job cost reports monthly.

- Project Manager reviews reports and verifies accuracy.

- Document and investigate variances.

- Distribute reports to Branch Manager.

- File per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Monthly Job Cost Report | Accounting | Per SOP 190A |
| Variance Notes | Project Manager | Per SOP 190A |
| Management Review Records | Branch Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Job cost reports generated monthly | 100% |
| Variances documented within 5 days | 100% |
| Reports distributed to management | 100% |

References

- GSL Project Manager Procedures – Cost Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- Job Cost Report Example

- Variance Analysis Form