SOP 9.4.440 – Prepare Billing Schedule

Department: Project Management / Accounting
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.4.400 - Monitor Project Costs; 9.4.405 - Manage Cost Forecasts; 9.4.410 - Manage Cost Codes; 9.4.415 - Manage Committed Costs; 9.4.445 - Prepare Monthly Pay Applications
Reference: GSL Project Manager Procedures – Billing & Invoicing

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.5 Accounting

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To develop a billing schedule that aligns with the project contract, milestones, and cash flow requirements.

Scope

This SOP applies to Project Managers and Accounting.
All billing schedules must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Prepares draft billing schedule and aligns with contract requirements. |
| Accounting | Reviews billing terms and ensures compliance with financial system. |
| Branch Manager | Approves billing schedule. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Project contract and schedule of values (SOV)

- Project budget

Procedure

- Review contract billing requirements (lump sum, unit price, progress billing).

- Prepare billing schedule with milestones or monthly applications.

- Submit draft schedule to Accounting and Branch Manager.

- Obtain approval and distribute to project team.

- File final billing schedule per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Billing Schedule | Project Manager | Per SOP 190A |
| Review Notes | Accounting | Per SOP 190A |
| Approval Record | Branch Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Billing schedule prepared within 15 days of turnover | 100% |
| Billing schedule matches contract requirements | 100% |
| Approved schedule filed prior to first billing | 100% |

References

- GSL Project Manager Procedures – Billing & Invoicing

- SOP 9.41.190A – Document Filing Standards

Appendix

- Billing Schedule Template

- Schedule of Values Example