SOP 9.4.680 – Conduct Weekly Foreman Meetings

Department: Field Operations / Project Management
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.4.010 - Conduct Coordination Meetings; 9.4.020 - Conduct Subcontractor Coordination Meetings; 9.4.030 - Conduct Client/Owner Meetings; 9.4.040 - Conduct Safety Meetings; 9.4.050 - Conduct Prefabrication Coordination Meetings; 9.4.060 - Conduct Quality Meetings; 9.4.345 - Conduct Schedule Review Meetings; 9.4.675 - Conduct Daily Huddles
Reference: GSL Project Manager Procedures – Field Execution

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To conduct weekly foreman meetings to review schedule, manpower, coordination issues, and site logistics.

Scope

This SOP applies to Project Managers, Field Supervisors, and Foremen.
All foreman meeting records must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Leads meeting and tracks action items. |
| Field Supervisor | Provides field updates and identifies constraints. |
| Foremen | Share crew progress and coordination needs. |
| Site Administrator | Records minutes and files documentation. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Meeting agenda template

- Updated lookahead schedule

Procedure

- Schedule weekly foreman meeting (typically Mondays).

- Review progress, upcoming tasks, and resource needs.

- Identify conflicts with subcontractors and resolve.

- Record attendance, minutes, and action items.

- File foreman meeting record per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Meeting Agenda | Project Manager | Per SOP 190A |
| Attendance Log | Site Administrator | Per SOP 190A |
| Meeting Minutes | PM / Supervisor | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Weekly meetings held as scheduled | 100% |
| Action items closed within 7 days | ≥95% |
| Minutes filed within 48 hrs | 100% |

References

- GSL Project Manager Procedures – Field Execution

- SOP 9.41.190A – Document Filing Standards

Appendix

- Foreman Meeting Agenda Template

- Action Item Log