SOP 9.4.710 – Manage Workface Planning

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.4.675 - Conduct Daily Huddles; 9.4.680 - Conduct Weekly Foreman Meetings; 9.4.690 - Track Manpower Utilization; 9.4.705 - Manage Work Packaging; 9.4.715 - Manage Field Coordination
Reference: GSL Project Manager Procedures – Field Execution

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To implement workface planning (WFP) by providing crews with all information, materials, and tools needed before starting field tasks.

Scope

This SOP applies to Project Managers, Field Supervisors, and Foremen.
All workface planning documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Oversees WFP process and reviews readiness. |
| Field Supervisor | Confirms workface readiness before assigning tasks. |
| Foremen | Execute tasks only once resources are fully available. |
| Site Administrator | Maintains WFP checklists and logs. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- WFP readiness checklist

- Lookahead schedules

Procedure

- Identify upcoming tasks from lookahead schedule.

- Verify availability of drawings, materials, tools, and labor.

- Complete WFP checklist before task start.

- Assign tasks to crews with confirmed readiness.

- File WFP documentation per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| WFP Checklist | Field Supervisor | Per SOP 190A |
| Workface Readiness Log | Site Administrator | Per SOP 190A |
| Task Assignment Records | Foremen | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of tasks readiness verified | 100% |
| Checklists filed before task start | 100% |
| Zero work stoppages due to missing resources | ≥95% compliance |

References

- GSL Project Manager Procedures – Field Execution

- SOP 9.41.190A – Document Filing Standards

Appendix

- WFP Checklist Template

- Readiness Log Example