SOP: 9.2.005 – Review Contract for High Risk Clauses

Department: Branch Management

Related SOPs:

Purpose

To establish standardized procedures for this activity.

Scope

Roles & Responsibilities

Requirements

- Review 9.2.015 - Project Turnover Meeting 9.2.0 30

- PM Review Contract  and  High-Risk Clauses ================================================================================ DOCUMENT REFERENCES ================================================================================ Training Materials (Foreman Training Binder): - Tab 2: Preplanning & Staging - Tab 3: Kickoff/Project Turnover Meeting - Tab 5: Purchasing Buy out - Tab 6: Scheduling - Tab 7: Job Plans Job Descriptions (Policy Manual Section 7): - 7.3.1 Operations Management Management Directives (Policy Manual Section 9): - 9.5 Project Management - 9.7 Estimating - 9.3 Field Leadership ================================================================================ PURPOSE To establish a standardized process for reviewing contract terms to identify unfavorable or high-risk clauses before baseline planning begins, ensuring proper risk mitigation and approval protocols are in place. SCOPE Applies to all projects / situations where: New contract has been  issued for  review and  signatures Contract modifications or amendments are received Subcontract  flow down  terms require review Risk assessment is needed before project baseline ROLES & RESPONSIBILITIES Branch Manager  Conducts initial contract review; Identifies risk areas; Documents concerns and mitigation strategies .   Approves risk acceptance; Authorizes contract negotiations; Final authority on high-risk decisions . Estimator   Validates scope assumptions; Confirms pricing aligns with contract terms  Business Manager    Reviews significant risk items; Advises on liability and insurance .    Issue a letter of clarification for negotiation of the contract. REQUIREMENTS Receive  contract documents General and special conditions Scope of work and specifications Original estimate and assumptions Standard contract review checklist Company risk tolerance guidelines PROCEDURE STEP 1 - Obtain Complete Contract Package Branch Manager   assures  all contract documents are received: Prime contract or subcontract agreement General conditions Special conditions Scope of work Specifications and drawings list Insurance and bonding requirements STEP 2 - Conduct Initial Review Business Manager  reviews contract using standard checklist for: Payment terms and retainage Change order procedures and markup allowances Liquidated damages and penalties Indemnification and liability clauses Insurance requirements Warranty obligations Termination provisions Dispute resolution procedures STEP 3 - Identify High-Risk Clauses Flag clauses that present risk: No-damage-for-delay provisions Pay-when-paid or pay-if-paid terms Broad indemnification requirements Excessive insurance limits Unreasonable warranty periods One-sided termination rights Waiver of lien rights STEP 4 - Document Risk Assessment For each identified risk: Describe the risk and potential impact Assess probability and severity Propose mitigation strategies Estimate cost of risk acceptance Recommend approval or negotiation STEP 5 - Obtain Approval Present risk assessment to Branch Manager: Review findings and recommendations Obtain approval for risk acceptance or negotiation Document decisions and rationale Update project baseline if risks accepted STEP 6 - Communicate Results Share approved contract review with: Project team at turnover meeting Accounting for billing compliance Safety for insurance requirements Purchasing for subcontract flowdown KEY PERFORMANCE INDIDCATORS Contract review completed before baseline  planning 100 % All high-risk clauses documented 100%  Branch Manager approval for risk acceptance 100% Risk mitigation strategies in place 100% APPENDIX Estimating Contract Review Forms Contract Review Checklist Risk Assessment Matrix Template Common High-Risk Clauses Reference Flowdown Requirements Checklist

Procedure

Appendix