SOP: 9.2.015 – Project Turnover Meeting

Department: Project Management / Operations

Related SOPs:

9.2.005 – Review Contract for High Risk Clauses

9.2.010 – Team Selection

9.2.040 – Project Manager Reviews Plans Specifications & Schedule

9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule

9.2.110 – Develop Project Schedule

9.2.130 – Construction Execution Kickoff Meeting

9.2.140 – Develop Project Budget

9.6.015 – Manage Project Turnover Documentation

Purpose

To ensure a consistent and documented turnover process for newly awarded projects using a standardized Smartsheet agenda to guide communication, task planning, and team alignment.

Scope

This SOP applies to all projects awarded through GSL's estimating department.

Roles & Responsibilities

Project Manager

- Schedules the meeting, maintains the Smartsheet agenda, and ensures all sections are completed.

Estimator

- Provides cost breakdowns, scope assumptions, and value engineering input.

General Superintendent

- Validates field plan, resources, and schedule expectations.

Safety Representative

- Reviews site-specific safety items and populates relevant Smartsheet sections.

Prefab Lead

- Evaluates prefab opportunities and updates prefab-related rows.

Purchasing

- Identifies procurement timelines, long-lead items, and vendor follow-ups.

All Attendees

- Review and update their assigned sections of the Smartsheet before the meeting.

Requirements

- Award package (estimate, scope, clarifications)

- Current Smartsheet agenda workbook (template link)

- Project specifications and drawings

- Prefab and safety planning tools

- Master planning worksheet

Procedure

Step 1 – Initiate Turnover Process

Upon award, the PM duplicates the standard Smartsheet Turnover Agenda template. The Smartsheet is saved to the project folder and link is shared with core stakeholders. The PM enters project details into the header section.

Step 2 – Assign Section Ownership

Each column of the Smartsheet corresponds to a topic (Scope, Safety, Prefab, Procurement, etc.). The PM assigns responsible parties for each topic using the 'Owner' column. Assigned individuals must review and pre-fill their sections before the meeting date.

Step 3 – Schedule the Turnover Meeting

PM schedules the turnover meeting within 5 business days of project award. Required attendees include: Estimator, PM, GS, Safety, Prefab, and Purchasing.

Step 4 – Conduct the Turnover Meeting

The PM shares the live Smartsheet during the meeting. Each topic owner presents their section, discusses open items, and logs comments directly in Smartsheet. Action items are entered into the 'Follow-Up' and 'Status' columns.

Step 5 – Document and Distribute Results

After the meeting, the PM ensures all sections are marked complete or have follow-ups logged. The Smartsheet remains the living document throughout planning. The final link is added to the project folder and shared with the extended team.

Appendix

- References & Training Materials Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans Job Descriptions (Policy Manual Section 7):

- 7.2.5 Project Superintendent

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

- 7.3.3 Estimating Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership Reference Documents:

- GSL Smartsheet Turnover Agenda Template

- Pre-Planning Smartsheet Agenda (Turnover Workbook)

- Sample Completed Turnover Workbook

- Prefab and Safety Planning Worksheets

RACI Responsibility Matrix

| Responsibility | Project Manager | Estimator | General Superintendent | Safety Representative | Prefab Lead | Purchasing | All Attendees |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Schedules the meeting, maintains the Smartsheet ag... | R | C | C | C | C | C | C |
| Provides cost breakdowns, scope assumptions, and v... | R | C | C | C | C | C | C |
| Validates field plan, resources, and schedule expe... | R | C | C | C | C | C | C |
| Reviews site-specific safety items and populates r... | R | C | C | C | C | C | C |
| Evaluates prefab opportunities and updates prefab-... | R | C | C | C | C | C | C |
| Identifies procurement timelines, long-lead items,... | R | C | C | C | C | C | C |
| Review and update their assigned sections of the S... | R | C | C | C | C | C | C |

R = Responsible (does the work)  |  A = Accountable (owns the outcome)  |  C = Consulted (provides input)  |  I = Informed (notified after)