SOP: 9.2.030 – Review Contract for Unfavorable or High Risk Clauses

Department: Project Management / Pre-Construction

Related SOPs:

9.2.005 – Review Contract for High Risk Clauses

9.2.010 – Team Selection

9.2.015 – Project Turnover Meeting

9.2.020 – Procurement of Large Feeder Wire

9.2.040 – Project Manager Reviews Plans Specifications & Schedule

9.2.070 – Conduct Site Visit

9.2.120 – Establish Tracking & Control Systems

9.2.130 – Construction Execution Kickoff Meeting

Purpose

To ensure all project contracts are reviewed systematically for unfavorable or high-risk clauses that could affect project execution, budget, or liability, and to define mitigation measures prior to mobilization.

Scope

This SOP applies to all Project Managers during the pre-construction phase of awarded projects.

Roles & Responsibilities

Project Manager

- Leads contract review, completes checklist, and escalates risks to Branch Manager.

Estimator

- Provides bid assumptions and clarifications for comparison.

- Field Supervisor:  Identifies field-related risks tied to contractual obligations.

Branch Manager

- Approves mitigation strategy for high-risk clauses.

Requirements

- Contract Review Checklist (Table 4.6)

- Executed contract documents (general conditions, terms, scope)

- Bid submission and clarification letters

- Insurance and bonding requirements

Procedure

Step 1 – Collect Documents

Gather executed contracts, specifications, drawings, and bid clarifications.

Step 2 – Review Key Clauses

Complete Contract Review Checklist with focus on: Indemnification and liability allocation Delay clauses and liquidated damages Dispute resolution (ADR, arbitration, mediation) Change order notification procedures Insurance, bonding, and permit requirements

Step 3 – Identify Risks

Flag unfavorable terms and propose mitigation strategies. Review risks with Branch Manager for approval.

Step 4 – Recordkeeping

Save completed checklist and notes in the project folder. Incorporate findings into turnover meeting agenda (9.2.015 Project Turnover Meeting).

Appendix

- References & Training Materials Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership Reference Documents:

- GSL Pre-Construction Planning

- Section 4.3 Scope and Contract Review

- Contract Review Checklist (Table 4.6)

- Contract Review Checklist (sample)

- Insurance & Bonding Matrix

- Dispute Resolution Clause Examples