SOP: 9.2.040 – Project Manager Reviews Plans, Specifications & Schedule

Department: Project Management

Related SOPs:

9.2.005 – Review Contract for High Risk Clauses

9.2.015 – Project Turnover Meeting

9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule

9.2.055 – Compare Estimated vs Planned Performance

9.2.057 – Identify VE and Prefabrication Opportunities

9.2.060 – Create Issue List and Begin RFI Process

9.2.110 – Develop Project Schedule

9.2.140 – Develop Project Budget

Purpose

To ensure that the Project Manager conducts a detailed review of project drawings, specifications, and schedules to confirm alignment with contract requirements and identify risks before mobilization.

Scope

This SOP applies to all Project Managers for awarded projects during the pre-construction planning phase.

Roles & Responsibilities

Project Manager

- Performs review of drawings, specifications, and schedules; documents findings.

General Superintendent

- Validates manpower feasibility and resource planning.

Estimator

- Provides bid documentation and assumptions for comparison.

Branch Manager

- Confirms alignment with branch capacity and execution strategy.

Requirements

- Latest project drawings and specifications

- Contract documents and milestone schedules

- Bid package and clarification letters

- Scope & Schedule Review Checklist (Table 4.7)

- Project Execution Plan (PEP) template

Procedure

Step 1 – Gather Documents

Collect all drawings, specifications, and contractual schedules. Obtain bid submission documents for baseline comparison.

Step 2 – Review Drawings and Specifications

Verify scope completeness and identify omissions, conflicts, or design gaps. Compare against contract inclusions/exclusions.

Step 3 – Review Schedule

Validate milestone dates, phasing, and dependencies. Identify long-lead items or sequencing conflicts.

Step 4 – Document Findings

Complete the Scope & Schedule Review Checklist. Record risks and clarifications in the PEP.

Step 5 – Communicate Results

Share findings with Superintendent, Estimator, and Branch Manager. Update turnover materials as required.

Appendix

- References & Training Materials Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership Reference Documents:

- GSL Pre-Construction Planning

- Section 4.3 Scope & Contract Review

- Scope & Schedule Review Checklist (Table 4.7)

- Project Execution Plan (PEP) template

- Example Bid Clarification Letter