SOP: 9.2.050 – Field Supervisor Reviews Plans, Specifications & Schedule

Department: Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0

Related SOPs:

9.2.015 – Project Turnover Meeting;

9.2.040 – Project Manager Reviews Plans Specifications & Schedule;

9.2.055 – Compare Estimated vs Planned Performance;

9.2.057 – Identify VE and Prefabrication Opportunities;

9.2.100 – Prepare Layout & Sequencing Plan;

9.2.110 – Develop Project Schedule;

Purpose

To ensure Field Supervisors conduct a detailed review of project drawings, specifications, and schedules with a focus on constructability, sequencing, and field logistics, supporting accurate execution planning.

Scope

Roles & Responsibilities

Requirements

Procedure

Step 1 – Gather Documents Collect current drawings, specifications, schedules, and bid assumptions. Step 2: Review for Constructability Verify installation feasibility of major systems. Identify site access issues, workspace conflicts, and constructability risks. Step 3: Validate Schedule Alignment Assess manpower loading requirements. Identify risks in durations, sequencing, or milestones. Step 4: Document Findings Record observations in Scope & Schedule Review Checklist. Flag issues that may require RFIs. Step 5: Provide Feedback Submit findings to Project Manager and General Superintendent for incorporation into the PEP. Deliverables Document Owner Location Field Review Notes Field Supervisor Project Folder Updated Scope & Schedule Checklist Field Supervisor / PM Project Folder Manpower Input Field Supervisor PEP File Compliance & Review KPI Target Field review completed prior to turnover 100% Constructability issues documented 100% Findings incorporated into PEP 100% References GSL Pre-Construction Planning

Section 4.3 Scope & Contract Review Scope & Schedule Review Checklist (Table 4.7)

Appendix