SOP: 9.2.055 – Compare Estimated vs Planned Performance

Department: Project Management / Estimating

Related SOPs:

9.1.050 – Prepare Construction Takeoff

9.2.005 – Review Contract for High Risk Clauses

9.2.040 – Project Manager Reviews Plans Specifications & Schedule

9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule

9.2.057 – Identify VE and Prefabrication Opportunities

9.2.090 – Develop Labor Budget

Purpose

To confirm that bid assumptions for labor, materials, and productivity align with the planned project execution strategy, ensuring accurate budgets and realistic performance goals.

Scope

This SOP applies to Project Managers and Estimators during the pre-construction planning phase of all awarded projects.

Roles & Responsibilities

Project Manager

- Compares estimated assumptions with planned execution; documents variances.

Estimator

- Provides bid documentation, scope notes, and clarifications.

General Superintendent

- Reviews manpower and sequencing implications of variances.

Branch Manager

- Validates budget alignment with operational strategy.

Requirements

- Estimator's bid package and clarifications

- Final Construction Takeoff (9.1.050

- Prepare Construction Takeoff)

- Labor productivity data

- Budget tracking tools

- Project Execution Plan (PEP)

Procedure

Step 1 – Collect Documents

Obtain bid package, assumptions, and estimator clarifications.

Step 2 – Compare Labor & Materials

Review bid productivity rates versus manpower plan. Confirm material quantities align with construction takeoff.

Step 3 – Identify Variances

Document discrepancies that may affect budget, schedule, or scope.

Step 4 – Adjust Plan

Incorporate adjustments into the PEP and labor budget. Escalate significant deviations to Branch Manager for resolution.

Step 5 – Record & File

Save comparison notes and updated budget files to project folder.

Appendix

- References & Training Materials Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents Reference Documents:

- GSL Pre-Construction Planning

- Section 4.3 Bid vs. Execution Review

- Sample Comparison Worksheet

- Variance Tracking Template