SOP: 9.2.057 – Identify VE and Prefabrication Opportunities

Department: Project Management / Prefabrication

Related SOPs:

9.2.005 – Review Contract for High Risk Clauses

9.2.010 – Team Selection

9.2.040 – Project Manager Reviews Plans Specifications & Schedule

9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule

9.2.055 – Compare Estimated vs Planned Performance

9.4.045 – Identify Value Engineering & Prefabrication Opportunities

9.4.050 – Conduct Prefabrication Coordination Meetings

9.4.585 – Plan Prefabrication Resources

Purpose

To define the process for identifying, developing, and documenting the project's prefabrication strategy, allowing for improved planning, efficiency, and field execution through the use of off-site construction.

Scope

Applies to all projects with opportunities for prefabricated assemblies or materials.

Roles & Responsibilities

Project Manager

- Supports prefab planning and ensures alignment with schedule and budget.

General Superintendent

- Validates site readiness and receiving capabilities.

Estimator

- Confirms prefab elements included in the bid and identifies cost impacts.

- Project Engineer:  Assists with documentation and submittal dependencies.

Requirements

- Project drawings and specifications

- Prefab scope summary from estimator (if available)

- Prefab Planning Template

- Initial submittals and vendor lead times

- Field logistics layout and receiving plan

Procedure

Step 1 – Identify Prefab Opportunities

Prefab Lead reviews riser diagrams, conduit routing, panelboard/lighting/feeder configurations, and typical branch devices. Estimate or bid package reviewed for included prefab scope.

Step 2 – Conduct Prefab Planning Session

PM schedules internal meeting including Prefab Lead, PM and PE, General Superintendent, and Estimator (as needed). Discuss what assemblies can be prefabbed, delivery strategy and schedule impacts, and submittal dependencies and approval timelines.

Step 3 – Draft Prefab Plan

Prefab Lead completes Prefab Planning Template including scope and quantity of prefabricated items, material sources and BOMs, assembly timeline and location (shop or field), and delivery logistics and staging on site.

Step 4 – Align with Schedule and Submittals

PM confirms all items required for prefab are submitted/approved. Schedule is reviewed to ensure prefab activities support project milestones. Long-lead items are flagged in procurement log.

Step 5 – Finalize and Distribute

Final Prefab Plan is reviewed and approved by PM and GS. Uploaded to project folder. Summary shared with field foreman and procurement team.

Appendix

- References & Training Materials Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans Job Descriptions (Policy Manual Section 7):

- 7.2.5 Project Superintendent

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

- 7.3.3 Estimating Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership Reference Documents:

- Estimating Prefab Scope Summary

- GSL Prefab Planning Template

- Procurement & Submittal Logs

- Prefab Plan Template (fillable)

- Prefab Opportunity Checklist

- Sample Prefab BOM & Delivery Tracker