SOP: 9.2.100 – Prepare Layout & Sequencing Plan

Department: Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0

Related SOPs:

9.2.005 – Review Contract for High Risk Clauses;

9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule;

9.2.080 – Prepare Material Handling Plan;

9.2.110 – Develop Project Schedule;

Purpose

To establish a coordinated layout and sequencing plan that supports efficient installation, minimizes trade conflicts, and ensures project milestones are achieved.

Scope

This SOP applies to Project Managers, Field Supervisors, and General Superintendents during the pre-construction planning phase.

Roles & Responsibilities

Requirements

Procedure

Step 1 – Collect Inputs Gather drawings, logistics plans, and BIM/coordination models. Step 2: Define Work Layout Map work areas, access points, and material staging zones. Step 3: Develop Sequencing Plan Break work into logical phases tied to contract milestones. Identify dependencies and potential trade overlaps. Step 4: Validate Plan Review plan with Superintendent, Field Supervisor, and Safety Coordinator. Adjust based on manpower availability and site logistics. Step 5: Document & Distribute Save plan in the project folder. Share with project team during turnover and kickoff discussions. Deliverables Document Owner Location Layout & Sequencing Plan Project Manager Project Folder Updated PEP PM Project Folder Field Logistics Notes Field Supervisor PEP File Compliance & Review KPI Target Sequencing plan completed prior to mobilization 100% Reviewed by Superintendent and Safety Coordinator 100% Distributed to project stakeholders 100% References GSL Pre-Construction Planning

Section 4.7 Layout & Sequencing

Appendix