SOP: 9.2.110 – Develop Project Schedule

Department: Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0

Related SOPs:

9.2.015 – Project Turnover Meeting;

9.2.040 – Project Manager Reviews Plans Specifications & Schedule;

9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule;

9.2.100 – Prepare Layout & Sequencing Plan;

9.2.140 – Develop Project Budget;

9.4.315 – Develop Project Schedule;

9.4.320 – Update Project Schedule;

9.4.325 – Monitor Schedule Performance

9.065.41 – Develop Labor Budget

Purpose

To outline the process for developing a complete project schedule that aligns field activities, procurement, prefab, and inspections to meet project milestones and client expectations.

Scope

Applies to all awarded projects prior to mobilization.

Roles & Responsibilities

Requirements

- PM reviews: Contractual completion dates GC milestone calendar Permit and inspection deadlines Long-lead material delivery dates Step 2: Define Work Phases and Tasks Break down the project into: Mobilization Underground Rough-in Gear install Trim-out and finishes Testing, startup, and inspections Assign task owners and durations Step 3: Align With Labor and Layout Plans Cross-check task durations and sequencing with: Labor budget loading Layout & sequencing strategy Prefab delivery and rack install timelines Adjust crew size and work sequence to optimize flow Step 4: Input Into Scheduling Tool PE or PM inputs tasks into GSL-approved scheduling tool Link dependencies and float between phases Highlight critical path and high-risk dates Include inspection and handoff checkpoints Step 5: Review, Approve, and Publish GS and Branch Manager review schedule logic and dates Final version shared with GC, Foreman, and support teams Upload to project folder and print for trailer posting Deliverables Document Owner Location Final Project Schedule Project Manager Project Folder / Share Drive Milestone Summary Sheet Project Engineer GC Correspondence Folder Labor Loading by Week/Phase PM / PE Job Cost & Labor Folder Compliance & Review KPI Target Schedule approved prior to first field mobilization 100% Schedule aligned with labor and procurement strategy 100% Milestones meet contract and GC deliverables 100% References Contract Specifications GC Baseline Schedule Labor Budget and Layout Plan Procurement Log Appendix GSL Scheduling Template Milestone Tracker Manpower Histogram Example

Procedure

Appendix