SOP: 9.2.120 – Establish Tracking & Control Systems

Department: Project Management / Operations

Related SOPs:

9.2.005 – Review Contract for High Risk Clauses

9.2.010 – Team Selection

9.2.015 – Project Turnover Meeting

9.2.020 – Procurement of Large Feeder Wire

9.2.030 – Review Contract for Unfavorable or High-Risk Clauses

9.4.190 – Document Filing Standards

9.4.195 – Manage Project Documentation System

9.4.400 – Monitor Project Costs

Purpose

To establish the project’s tracking and control systems during early preconstruction planning so that cost, schedule, labor productivity, procurement, RFIs/submittals, and change management can be monitored and controlled throughout project execution.

Scope

This SOP applies to Project Managers, Project Engineers/Coordinators, Field Supervisors, and General Superintendents for all awarded projects.

Roles & Responsibilities

Project Manager

- Establishes the project controls structure including cost codes, reporting cadence, logs, filing standards, and dashboards.

- Ensures systems are maintained and used consistently throughout the project.

- Project Engineer / Project Coordinator:  Maintains core logs (RFI, submittal, issue), supports document control, and updates trackers per the defined cadence.

- General Superintendent / Field Leadership:  Provides field inputs for labor productivity tracking, lookahead schedules, daily progress reporting, and field condition updates.

- Safety Coordinator:  Submits safety inspection reports and compliance updates into the project tracking system.

Purchasing

- Updates the procurement log with material orders, vendor status, delivery tracking, and expediting notes.

Branch Manager

- Confirms that required controls are in place prior to mobilization.

- Reviews weekly reports and supports escalation or resource needs.

Requirements

- Project budget and cost codes (from 9.2.140

- Develop Project Budget)

- Baseline project schedule (from 9.2.110

- Develop Project Schedule)

- Project folder / document repository structure (per 9.4.190

- Document Filing Standards)

- Standard log templates: RFI log, submittal log, issue log, change log, procurement log

- Labor tracking sheets and productivity reporting forms

- Safety inspection forms and compliance checklists

- Weekly dashboard template (Smartsheet, Excel, or equivalent)

- Reporting cadence expectations (weekly cost, schedule, labor, and safety updates)

Procedure

Appendix

- Templates & Logs

- RFI Log Template

- Submittal Log Template

- Issue Log Template

- Change Log Template

- Procurement Log Template

- Labor Tracking Template

- Weekly Cost Report Template

- Weekly Dashboard Example

- Schedule Update Checklist Appendix

- References & Training Materials Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

- 7.4.4 Purchasing Manager Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership Reference Documents:

- GSL Pre-Construction Planning

- Section 4.9 Tracking & Control