SOP: 9.3.030 – Setup Site Fencing and Access Control

Department: Field Operations / Safety

Related SOPs:

Purpose

To establish standardized procedures for this activity.

Scope

Roles & Responsibilities

Requirements

- -------------------------------------- FS and Safety review: - Contract fencing requirements - Local code requirements - Owner/GC security standards - Gate locations for personnel and vehicles - Emergency egress needs STEP 2 - Plan Installation -------------------------------------- Develop installation plan: - Mark perimeter boundaries - Identify gate locations - Plan for temporary openings during construction - Coordinate with utilities (underground conflicts) - Schedule installation crew/subcontractor STEP 3 - Install Perimeter Fencing -------------------------------------- Execute installation: - Set fence posts at proper spacing - Install fence panels/fabric - Ensure proper height throughout - Secure bottom of fence to prevent entry - Install barbed wire/topping if required STEP 4 - Install Gates -------------------------------------- Install access points: - Personnel gates at designated locations - Vehicle gates sized for deliveries - Install locking hardware - Ensure gates swing properly - Install gate stops/holders STEP 5 - Establish Access Control -------------------------------------- Implement access protocols: - Install locks and distribute keys - Set up sign-in/sign-out procedures - Post access control signage - Brief all personnel on procedures - Coordinate with security (SOP 9.3.090) STEP 6 - Verify and Document -------------------------------------- Complete installation: - Walk perimeter to verify completeness - Test all gates and locks - Document with photos - Verify emergency egress routes - Communicate access procedures to team ============================================================ COMPLIANCE & REVIEW ============================================================ | KPI | Target | |-----|--------| | Fencing complete before work begins | 100% | | All gates operational with locks | 100% | | Emergency egress verified | 100% | | Access procedures communicated | 100% | ============================================================ APPENDIX ============================================================ - Fencing Installation Checklist - Gate Location Plan Template - Access Control Sign-In Log - Emergency Egress Plan Template ============================================================ REVISION HISTORY ============================================================ Formerly: SOP 9.41.100 - Setup Site Fencing and Access Control Revision: 2.0 | Effective Date: 2025-10-10 Owner: Field Operations | Approver: Executive Committee

Procedure

Appendix