SOP: 9.4.045 – Identify Value Engineering & Prefabrication Opportunities

Department: Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0

Related SOPs:

9.2.057 – Identify VE and Prefabrication Opportunities;

9.4.010 – Conduct Coordination Meetings;

9.4.020 – Conduct Subcontractor Coordination Meetings;

9.4.030 – Conduct Client/Owner Meetings;

9.4.040 – Conduct Safety Meetings;

9.4.050 – Conduct Prefabrication Coordination Meetings;

9.4.055 – Procurement of Large Feeder Wire;

Purpose

To identify and evaluate opportunities for value engineering (VE) and prefabrication to reduce cost, improve efficiency, and simplify work without compromising project scope or quality.

Scope

This SOP applies to Project Managers, Field Supervisors, and Prefabrication Leads during the pre-construction planning phase of all awarded projects.

Roles & Responsibilities

Requirements

Procedure

Step 1 – Review Drawings and Specs Identify repetitive, modular, or offsite-constructible components. Note materials or assemblies that may have VE alternatives. Step 2: Analyze Opportunities Evaluate cost savings, labor efficiency, and schedule benefits. Confirm prefab shop capacity and logistics feasibility. Step 3: Document Proposals Record each opportunity in a VE/Prefab Proposal Log. Provide cost/benefit analysis and schedule impact notes. Step 4: Approve and Integrate Present opportunities at turnover or planning meetings. Integrate approved items into PEP, budget, and procurement plan. Step 5: Monitor Execution Track implementation of approved VE/prefab opportunities. Update logs and share with project team. Deliverables Document Owner Location VE/Prefab Proposal Log Project Manager Project Folder Prefab Strategy Sheet Prefab Lead Prefab Subfolder Updated PEP PM Project Folder Compliance & Review KPI Target 100% of projects reviewed for VE/prefab 100% Documented proposals with cost/schedule impact 100% Approved opportunities integrated into PEP 100% References GSL Pre-Construction Planning

Section 4.3 VE & Prefabrication

Appendix