## Contract Review Items
Table 4.6: Contract Review Items¹ (page 17)
Project Number: ________________________________________________________________________________
Project Name: ________________________________________________________________________________
Location: ________________________________________________________________________________
Project Manager: ________________________________________________________________________________
Completed | Date Completed | ITEM
☐ |  | Check for ambiguous clauses and seek clarification.
☐ |  | Check for one-sided clauses that favor the other party.
☐ |  | Cross-reference clauses to understand the whole meaning of clauses.
☐ |  | Identify discrepancies and conflicting clauses and seek clarification.
☐ |  | Check for agreement between plans and specifications, and seek clarification if there is any discrepancy.
☐ |  | Identify any "killer clauses" that assign full responsibility for everything to the electrical contractor.
☐ |  | Determine whether the contract clearly favors the other party (owner/CM/GC), and seek more equitable contract terms.
☐ |  | Review the Indemnification Clause, and ensure your insurance coverage can sufficiently cover the risk.
☐ |  | Evaluate the Coordination Clause to determine each party's responsibility to coordinate the work.
☐ |  | Determine your rights and responsibilities if the sequence of work is changed or if out-of-sequence work impacts the project.
☐ |  | Carefully review all time-sensitive clauses that cover commencement, completion, milestones, accelerations, delays and progress.
☐ |  | Review and understand your rights to receive damages if the schedule is accelerated or delayed by other parties.
☐ |  | Determine whether there is a no-damages-for-delay clause, and review your rights and responsibilities.
☐ |  | Review and understand the clause that describes waivers.
☐ |  | Review the concealed conditions clause, and identify the circumstances that will entitle you to compensation.
☐ |  | Review the Force Majeure clause, and identify the circumstances that will entitle you to a time extension.
☐ |  | Evaluate clauses that identify procedures for seeking change orders.
☐ |  | Evaluate clauses that identify the compensation for extra work.
☐ |  | Identify payment provisions, especially a "pay when paid" clause and a "pay if paid" clause.
¹Detailed contract review guidelines can be found in ELECTRI International (2000) Fundamentals of Contract Risk Management for Electrical Contractors.