- Table of Contents

Executive Summary	4

1	Introduction	7

1.1.	How the Pre-construction Planning Process was Developed	7

1.2.	Purpose of this Implementation Manual	8

2.	User’s Guide to the Implementation Manual	9

2.1.	How to Use the Pre Construction Planning Process	9

2.2.	Development of a Pre-Construction Planning Binder	9

2.3.	Other Related Documents and Tools	9

2.4.	Organization of the Manual	10

3	Overview of the Pre-Construction Planning Process	11

3.1.	Definition of Pre-Construction Planning	11

3.2.	Pre-Construction Planning Process	11

3.3.	Team Members in the Planning Process	11

3.4.	Strategies for Successful Implementation	11

3.5.	Expected Benefit	12

3.6.	Figure 3.2: The Pre-Construction Planning Process (continued)	17

3.7.	17

3.5.1	Relationship between Planning and Performance	19

4	Pre-Construction Planning Activities	20

4.1.	Introduction to the Pre-Construction Planning Activities	20

4.1.1	Pre-Construction Planning Categories	20

4.1.2	When Should Pre-Construction Planning Occur?	20

4.1.3	Goals of the Pre-Construction Planning Stage	21

4.2.	Team Selection and Turnover	21

4.2.1	What Activities Should be Performed During the Team Selection and Turnover?	21

4.3.	Scope and Contract Review	22

4.3.1	What Activities Should be Performed During a Scope and Contract Review?	23

4.4.	Administrative Setup	28

4.3.2	What Activities Should be Performed During Administrative Setup?	29

4.5.	Buyout Process	37

4.5.1	What Activities Should be Performed During the Buyout Process?	37

4.6.	Material Handling Plan	41

4.6.1	What Activities Should be Performed During Material Handling Planning?	41

4.7.	Budget Preparation	42

4.7.1	What Activities Should be Performed During Budget Preparation?	42

4.8.	Layout and Sequencing Plan	46

4.8.1	What Activities Should be Performed During Layout and Sequencing Planning?	46

4.9.	Schedule Development	48

4.9.1	What Activities Should be Performed During Schedule Development?	48

4.10.1	What Activities Should be Performed During Tracking and Control?	51

4.10.	Construction Execution Kickoff Meeting	55

4.11.1	What Activities Should be Performed During a Construction Execution Kickoff Meeting?	55

5	The Planning Assessment Process	114

5.1.	Introduction to the Planning Assessment Process	114

5.2.	Purpose of the Planning Assessment Process	114

5.3.	Important and Influential Planning Activities	114

5.3.1	The 16 Influential Planning Activities	114

5.4.	Planning Assessment Process	116

5.4.1	The Planning Effectiveness Scorecard	116

5.4.2	Score Analysis	116

6	Pre-Construction Planning Best Practices	117

6.1.	Introduction to Pre-Construction Planning Best Practices	117

6.2.	What are Best Practices?	117

6.3.	The 25 Pre-Construction Planning Best Practices	117

6.3.1	Team Selection and Turnover Best Practices	118

6.3.2	Scope and Contract Review Best Practices	118

6.3.3	Administrative Setup Best Practices	120

6.3.4	Buyout Process Best Practices	121

6.3.5	Material Handling Plan Best Practices	122

6.3.6	Layout and Sequencing Best Practices	122

6.3.7	Schedule Development Best Practices	123

6.3.8	Tracking and Control Best Practices	124

7	Reasons for Successful or Less-than-Successful Performance	125

7.1.	Introduction to the Performance Reasons	125

7.1.1	The Most Common Reasons Projects Performed Successfully	125

7.1.2	The Most Common Reasons Projects Performed Less-than-Successfully	125

# Executive Summary

In 2003, The Foundation for Electrical Construction, funded a research project to develop a model pre-construction planning process that contractors could use to improve their planning practices. The study critically evaluated the relationship between pre-construction planning and project performance. As part of the research process, in-depth project specific information was collected on the planning effort and project outcome for several “successful” and “less-than-successful” projects. This data collection effort culminated in a detailed analysis of the planning practices of these two groups to identify clear differences between successful and less-than-successful projects. Ultimately, 27 randomly-selected companies from 11 states agreed to participate in an interview for the research project. Data was collected on 29 “successful” and 27 “less-than-successful” projects.

The planning activities that were performed on the successful projects were used to develop the model Pre-Construction Planning Process. The model process was fashioned after those projects that performed good planning and achieved a successful outcome. As such, the model planning process incorporated the best planning practices in the electrical construction industry.

The planning process of successful and less than-successful projects were compared to the model process, and ultimately, it was discovered that those planning processes that more closely matched the model resulted in more successful performance.

Ultimately, the study responded to the research questions and hypotheses. In particular, evidence supported the two hypotheses, and a tool was developed to help contractors evaluate their preconstruction planning process.

##### Planning Effectiveness and Outcomes

The research provided evidence to support the first hypothesis: Projects that experience an appropriate planning effort also experience more successful outcomes. The phrase “appropriate planning effort” was ultimately defined as planning that takes into account the inherent characteristics of a project, where inherent characteristics were taxonomized into five classes. These classes included:

- Project size, in terms of estimated cost, estimated work hours, estimated number of workers, and duration

- Initial uncertainty of the project, in terms of perceived uncertainty of the work, completeness of the design and the perceived complexity

- Bid accuracy, in terms of the accuracy of the cost estimate and the accuracy of the estimated work hours

- Existing relationships, in terms of whether the subcontractor has work with the owner or general contractor before

- Type of construction and award, in terms of type of work and whether the subcontractor was the low bidder projects.

It was ultimately discovered that projects that performed more effective planning (or performed planning activities similar to the model planning process) and had lower uncertainty and bid inaccuracy tended to perform more successfully. Indeed, various combinations of project characteristics and effective planning resulted in various chances of achieving a successful outcome. Therefore, both planning effectiveness and inherent characteristics should be evaluated together to identify the likelihood of successful performance.

##### Significant Planning Activities

Evidence was also provided to support the second hypothesis: There are significant pre-construction planning activities that distinguish a successful project from a less-than-successful project. These activities are related to:

- Pricing and cost control

- Materials and installation

- Submittals

- Field involvement

- Labor planning

Specifically, ten activities that significantly affected the performance of a project included:

- Develop field instructions, including panel or conduit schedules

- Develop installation sequence and layout drawings

- Review submittal processing procedures

- Initiate a submittal tracking and control system

- Hold a turnover meeting between the project manager and field supervisor

- Field supervisor reviews plans, specs and schedule

- Compare bid work activities and materials to planned performance

- Forecast crew requirements

- Evaluate and plan crew size and mix

- Review customer coordination meeting schedule

A total of 24 planning activities that influenced the planning component scores and significantly impact the probability of successful performance were highlighted through the research and are discussed further in the implementation manual.

##### Practical Application

The research resulted in the creation of a model Pre-Construction planning process that was based on outstanding processes used on successful electrical projects. The model process is a standardized process that electrical contractors can implement in order to formalize their planning practices and improve the effectiveness of their planning. Furthermore, the research developed a method to assess planning effectiveness by comparing actual planning to the model process and filling out a scorecard (see the implementation manual). The scorecard can be used by contractors to identify specific planning activities that need additional effort prior to project execution.

# Section 1: Introduction to the Implementation Manual

# Introduction

Electrical Contractors continue to be faced with the challenge of improving productivity in order to remain successful in an increasingly competitive industry. As a result, many contractors are searching for new ways to increase their productivity and decrease their costs in order to gain or maintain market share.

While there may not be a single measure of productivity, it is generally acknowledged that increased project and company efficiency are key components of enhanced profitability. Indeed, the competitive nature of the construction industry has motivated many contractors to search for ways to improve efficiency by increasing their quality and decreasing their costs in order to strengthen their market share. As a result, contractors are turning to “better planning” as a method for improving their efficiency and, consequently, increasing their profitability. In fact, a consensus exists in the construction industry that more formalized pre-construction planning is necessary to remain successful in an increasingly competitive industry. Accordingly, contractors are turning to pre-construction planning as one approach to improving their competitive edge.

## How the Pre-construction Planning Process was Developed

In 2003, The Foundation for Electrical Construction, funded a research project to develop a model pre-construction planning process that could be used by Contractors to improve their planning practices. The study critically evaluated the relationship between pre-construction planning and project performance. As part of the research process, in-depth project-specific information was collected on the planning effort and project outcome for several successful and less-than-successful projects. This data collection effort culminated in a detailed analysis of the planning practices of these two groups to identify clear differences between successful and less-than-successful projects. Ultimately, 27 randomly-selected companies from 11 states agreed to participate in an interview for the research project. Data was collected on 29 successful and 27 less-than-successful projects.

The planning activities that were performed on the successful projects were used to develop the Model Pre-Construction Planning Process. The model process was fashioned after those projects that performed good planning and achieved a successful outcome. As such, the model planning process incorporated the best planning practices in the electrical construction industry.

The planning process of successful and less than-successful projects were compared to the model process, and ultimately, it was discovered that those planning processes that more closely matched the model resulted in more successful performance (see Figure 3.3).

## Purpose of this Implementation Manual

This implementation manual presents the Pre-Construction Planning Process and provides guidance on the following:

- when to begin the pre-construction planning process

- which planning activities have been effective at improving project success

- who should be involved at each stage of planning

- how to successfully implement a pre-construction planning process

- what are the expected benefits of proper pre-construction planning

The Pre-Construction Planning Process can and should be used on all projects regardless of size or type of construction. However, the process should be tailored to the unique characteristics of each project, including complexity, duration and sheer volume of work.

# User’s Guide to the Implementation Manual

The Pre-Construction Planning Process is presented in a graphical flow-chart format to illustrate the interrelationship between planning activities. The process organizes 46 pre-construction planning activities into a framework that represents key planning stages, such as scope review, administrative setup and schedule development. This manual presents and discusses each planning stage, and each activity will have a set of implementation guidelines to assist with performing the activity. The process can be implemented fully or partially to accommodate each company’s unique project planning situation.

## How to Use the Pre Construction Planning Process

The Pre-Construction Planning Process targets three primary audiences:

- Companies that do not currently have a formal pre-construction planning process and who want to adopt the model process

- Companies that have a semiformal preconstruction planning process and who want to modify their process to be aligned with the model process

- Companies that already have a formal preconstruction planning process and who want to verify and adjust their process based on the information provided in this manual

The planning process is presented in a flow chart that identifies an approximate sequence of activities. However, several activities may occur concurrently unless completion of one activity is dependent on the completion of a preceding activity. The flow chart is supported by a set of implementation guidelines and checklists that guide the project manager through the pre-construction planning process.

## Development of a Pre-Construction Planning Binder

It is strongly recommended that the project manager develop a pre-construction planning binder that will contain all of the products that will result from the planning process. This binder can then be referenced during the construction management and execution processes. The binder should be divided into the ten categories of planning, as described in Chapter 3, and nearly every category of planning will have one or more products that can be added to the binder. Examples of planning products include scope review checklist and notes, team member contact sheet, written standard request for information (RFI) process, schedule of values (SOV), bar chart schedule and numerous other items. As the project manager completes the pre-construction planning process, the checklists, forms and products should be added to the binder. Then, the plans and planning products can be updated, as necessary, during the construction management process.

## Other Related Documents and Tools

Other tools associated with the Electrical Pre Construction Planning Process include a planning assessment process and a planning effectiveness scorecard (Section 3). The planning effectiveness scorecard identifies the 46 planning activities that comprise the Model Pre-Construction Planning Process and allows contractors to identify whether each activity has been performed. The planning effectiveness scorecard allows contractors to make adjustments to their planning practices in order to increase their chances of achieving a successful outcome.

Furthermore, a set of planning Best Practices and reasons for successful performance were produced and are also compiled in Section 3.

## Organization of the Manual

Chapter 3 presents an overview of the Pre-Construction Planning Process, including relevant definitions, team member involvement, and guidelines for successful implementation.

Chapter 4 identifies the pre-construction planning activities. Each set of activities has associated with it a brief instruction sheet that describes the following:

- Definition of the activity group

- What activities should be performed

- Instructions on how to implement the activity, with relevant examples

Tools that support the planning activities, including checklists, tables, charts and forms, are also included.

# Section 2: The Electrical Construction Pre-Planning Process

# Overview of the Pre-Construction Planning Process

Recent research has resulted in the development of a model planning process that has been used by some of the most successful recent projects in the electrical construction industry. In fact, those projects that used a planning process similar to the model planning process tended to perform more successfully—they achieved an average gross annual profit margin of 25% as compared to projects that were poorly planned and achieved an average profit margin of only 4%. Furthermore, projects that were well planned tended to perform above average on profitability, budget achievement, schedule achievement and labor productivity. Section 3.6.1 presents more detailed information on the relationship between planning and project performance.

## Definition of Pre-Construction Planning

Pre-construction planning prepares for a construction project for execution. In general, pre-construction planning begins during the preparation of the bid and ends shortly after the project has been executed. However, the vast majority of planning activities are performed after a contractor has been notified of a pending award. Hence, this manual covers the planning activities that are performed after notification of pending award and are generally completed before the project has been executed.

The Model Pre-Construction Planning Process includes 17 critical activities, 25 important activities and four highly recommended activities. The critical and important activities have been statistically linked to more successful project outcomes, while those activities that are highly recommended had modest statistical evidence that they contributed to better performance. As a result, the successful completion of these 46 planning activities will help prepare a project team to efficiently execute a construction project.

## Pre-Construction Planning Process

Figures 3.1 and 3.2) present the Model Pre-Construction Planning Process that resulted from a detailed analysis of the planning processes used on successful projects. The Pre-Construction Planning Process consists of ten categories and 46 activities. The next few paragraphs will identify these categories of activities, and Chapter 4 will discuss them in greater detail.

## Team Members in the Planning Process

Team member involvement in planning will typically be driven by the type of planning that needs to be completed. Table 3.1 presents a matrix of the ten planning categories and potential team members that will be involved.

## Strategies for Successful Implementation

Provided below are several strategies for successfully implementing a pre-construction planning process as a standard procedure on all projects.

- Top managers must reinforce their commitment to a standardized planning process and must ensure planning is performed on every project.

- The model planning process should be tailored to each project based on the characteristics of a project. For example, a small project might spend only five minutes on some of the activities, whereas a large project might spend several hours or days on those same activities.

- A system for tracking the success on projects that are well-planned and followed the model planning process will demonstrate the benefits of implementing a standardized planning process.

- In addition to implementing the model planning process, consider implementing a double-check system, where the supervisor double checks the planning the project manager performed. This will ensure the planning is performed consistently across the company.

- The early involvement of the field supervisor in the planning process has been shown to improve the chances for a successful project.

- Therefore, consider selecting and involving your field supervisor during the bidding stage or in the early part of the post-award stage.

- Ensure that excellent planning effort is applied to those activities that are identified as critical in Section 2. These are the activities that have the greatest potential for impacting the outcome of the project.

- The planning kickoff meeting alerts all involved team members that the planning process is officially underway, and it allows the project manager to establish deadlines for completion of activities. Likewise, the construction execution kickoff meeting brings the team members back together to review the progress of the planning and ensures all tasks have been or will be completed by the deadline. These two meetings should be held on all projects regardless of size.

- Lessons learned and a feedback loop will be an essential part of your standardized planning process. Project managers and field supervisors should share planning practices that worked well or did not work well.

## Expected Benefit

The results of the study revealed projects that received more effective pre construction planning were also more likely to achieve successful outcomes. Electrical contractors defined success as the following:

- The project was profitable.

- The customer was satisfied.

- The project resulted in repeat business.

- The project resulted in good working relationships between the electrical contractor, the general contractor and the owner.

- The worksite was safe, and there were no accidents.

- The project was completed on time.

- The workers took pride in the completed project.

- There was good communication and cooperation between the electrical contractor, the general contractor and the owner.

- The quality of the work was excellent.

- The project achieved its budget goal.

Consequently, projects that are planned using the pre-construction planning process can expect to increase their chances of achieving a successful outcome. However, it must be noted that good planning alone will not guarantee the success of a project.

Hence, good planning should be performed during the pre-construction stage, and good project management should be applied during the execution stage to maximize the chances of completing a project successfully.

##### Figure 3.1: Overview of the Model Electrical Pre-Construction Planning Process

##### Figure 3.2:  The Pre-Construction Planning Process

##### Figure 3.2:  The Pre-Construction Planning Process (continued)

## Figure 3.2: The Pre-Construction Planning Process (continued)

##### Table 3.1: Team Member Involvement in Pre-Construction Planni

### Relationship between Planning and Performance

Overall, projects that implemented a planning process that was similar to the model planning process presented in this technical document tended to outperform those projects that were poorly planned or whose planning process was significantly different from the model process. Figure 3.3 is a graph that plots the planning effectiveness score (where a higher score indicates more effective planning) against the chances of achieving a successful outcome. Projects in the upper right quadrant are those projects that were well planned and also performed well, while those projects in the lower left quadrant were not well-planned and did not perform very well.

Good planning coupled with good project management that takes into account a project’s specific characteristics will improve the likelihood of achieving successful project performance.

#### Figure 3.3: The Effectiveness of Planning versus the Chances of Achieving a Successful Outcome

# Pre-Construction Planning Activities

## Introduction to the Pre-Construction Planning Activities

While planning begins during the bidding process, the bulk of the planning takes place during the pre-construction stage—after bidding but before execution. This chapter discusses those planning activities that should begin immediately upon notification of a pending award and should be essentially completed before executing the work. These activities, furthermore, set up a project to be successfully managed, which can significantly improve the chances that the project will make a profit and be completed on time.

### Pre-Construction Planning Categories

By examining several well-planned projects, 42 significant activities that occurred during the preconstruction planning stage were identified, and four additional activities were highly recommended for performance. These 46 activities could be further divided into ten categories of pre-construction planning, including the following:

- Team selection and turnover

- Scope and contract review

- Administrative setup

- Buyout process

- Material handling plan

- Budget preparation

- Layout and sequencing plan

- Schedule development

- Tracking and control

- Construction execution kickoff meeting

Table 4.1 provides a sample checklist of the 46 activities that make up the preconstruction planning process. The activities should be checked off as they are performed to ensure all activities are completed before the work is executed. However, there are instances when a project must begin before the pre-construction planning has been completed. The checklist can then be used to ensure all of the planning activities are eventually completed and are not overlooked during the busy and often intense mobilization and execution stage.

### When Should Pre-Construction Planning Occur?

Pre-construction planning begins immediately upon notification of a pending award. The planning may continue for several days, several weeks or several months, depending on the magnitude of the project. Planning should continue until all planning activities have been completed, even if the project must be executed prior to completing the planning process. Furthermore, the planning process should provide the framework for managing the project once the work has been executed.

### Goals of the Pre-Construction Planning Stage

There are three primary goals of the pre-construction planning process:

To completely plan the project in a standardized and efficient manner to ensure that the tools, materials, equipment and labor will be available to complete the project on time and within budget

- To set up the systems that will be needed to efficiently manage the project, such as material purchasing, delivery and storage; scheduling and tracking; change management; submittal tracking; and numerous other processes that are necessary to manage a successful project

- To set the job up for successful execution and jobsite management

## Team Selection and Turnover

Team selection and turnover involves selecting the project manager and field supervisor who will be responsible for managing the job during construction execution. After the management team has been selected, a meeting should be held to formally turn over the project from the estimating stage to the project management stage. Furthermore, a planning kickoff meeting should be held to assign planning responsibilities to internal team members, such as the purchasing agent, safety director and operations director.

### What Activities Should be Performed During the Team Selection and Turnover?

The team selection and turnover process consists of four main activities. Table 4.2 provides the team selection and turnover activities in a checklist.

##### Activity 1 - Finalize selection of project manager, field supervisor and other key team members.

  - Assemble a list of project managers, and review their current work load and special skills.

  - Determine whether an ideal match can be made between the project manager and the job, and then select the project manager.

  - Assemble a list of field supervisors and review their current work load and special skills.

  - Determine whether an ideal match can be made between the field supervisor and the job, and then select the field supervisor.

  - When appropriate, work with the project manager, field supervisor, and/or the director of operations to select key foremen.

##### Activity 2 - Hold turnover meeting between estimator and project manager (when applicable).

  - Arrange a meeting time and location, and ensure enough time has been allocated to transfer knowledge between the estimator and project manager. Note: A formal turnover meeting is strongly recommended. The meeting time can vary widely from one hour to more than one day depending on the size and complexity of the project.

  - Follow and complete a checklist that describes the information that should be transferred.

Note: See Table 4.3 for a sample turnover meeting agenda.

##### Activity 3 - Hold separate turnover meeting between project manager and field supervisor.

  - Arrange a meeting time and location that will ensure enough time can be allocated to transfer knowledge between the project manager and field supervisor. Note: Again, a formal turnover meeting is strongly recommended. It is also recommended that the meeting be held at the office rather than on an existing jobsite, so the field supervisor can focus on the upcoming project without being interrupted. The meeting time can vary widely from one hour to more than one day depending on the size and complexity of the project and how many tasks must be completed during the turnover meeting.

  - Follow and complete a checklist that describes the information that must be transferred.

Note: See Table 4.3 for a sample turnover meeting agenda.

##### Activity 4 - Hold pre-job (planning) kickoff meeting with internal team members to assign responsibilities.

  - Arrange a meeting time and location, and ensure enough time has been allocated to assign planning responsibilities.

##### Invite internal team members that will be involved during the construction execution process, such as project manager, field supervisor, accounting, purchasing, Director of Field Operations, etc.

  - Follow and complete a checklist that describes the planning activities that must be completed and who is responsible for completing them.

Note: See Table 4.4 for a sample planning kickoff meeting agenda.

## Scope and Contract Review

A scope review involves reviewing all contract documents that will be used to execute the work and produce a high quality end product. It involves becoming familiar with the detailed project requirements, including the systems that will be installed, equipment that must be powered, the materials that are specified, and the labor that will be required to complete the job successfully. A contract review involves reading the entire contract agreement, including general and special conditions to identify any unusual or special provisions that must be accomplished as part of the scope of work.

### What Activities Should be Performed During a Scope and Contract Review?

The scope and contract review process consists of eight activities. Table 4.5 provides the scope and contract review activities in a convenient checklist.

##### Activity 5 - Review contract for unfavorable or high risk clauses (performance recommended)

  - Complete the Contract Review checklist (Table 4.6).

  - Identify all required bonds, permits, certificates and insurance requirements.

Example: An electrical contractor might be required to provide a performance and payment bond or a completion bond. The electrical contractor might also be responsible for obtaining the electrical permit and must provide a certificate of insurance demonstrating that they have the insurance required by the contract.

  - Review contractual billing requirements.

Example: The owner typically will require that pay requests be submitted by a date identified in the contract. Furthermore, the electrical contractor’s own accounting department will often identify a date by which they would like to receive both draft and final pay requests. These dates should be identified upon initiation of the project to ensure timely payment is received.

  - Review and understand procedures for requesting change orders. Note: Review the contract and specifications carefully to understand the procedures that must be followed to request a change order and recover the additional time or money spent on work items. It is strongly recommended that the electrical contractor set up a change management process and ensure all team members understand and follow the process.

  - Identify whether disputes must be resolved through alternative dispute resolution (ADR), such as mediation or arbitration. Note: Alternative dispute resolution (ADR) requirements are typically covered in the contract or specifications. Be sure to understand whether ADR is contractually required and whether it is binding or non-binding.

##### Activity 6 - Project manager reviews plans, specifications and schedule

  - Order extra sets of plans and specifications, if necessary. Note: Be sure to order enough plans so that there is at least one set in the main office (project manager’s copy), two sets in the field trailer (field supervisor’s copy and the marked up copy) and one or more copies that can be distributed to foremen.

  - Complete the Scope and Schedule Review Checklist (Table 4.7).

  - Compare the scope identified in the contract to the scope from the bid submission to verify that they match.

Note: The bid submission letter will typically identify the scope of work, clarifications and inclusions/exclusions. This letter should be compared to the scope identified in the contract to determine if there is a discrepancy. Any discrepancy should be discussed with the estimator and company officer to determine how to resolve the discrepancy.

  - Compare the plans to the specifications to identify any discrepancies.

Example: There are many ways the plans can differ from the specifications. In general, the specifications will supersede the plans.

  - Review the customer-furnished schedule to determine whether the electrical work can be completed within the contractual timeframe, and plan the work strategy based on this finding.

Example: Occasionally, the time required to complete the electrical work is longer than the contractual duration. In such cases, the electrical contractor will be required from the beginning to plan for overtime, overmanning, or acceleration. The need to accelerate should ideally be established during the bidding stage, but the techniques for accelerating the work will be selected after award.

##### Activity 7 - Field supervisor reviews plans, specifications and schedule

  - Complete the Scope and Schedule Review Checklist (Table 4.7)

  - Review best field practices or lessons learned.

Example: If the company has a book of best field practices or lessons learned, the field supervisor should review this book before planning the execution of the new project in order to avoid “reinventing the wheel.” If no best practices or lessons learned exist, the field supervisor can talk to other field personnel or hold a meeting to identify the best methods for executing the new project.

  - Identify value engineering or prefabrication opportunities (see also Activity 11).

Example: While reviewing the plans and specifications (and after reviewing best practices and lessons learned), the field supervisor should begin assembling a list of installation methods, materials or prefabrication of systems that could result in a savings to the electrical contractor. Note whether the technique requires owner or engineer approval and whether the savings must be shared with the owner. One of the most common changes is the running of conduit underground instead of overhead. It usually results in a savings and is typically approved by the engineer.

  - Identify labor requirements and begin selecting foremen.

Example: The field supervisor should identify the number of workers and foreman that will be required each week of the project. This can be determined by creating a manpower loading chart. The field supervisor can select foremen to cover specific systems or specific areas (such as one foreman per floor on a multi-story building). Foremen can also be selected based on skills, such as experience working on a hospital or a power plant.

  - Identify special tools that will need to be purchased or assembled

Example: Along with the list of potential cost saving changes that are identified while reviewing the plans and specifications, the field supervisor should also assemble a list of special tools that might be needed to install the materials identified in the contract documents or to complete the installation more efficiently.

##### Activity 8 - Create list of issues that need to be resolved and begin the request for information (RFI) process

  - Establish a request for information (RFI) process (see also Activity 16) and create a list of questions that require clarification.

Example: While reviewing the plans and specifications, the field supervisor should also assemble a list of discrepancies and issues that need to be resolved in order to execute the work efficiently. This list will kick off the request for information (RFI) process and should be resolved as quickly as possible. The electrical contractor should consider holding a special meeting to get these issues resolved.

  - Formalize the RFIs by assigning them a trackable number and submitting them to the owner/CM/GC.

Note: Activity 16, which is an administrative procedure that involves initiating an RFI process, is closely related to Activity 8. Most companies have a formal RFI process that includes a hierarchy of personnel who must review the RFI and the standard submission format, such as e-mailed, faxed or mailed RFI form with a clear routing sequence. All RFI should have a unique number that permits them to be tracked for resolution.

##### Activity 9 - Conduct site visit (recommended).

  - Complete the Site Visit Checklist (Table 4.8).

  - Examine site access and layout, including parking, material delivery points, and material lay down and storage.

Example: Site logistics is especially important on small, bounded sites. You should determine:

- whether workers can park on the site or must park in a nearby garage for a fee

- whether materials can be delivered at any time or only at certain hours of the day

- whether a material and/or office trailer will be permitted on the site

- whether materials can be stored on the site under secure conditions

  - Identify locations and availability of material and personnel lifts, elevators, cranes, scaffolding and forklifts.

Example: Verify whether lift, crane, and machinery time must be scheduled in advance. Also determine whether you must supply your own scaffolding or whether it will be furnished by the general contractor.

  - Create a plan for installing temporary power (when applicable).

Example: While on the site visit, sketch out a plan for installing temporary power and lighting, and determine how these systems will be maintained. A carefully thought out temporary power and lighting plan can prevent spending more than was estimated to install and operate these systems.

  - Verify existing conditions and compare them to the conditions shown on the plans and described in the specifications.

Example: If the site contains facilities that must be renovated or demolished or if the site has existing structures or utilities, a site visit should be conducted to compare the information on the plans to the actual conditions on the site. For example, if a building is being renovated, the plans will show the locations of all existing systems (mechanical, electrical, plumbing, etc.). These locations should be verified and marked up on the plans to avoid conflicts with coordination later.

##### Activity 10 - Compare estimated (bid) work activities and materials to planned performance

  - Compare the estimator’s concept of how to perform the work to typical field operations and document the differences.

Example: An estimator typically has less time to plan out the work sequence, materials and methods than the project manager and field supervisor. As a result, the project manager and field supervisor should compare how they plan to perform each work item to how the estimator estimated the same work item. For example, the estimator may not have planned to perform any prefabrication of systems, but the project manager might identify several work items that could be prefabricated prior to installation.

  - Discuss unclear methods or discrepancies with the estimator.

Note: If the project manager or field supervisor is unclear how the estimator planned a particular work item, they should seek clarification to make sure they do not unnecessarily expend time, money or work hours.

  - Determine the cost difference between the as-bid and planned performance of the work.

Example: If a less expensive work method can be identified, the project manager should document the cost savings in the cost control report so that the additional funds can be added to profit or cover cost overruns.

##### Activity 11 - Identify value engineering and prefabrication opportunities and how to simplify the work

  - Review value engineering (VE) or prefabrication opportunities that were identified in the turnover meeting between the estimator and project manager.

  - Review procedures for formally requesting VE consideration, if required.

Example: Some VE changes involve substituting materials or modifying installation routes, which might require approval by the owner or architect. Other VE changes may be strictly associated with methods and might not require approval. If approval is required, the project manager should understand the timeline and procedures for receiving approval to determine whether the VE suggestion will be feasible.

  - Search for and identify additional VE and prefabrication items.

Note: In addition to the VE and prefabrication opportunities that were identified during the turnover process, the project manager and field Supervisor should seek additional opportunities that would result in a time or cost savings. Opportunities that do not require customer approval are particularly appealing.

  - Identify additional ways to simplify the work.

Example: Simplification might involve, for example, ordering wire in bulk on reels so that it is readily available on the site. Or, simplification might involve marking conduits with tags to identify the wire that must be pulled and where it is initiated and terminated. There are numerous ways the field supervisor and foremen can simplify the installation process, and these methods should be explored during the scope review process

  - Price out the cost difference between the as-bid and VE options.

Note: This is an exercise performed by the project manager to determine the cost savings or cost expenditure to implement a VE option. Although the goal is typically cost savings, occasionally a VE option will be selected to save time.

##### Activity 12 - Prepare construction takeoff

  - Take off the materials, equipment and systems in the order they will be constructed.

Example: The construction takeoff is often performed to (1)

- verify the bid quantities are correct

- calculate accurate quantities for ordering materials and equipment

- begin sequencing the work

- validate the cost estimate

It is an important exercise that can identify problems and opportunities early in the planning process.

  - Code each plan sheet as you take it off so that you can return to it later and immediately identify the quantity of various materials shown on the sheet.

Example: A common method to prepare a quantity takeoff is to color-code the plan sheets for easy reference. Each system should be coded individually, and a legend should be provided.

  - The final quantities should be identified by the units in which they will be purchased.

Example: If wire will be purchased by reel, then the number of required reels should be identified rather than the linear feet of wire. The construction takeoff should be the first step to purchasing the actual materials needed to complete the work.

  - All assumptions should be noted on the quantity takeoff sheets.

  - Be sure the quantities that are estimated include a waste factor.

Example: An accurate quantity takeoff will provide a definitive amount of conduit needed to complete the work. However, since most conduit will need to be cut or bent to fit its exact placement in the system, a waste factor of 5%10% should be added to the quantity.

  - Compare the construction takeoff to the bid takeoff to identify significant differences or discrepancies.

Example: It is unlikely that the bid estimate and the construction takeoff will match exactly. However, most quantities of materials and labor should be within 5% of the bid amount.

  - Significant differences might be an indication of a bid mistake or a misunderstanding of how the work will be performed. Any discrepancies should be reviewed by the project manager and estimator.

## Administrative Setup

The administrative setup involves creating standardized paper and computer files that will be used to manage correspondence, changes, submittals, schedules and progress. A standardized administrative setup process is necessary to run an organized and efficient project.

### What Activities Should be Performed During Administrative Setup?

The administrative setup process consists of six activities. Table 4.9 provides the administrative setup activities in a convenient checklist.

##### Activity 13 - Set up project files and create contact list

  - Use the File System Checklist (Table 4.10) to create paper files.

  - Create a contact sheet that lists all team members and their company contact information.

Note: The list should include owner, architect, engineer and general contractor contacts. It also might include consultants, facility occupants, maintenance staff, city inspectors and all internal team members (project manager, field supervisor, foremen, administrative assistant, etc.).

##### Activity 14 - Set up computerized tracking and control system (forms, database, schedule, and tracking)

  - Verify the accounting office has assigned a project number and entered initial information in the cost control system.

Example: During the bidding stage or upon notification of award the estimator may have requested the accounting office enter the project into the accounting database. If no project number has been assigned, the project manager should request a number from the accounting department.

  - Use the File System Checklist (Table 4.10) to create computer files.

If a separate project management software system is used, set up the project in the system. Example: Commercially available project management software is available, as well as web based project management systems. Most software can be tailored to the needs of the company. The software should be tailored to reflect the processes established by the company. If a commercial software is not used, the project manager can set up the files in a word processing and spreadsheet program.

  - If a separate computer scheduling system is used, set up the schedule in the system (see Activity 37).

Example: The most common software available includes Microsoft Project and Primavera Project Planner. Prior to entering activities in the schedule, the project manager and field supervisor should develop a sequence of work.

##### Activity15 - Initiate a change management system

  - Review the contract to identify required change order, field change and time-and-materials procedures.

Note: If the contract does not specifically address change orders, field changes and general change procedures, the project manager or a company officer should request a separate meeting to discuss the company standard procedures.

  - Review your company’s standard procedures for initiating, requesting, and processing change orders and field changes.

Example: A standard change management system is intended to protect both parties and minimize disputes. Figure 4.1 presents a sample standard change management procedure. This example can be tailored to each company’s individual need. Figure 4.2 provides a sample change order proposal form, and Figure 4.3 provides a sample field change directive form.

  - Develop a log with sequential numbering to track all changes, including change orders, field changes and time-and-materials requests (Table 4.11).

Example: Table 4.11 can be reconstructed in a spreadsheet program. Also, many commercial project management software programs provide a method for entering and tracking changes.

#### Figure 4.1:  Standard Change Order Procedure

Types of Changes

Three types of changes are commonly encountered in construction:

- request for quotation

- field change directive

- disputed changes to the work

A request for quotation (RFQ) typically occurs when the customer acknowledges a change is needed and requests an estimate of the cost prior to approving the change. A field change directive is an order given in the field to immediately execute a change before the cost of the work has been negotiated. Disputed changes are changes to the work that are necessary to continue making progress but are not acknowledged by the customer as a change to the contract requirement. Disputed changes are difficult to recover and require careful documentation to maximize the chances of receiving compensation.

Request for a Quotation Procedure

- Enter the change order request in the change order log (Table 4.11) and assign it a C.O. number. The status will remain “open” until the C.O. has been approved by the customer.

- The project manager should develop a written recap of the requested scope of work, identifying all inclusions, exclusions and qualifications.

- The project manager should develop a cost estimate for the scope of work. If the scope is large or complex, the project manager may request assistance from an estimator.

- The cost estimate should include direct costs (labor, materials, equipment, subcontractors, expediting fees, etc.), indirect costs (jobsite overhead, home office overhead, insurance premiums, bonds, etc.), and profit (which is added after all other costs have been tallied).

- The project manager will fill out a change order proposal (Figure 4.3) with the scope of work and quoted price.

- The change order proposal is forwarded to the customer for approval.

- Once the approval has been received, the status in the change order log is changed to “approved,” and the work is implemented

Field Change Directive Procedure

- A field change directive (FCD) is often issued by the owner’s representative, architect/engineer or general contractor. The field superintendent and foreman are authorized to accept an FCD only if the issuing authority signs a field change form (Figure 4.4).

- If the FCD is received by a foreman, the foreman should notify the field supervisor immediately.

- FCDs are typically performed on a time and materials (T&M) basis.

- The issuing authority and the field supervisor/forman should verbally agree to the scope of work, and this scope should be documented on the field change form. The foreman and issuing authority should each sign the field change form.

- The FCD is entered into the change order log (Table 4.11) and assigned a C.O. number. The status will remain “open” until the FCD has been paid by the customer.

- All labor, materials, equipment and subcontracts that are used to complete the work should be annotated on the field change form.

- The field change form is then forwarded to the project manager, who will add the markup and calculate the total cost of the work.

- The field change form is then forwarded to the accounting department where it will be entered into the accounting system as a separate line item and invoiced during the next billing cycle.

- Once the FCD has been paid, the status in the change order log is changed to “approved.”

Procedure for Disputed Changes

- The disputed work should be processed similar to an RFQ.

- The project manager and/or field supervisor should develop a detailed written scope of the work that is outside the original contract scope of work, identifying plans, specifications, other contract documents and qualifications that support their position.

- The project manager should develop a cost estimate for the scope of work. If the scope of large or complex, the project manager may request assistance from the estimator.

- The cost estimate should include direct costs (labor, materials, equipment, subcontractors, expediting fees, etc.), indirect costs (jobsite overhead, home office overhead, insurance premiums, bonds, etc.), and profit (which is added after all other costs have been tallied).

- The project manager will fill out a change order proposal (Figure 4.3) with the scope of work and quoted price.

- The disputed change order proposal is entered into the change order log (Table 4.11) and assigned a C.O. number

##### Activity 16 - Initiate a request for information (RFI) tracking and processing system

  - Develop a log with sequential numbering to track all requests for information (RFIs) (Table 4.12).

Note: Many of the commercial project management software programs will provide a method for initiating and tracking RFIs. However, Table 4.12 can be reconstructed in a spreadsheet for the purpose of tracking RFIs.

  - Determine whether RFIs will be submitted by e-mail, fax or postal mail.

  - Review your company’s standard procedures for processing RFIs and use a company standard form for submitting RFIs.

Example: Figure 4.4 presents a sample company standard RFI procedure, and Figure 4.5 identifies a sample RFI form. However, most commercial project management software programs can be tailored so that the RFI form bears your company name and logo.

  - Ensure each RFI also identifies a proposed solution and price change.

Example: For a quick resolution to your question, identify a possible solution to the issue. For example, if there is a conflict between a conduit and a heating duct, identify a possible relocation route for either the conduit or the duct. The engineer will only have to check your proposed reroute rather than develop an alternate route, which would take more time.

#### Figure 4.4:  Standard Request for Information Procedure

TYPES OF INFORMATION

A Request for Information (RFI) is a formal process for receiving more details about a work process and/or alerting the customer to a potential deficiency in the contract documents. The types of information that must be cycled through the RFI process include: discrepancies between plans and specifications; incomplete design details; conflicts between systems; clarifications about design intent; identification of a changed condition with a request for instructions; missing scope items that would produce a complete product; and many other issues.

REQUEST FOR INFORMATION PROCEDURE

- A hierarchy should be followed when identifying and processing RFIs. Crew members should address questions to their crew foreman. The crew foreman should fill out the request for information form (Figure 4.6) and forward it to the field supervisor. The field supervisor should review the form and forward it to the project manager. The project manager should review the form and process it.

- Fill out the request for information form, including a detailed description of the requested information and the date that a response is required. When possible, identify a possible solution to a problem, which might speed up the response time and result in a favorable outcome to the electrical work.

- The project manager or field supervisor should enter the RFI in the request for information log (Table 4.12) and assign it an RFI number. The status will remain “open” until the RFI has received a response from the customer.

- The RFI form is forwarded to the customer for a response.

#### Figure 4.5:  Standard Request for Information Form

##### Activity 17 - Initiate a submittal tracking and processing system

  - Develop a log, with sequential numbering, to track all submittals, including those of vendors and subcontractors (Table 4.13).

Example: Review the specifications to determine whether the customer has included a submittal log. If so, this information can be transferred to your own company tracking system. If not, use either commercial project management software or create a spreadsheet. Go through each section of the specifications to determine whether it identifies a submittal that you or your suppliers or subcontractors are responsible for providing. Enter this information in your submittal tracking log.

  - Review your company’s standard procedures for processing submittals and use a company standard form for submissions.

Example: Figure 4.6 presents a sample company standard submittal procedure, and Figure 4.7 identifies a sample submittal transmittal form. However, most commercial project management software programs can be tailored to include a standardized company form.

  - Verify that each submittal processing form identifies a “respond no later than” date, which is associated with timely ordering and delivery of the materials and equipment.

Example: Be sure to review the work sequence and schedule carefully to identify when each material or equipment item will be installed. Then, annotate on the submittal form the date you will need an approval in order to order and receive the materials or equipment on time to avoid a delay. This technique also puts the architect/engineer on notice in case there is a delay that is disputed later.

#### Figure 4.6:  Standard Submittal Procedure

TYPES OF SUBMITTALS

Three types of submittals are commonly encountered in construction:

- shop drawings

- product data/cut sheets

- samples

Shop drawings reflect the manufacturer’s or equipment designer’s technical details for the product specified in the plans and specifications and usually include dimensions and quantities. Product data/cut sheets provide information about the make, model, size, capacity, performance and finish of a product specified in the plans and specifications. Samples are physical representations of the specified product, such as paint color, brick finish, floor tile, metal roof style and color, and so on.

SUBMITTAL PROCESSING PROCEDURE

- The project manager should review the plans and specifications to identify all of the submittals that are required by the contract documents and begin filling out the submittal log (Table 4.13).

- While preparing purchase orders for the materials and equipment, the required type and number of submittals should be identified on the purchase order form (Figure 4.11).

- When the submittal item is received from the subcontractor/supplier/vendor, the project manager should carefully review the submittal to make sure the proposed product conforms to the plans and specifications.

- The front sheet of each submittal should be stamped with the company submittal stamp and initialed by the project manager to signal a review has been completed.

- If binders of submittals are not required, the project manager should fill out a submittal transmittal form (Figure 4.8) and forward the proper number of copies to the customer for review and approval. If binders are required, begin assembling binders of all submittals according to their CSI section. The submittal log should be updated to reflect the date sent to the customer.

- One copy of each submittal should be retained for the files, and one copy should be forwarded to the field. Make sure the copies are marked with their preliminary status (such as, “draft – For Information Only”).

- Once the submittal has been reviewed and returned by the customer, one copy should be returned to the subcontractor/supplier/vendor, and the submittal log should be updated.

- If the submittal was approved, one approved copy should be retained for the files and one copy sent to the field with the annotation, “approved for construction.”

- If the submittal was rejected, the submittal process will have to be repeated.

##### Activity 18 - Develop a “Labor Requirements/Expectations” letter (for background check, etc.) (Performance recommended)

  - For projects that have special requirements, such as drug testing, background check or special safety training, develop an “expectations” letter that must be reviewed and signed by crew members.

Example: See Figure 4.8 for a sample labor requirements and expectations letter.

  - For projects that will require hiring workers from the union hall, develop an “expectations” letter that must be reviewed and signed by crew members.

Example: See Figure 4.8 for a sample labor requirements and expectations letter.

## Buyout Process

The buyout process involves purchasing all materials and equipment—and hiring all subcontractors—that will be necessary to complete the project. Consequently, it involves evaluating material pricing, reviewing the qualifications of vendors and subcontractors, selecting the successful parties, issuing purchase orders and initiating the submittal process.

### What Activities Should be Performed During the Buyout Process?

The buyout process consists of six activities. Table 4.14 provides the buyout activities in a convenient checklist. Note that submittal processing and tracking (Activity 24) should be conducted in conjunction with “Initiate a submittal tracking and processing system” (Activity 17).

##### Activity 19 - Request and/or review subcontractor/supplier/vendor prices and qualifications

  - Request subcontractor/supplier/vendor pricing if it was not requested or received during the bidding stage.

Example: Two scenarios are possible. In the first scenario, actual pricing was requested and received from interested subcontractors/suppliers/vendors during the bidding stage. In the second scenario, estimated pricing was obtained from a cost database. If actual pricing was quoted, the electrical contractor may want to request “best and final” pricing (also called “buy pricing”) from all interested subcontractors/suppliers/vendors. If estimated pricing was obtained from a database, the electrical contractor will want to request actual quotations.

  - Compare actual subcontractor/supplier/ vendor scope of work with the scope identified in the subcontractor/supplier/vendor bid submission.

Example: The subcontractor/supplier/vendor scope of work should be discussed when the quotation is requested. Ideally, the project manager will hold a meeting to review the scope with each potential subcontractor/supplier/vendor. Then, after quotations have been received, the project manager should compare the submitted scope of work with the actual scope of work to identify any discrepancies. These differences will need to be resolved prior to making an award.

  - Evaluate the subcontractor/supplier/vendor qualifications.

Example: The project manager should evaluate the following questions:

- Has the subcontractor/supplier/vendor performed this type (and/or size) of work before?

- Has the electrical contractor worked with the subcontractor/ supplier/vendor before?

- On previous jobs, has the subcontractor/ supplier/vendor performance been satisfactory?

  - Compare pricing and qualifications among the subcontractors/ suppliers/vendors.

Example: Use a spreadsheet (or commercial project management software) to compare price and qualifications of the subcontractors/ suppliers/vendors (see Table 4.15, for an example).

##### Activity 20 - Negotiate pricing and contract conditions, and select subs/suppliers/vendors

  - Discuss potential cost savings with potential subcontractors/suppliers/ vendors.

Example: Many suppliers can offer significant discounts if materials are purchased in bulk rather than weekly. Furthermore, suppliers and subcontractors may be able to offer value engineering ideas, such as material substitutions or innovative purchasing techniques. These savings should be discuss with potential subcontractors/suppliers/vendors before making a final selection.

  - Review the contract or purchase order terms and conditions with potential subcontractors/suppliers/vendors prior to award.

Example: Specifically discuss:

- shipping and delivery terms, especially if special delivery or packaging is required

- who will conduct an inventory when the materials are delivered

- documenting, returning and replacing damaged materials

- consequences of early or late deliveries

- signing authority

- other terms specific to each project

  - Select all successful subcontractors/suppliers/vendors, and issue a letter of intent (if necessary).

Example: After carefully reviewing pricing and qualifications of all sub-contractors/suppliers/ vendors, select the successful parties. These companies should be notified by phone, and a letter of intent (Figure 4.9) should be issued (by fax) if there will be a delay in processing the contract or purchase order. The letter of intent will authorize the contractors/suppliers/vendors to purchase materials or begin work on the project while the official paperwork is being processed.

##### Activity 21 - Develop and issue purchase orders and contracts for materials and equipment

  - Develop the purchase orders or contracts for subcontractors/suppliers/ vendors.

Example: Figure 4.10 presents a sample purchase order for materials. Standard subcontracts, such as AIA or AGC standard forms, should be used in place of a purchase order for work that involves materials and labor because the subcontract will outline responsibilities, liability, insurance, and indemnification. The purchase orders are typically prepared by the accounting department or by the project manager with the assistance of the accounting department.

  - Process and issue the purchase orders or subcontracts.

Note: Ensure a company officer from both the electrical contractor and the subcontractor/supplier/vendor has signed the purchase order or subcontract to acknowledge the terms and conditions. The purchase order of subcontract should also note whether the materials, equipment or services are to be ordered or supplied immediately or whether the supplier should hold the order until an order and delivery date has been established.

##### Activity 22 - Order long-lead-time materials and equipment

  - Compare the sequence, schedule and materials/equipment to identify long-lead-time items.

Example: When reviewing the scope of work, the project manager and/or field supervisor should document those materials and equipment that might have a long lead-time or might impact the schedule if delivery is delayed. If these items were not annotated during scope review, the project manager and/or field supervisor will need to carefully re-review the scope and schedule to identify long-lead time items that could impact work progress.

  - Negotiate and issue purchase orders and subcontracts for long-lead-time items before negotiating standard purchase orders and subcontracts.

Example: If a material or equipment item might require a long lead time before it can be delivered (such as generators or transformers, which must be manufactured), then the purchase of the item should be negotiated and authorized before non-long-lead-time items are evaluated and purchased to ensure timely ordering and delivery.

  - Issue a letter of intent or purchase order immediately to release long-lead-time items for order and delivery.

Example: Often, long-lead-time material and equipment pricing is negotiated prior to the electrical bid submission. Then, after the electrical contractor receives the notification of a pending award, the project manager can immediately issue a letter of intent or purchase order requesting that the item(s) be ordered. The letter of intent or purchase order can be faxed, with a hard copy mailed the same day, to expedite the ordering process.

##### Activity 23 - Request submittals, cut sheets and shop drawings

  - Upon issuing the contract document, the subcontractor/supplier/ vendor should be requested to assemble and submit samples, cut sheets, or shop drawings.

Example: As part of the contract agreement, the subcontractors/suppliers/ vendors should be requested to submit items as identified in the specifications. The electrical project manager should identify in the contract document which submittals are required, and these items should be verified with the subcontractors/suppliers/vendors. Occasionally, submittals are requested during the bidding stage as part of the subcontractor/supplier/vendor bid submission, and some cut sheets are available through a cost database. Therefore, these submittals might already be available for processing.

  - Identify a deadline by which the submittals, cut sheets and shop drawings must be submitted to the electrical contractor.

Example: Two submittal strategies are possible. In the first strategy, the electrical contractor might be required to assemble a binder with all of the required submittals in it so that all submittals can be processed at the same time. In the second strategy, the electrical contractor might be able to submit items in the order of their installation or as they are received from subcontractors/suppliers/vendors. In either case, the electrical project manager should review the schedule and identify a deadline for receiving each submittal so that it can be processed in a timely manner to avoid delays. This deadline should ideally be identified in the contract document (purchase order or subcontract).

##### Activity 24 - Develop and process log and book of submittals, cut sheets and shop drawings

  - Develop a log with sequential numbering to track all submittals, including those of vendors and subcontractors (see also Activity 17 and Table 4.13).

Example: Review the specifications to determine whether the customer has included a submittal log. If so, this information can be transferred to your own company tracking system. If not, use either commercial project management software or create a spreadsheet. Go through each section of the specifications to determine whether it identifies a submittal that you or your suppliers or subcontractors are responsible for providing. Enter this information in your submittal tracking log (see Table 4.13, for a sample).

  - Assemble two or more binders of all draft and approved submittals.

Example: At least two complete binders of submittals should be assembled so that the project manager has a copy in the office and the Field Supervisor has one on the jobsite. If a complete binder of submittals will be processed for approval by the architect/engineer, additional copies of the binder will be required so that the architect/engineer and the owner each receive a copy.

  - Submit and track required submittal items.

Example: Use the submittal log (Table 4.13) to track receipt and approval of all submittals. Issue dunning letters, as necessary, if the architect/engineer does not approve or return the submitted items by the requested deadline.

## Material Handling Plan

Material handling planning involves establishing processes for ordering, receiving, staging and storing major materials and equipment on the jobsite or at a storage location. As part of the material handling planning process, participants should also review general site logistics to ensure the materials and site facilities are located efficiently and promote maximum productivity of workers and equipment.

### What Activities Should be Performed During Material Handling Planning?

Material handling planning consists of two activities. Table 4.16 provides the material handling planning activities in a convenient checklist.

##### Activity 25 - Develop material delivery and handling plan

  - Review the “Material Delivery/Storage and Site Logistics Best Practices” (see Table 4.17).

  - Establish and maintain a file of delivery receipts and packing slips.

Example: The person who is in charge of receiving materials and equipment should maintain the file of delivery receipts and packing slips.

Other individuals who might receive shipments (in the main office or at the site office) should ensure that the material/equipment delivery manager ultimately receives the receipts so that accurate records can be maintained.

  - Establish a material and equipment delivery and storage log.

Example: Table 4.18 provides an example of a material and equipment delivery and storage log. The log should be maintained by the person in charge of receiving materials and equipment.

  - Create a material and equipment delivery schedule.

Example: During the scope and schedule review (or the buyout process), the project manager and field supervisor should annotate when materials and equipment will be ordered and delivered to the site. These annotations should be developed into a formal schedule of deliveries. This schedule should be distributed to the material manager, and the schedule should be reviewed and updated regularly by the material manager and field supervisor.

  - Establish standard procedures for receiving, handling and storage of materials and equipment.

Example: The formal procedures should document delivery hours, site entry and exit points, site circulation and procedures for delivering materials to the work location or storage area. For example, the plan should outline who will determine the unloading point (work location or storage location) and how this information will be conveyed to the vendor. The plan should also identify authorized signing agents and the name and contact information of the material manager and field supervisor. The plan should also identify how to annotate delivery, inspection, acceptance and storage location of all materials and equipment delivered to the site. The procedures should be strictly enforced to maximize the efficient and orderly receipt of materials.

##### Activity 26 - Develop material storage and staging plan

  - Complete the site logistics review checklist (Table 4.19).

  - Review the “Material Delivery/Storage and Site Logistics Best Practices” (Table 4.17).

  - Develop a storage site layout that identifies where the materials and equipment are stored.

Example: A storage site layout should be developed that shows the locations of all major groups of materials or equipment as well as consolidated storage locations. An identification system should be developed so that materials and equipment can be logged in and tracked by their storage location identification.

## Budget Preparation

Budget preparation involves developing a cost code scheme and breaking down materials, labor and overhead into discrete categories that can then be used for billing during execution. As part of the budgeting process, a breakdown of costs for tracking progress must be performed, and this breakdown may be different than the cost breakdown identified on a schedule of values used for billing. Developing a budget (for tracking) and schedule of values are the key elements of cost and cash flow management.

### What Activities Should be Performed During Budget Preparation?

The budget preparation process consists of three activities. Table 4.20 (page 76) provides the budget preparation activities in a convenient checklist.

##### Activity 27 - Develop, review or expand the Cost Code Scheme.

  - Decide whether to use a cost   code scheme based upon 16 specifications divisions or 50 specifications divisions.

Note: The Construction Specifications Institute (CSI) formerly promoted 16 specifications division. However, this format was modified in 2004 and now encompasses 50 divisions. You should use the format that is standard in your company and the same format that was used in the bid preparation stage.

  - Review the cost estimate to identify the existing cost code breakdown, and decide whether additional breakdown is necessary.

Note: During the preparation of the cost estimate, it is likely that the estimator developed an initial cost breakdown based on the standard company cost codes. This breakdown should be reviewed to identify whether additional codes will be needed to track and bill the work.

Review the company standard list of cost codes and decide which codes will be needed for breaking down the work for tracking and billing.

Example: A cost code scheme can provide an outline for breaking down materials, labor and equipment. Keep in mind that this breakdown should reflect how the work will be performed, and it should be as accurate and detailed as practical for tracking and billing.

  - Add new codes for work items that are not on the standard list.

Example: The standard list will typically contain only “standard” items encountered on most projects. If your job, for example, calls for installing stadium lighting that must be lifted by a crane, you probably won’t have the proper line items to cover this specialty work. Therefore, you will need to work with your accounting department to temporarily create new codes that cover the specialty items on your project.

  - Assign additional codes to specify the costs associated with material, equipment, labor, subcontractors and other miscellaneous costs.

Example: Each line item or task is usually divided into material costs and labor costs. An example for making such a division might be to add a dash after the cost code and then add the additional code. For example, if the cost code for cable is 16100 and the additional code for material is M and for labor is L, then the code for cable (material) would be 16100-M and for cable (labor) would be 16100-L.

##### Activity 28 - Develop budget by breaking down labor, material, overhead and profit costs.

  - Create the budget in concert with the labor and materials tracking report.

Example: One of the main purposes of a budget is to track material and labor costs.

Therefore, you should decide which cost and work items you want to track, and develop your budget to match the items that will be tracked. Table 4.22 presents a sample budget breakdown and tracking spreadsheet.

  - Establish a budget with sufficient line items to identify potential problems yet simple enough to avoid time-consuming data entry.

Example: Remember that the goal of material and labor cost tracking is to make sure the project cost is not exceeding the estimated amount. Therefore, make sure there are enough line items to pinpoint a specific problem work item. However, the budget should not be so detailed that it requires an unbalance proportion of time to enter all of the cost data.

  - Verify that labor and materials can and will be reported according to the budget line items.

Example: The true test of a good budget is to identify whether the field can track labor against the line items. The field supervisor should be able to tell you if the budget is too detailed and whether it would require too much time to track labor against all of the line items. If the budget appears to be too detailed, consider rolling up or combining several line items into summary items.

##### Activity 29 - Develop schedule of values.

  - Review the contract to identify the contractual format and process for developing a schedule of values.

Example: Some contracts specify that an AIA Form G703 be used to submit the schedule of values for approval. If a standard AIA form is not specified, prepare a company schedule of values (see Table 4.23 for a blank sample form).

  - Create the schedule of values in concert with the billing process.

Example: Review the company billing procedures (Figure 4.11) for a sample company standard billing procedure). Then, while preparing the schedule of values, think about how easy or difficult it will be to determine the percent complete of each of the line items. If the process is difficult, you might need to add more details to accurately capture the work that has been completed.

  - Consider “rolling up” the budget, so that the schedule of values has the same summary line items but fewer sub-line items.

Example: One way to develop the schedule of values is to copy the budget but eliminate the detailed line items. Instead, the summary line items are used.

#### Figure 4.11: Standard Billing Procedure

TYPES OF BILLING

Most larger projects will require progress billing, where a schedule of values (SOV) is developed to break down and bill portions of the work. These procedures cover the progress billing procedure. However, other types of billing that might occur include requisitions, time and materials (T&M) pay request, cost plus pay request, and unit price billing.

BILLING PROCEDURE

The first step to the billing process involves the creation of a schedule of values (Figure 4.24) that breaks down the work into discrete line items that can be tracked and billed. The SOV must be approved by the customer prior to the first billing cycle.

The accounting department will initiate the monthly billing process by distributing the previous month’s bill to the project manager for updating.

The project manager will update the percent complete of each line item on the SOV using a pen or pencil. It is recommended that each line item be overbilled by about 10%.

The project manager returns the marked-up bill to the accounting department, who will then revise the percent complete in the accounting system and print a new bill.

The accounting department will obtain lien waivers from all subcontractors and suppliers who have line items on the bill.

The bill will be submitted to the customer for review, approval and payment.

Once a month, the accounts receivable will be updated so that all project managers can view the most current payments received on their projects.

It is the project manager’s responsibility to follow up on open receivables on a weekly basis.

## Layout and Sequencing Plan

Layout and sequencing planning is the process of developing a sequence of work, laying out that sequence in a series of drawings for field execution and developing installation instructions for crew members. As part of the layout and sequencing process, CAD installation drawings and/or panel and pull schedules may be developed and distributed to foremen and field crew to minimize questions and maximize productivity of the workforce.

### What Activities Should be Performed During Layout and Sequencing Planning?

The layout and sequencing planning process consists of three activities. Table 4.24 provides the layout and sequencing planning activities in a convenient checklist.

##### Activity 30 - Develop installation sequence and layout drawings

  - Organize the project by areas, floors or systems.

Example: Breaking down the project in areas or systems has several benefits. For example, separate foremen can be assigned to manage each area/system, providing a smaller span of control. Furthermore, the schedule and tracking programs can be developed to match the area/system breakdown.

  - Allocate sufficient time to mentally think through the sequencing of all work processes from start through completion.

Example: The project manager, field supervisor and key foremen might participate in this mental exercise, which might be conducted as a brainstorming meeting. One participant should be assigned the responsibility of taking minutes so that the final sequencing can be transferred to layout and installation drawings. Key participants should identify every activity that must be accomplished in order to develop a completed product. Initially, all ideas should be written on a white board or flip pad, and then the activities can be sequenced, eliminated or consolidated through a series of iterations.

  - Determine whether to create sequence and layout drawings by hand (marked-up drawings) or by creating new CAD drawings.

Example: This decision might be driven by company capabilities. Many companies are hiring CAD operators to work on the jobsite creating layout and installation CAD drawings.

These drawings are handed out each morning to foremen who direct the activities of their crew members. If the company does not have CAD capabilities, hand sketches or marked-up plan sheets can also be distributed to foremen as installation drawings. Both techniques appear to minimize questions, improve productivity and contribute to a more organized and efficient installation process.

  - Create daily installation drawings at least one day prior to the date when the work needs to be performed so that the drawings can be distributed each morning to foremen and field crews.

Example: The person preparing the installation drawings should stay one or more days ahead of the installation schedule. Ideally, the preparer should prepare at least a week’s drawings one week or more ahead of the schedule.

  - Review the sequence daily or weekly to ensure the project is progressing as expected.

Example: The sequencing and installation plans should be used in conjunction with the schedule to ensure the project is progressing as planned. Any deviations from the planned sequence or schedule should be discussed with the customer or general contractor and documented. Some flexibility with the sequencing or installation of the work might be required to keep the project progressing as a whole.

##### Activity 31 -Develop field instructions, including panel, pull or conduit schedules.

  - Review the sequence and installation process to identify any additional information that might minimize questions and improve productivity.

Example: A pull or conduit schedule can augment the installation drawings by specifying the point of initiation and point of termination of all wires within every conduit that must be installed. Likewise, a panel schedule can show the location of a panel within a room as well as the location and route of all conduits that feed into or out of the panel.

  - Create the panel, pull or conduit schedules in conjunction with the installation drawings so that they can be distributed as a package to the foremen or field crews.

Example: Ideally, as the installation drawings are created, all additional information will be assembled into a set of field instructions that can be used by the field crew to maximize productivity and minimize questions. Conduit schedules or special information about the materials and methods are examples of common field instructions.

  - Develop field instructions and drawings for repetitive work, when repetitive work is scheduled on a project.

Example: A good example of a project that will include repetitive work is a hotel or dormitory. Each room is similar or identical to all of the other rooms. Therefore, a single installation sequence, drawings, and set of instructions can be developed for the crew performing the repetitive work. After the first few rooms have been completed, the crew will most likely have the sequence memorized.

##### Activity 32 - Develop prefabrication drawings for field use (when applicable).

  - For systems that are partially or completely prefabricated in a prefabrication shop, develop drawings that show how the prefabricated parts should be assembled and installed in the field.

Example: Drawings that resemble standard “product assembly instructions” are particularly useful for field assembly and installation.

These drawings should show each piece (or prefabricated piece) and how it connects to every other piece to form a complete system. Step-by-step assembly and installation instructions are especially helpful.

  - For systems prefabricated in a shop, ensure the prefabricated parts are clearly labeled and that these labels correspond to an assembly and installation scheme identified on the drawings.

Example: Tag each prefabricated piece and match the tag to the step-by-step assembly and installation instructions. The idea is to make the installation of the prefabricated parts as simple as possible in order to decrease the amount of time it takes to install the system.

  - If on-site prefabrication is scheduled, the drawings should identify the step-by-step process of how each piece is assembled into the prefabricated system.

  - If on-site prefabrication is scheduled, separate drawings should also be created to identify how the prefabricated parts should be installed.

Example: Step-by-step installation instructions should be developed in conjunction with the pre-fabrication instructions.

  - Distribute the prefabrication drawings to the foremen or field crews that will perform the work.

## Schedule Development

According to Mincks and Johnston, the project schedule is a manifestation of the project plan and should be used as a tool to communicate the plan to all team members, including field personnel, owners and other contractors on the jobsite.

Consequently, schedule development involves converting the sequencing and installation plan into a set of discrete work processes that can be mapped onto a timeline. While a separate bar chart schedule is highly recommended, many contractors have successfully added electrical line items to the general contractor’s bar chart schedule and essentially integrated their own schedule into the general contractor’s schedule. Ultimately, a project schedule— whether independent or integrated—is essential for organizing the work and monitoring progress.

### What Activities Should be Performed During Schedule Development?

The schedule development process consists of five activities. Table 4.25 (pages 81–82) provides the scope review activities in a convenient checklist.

##### Activity 33 - Review customer’s (general contractor’s) schedule and timeline.

  - Complete “Customer’s Schedule Review Items” checklist (Table 4.26).

  - Initiate or attend a customer schedule review meeting to identify any special requirements and clarify any questions.

Example: Although schedule review meetings are not common in the construction industry, they are an effective way to clarify any special requirements, such as the timing of delivery of owner-furnished materials or the placement of heavy items on the roof (which would cause a temporary disruption in the work).

##### Activity 34 - Identify work that impacts electrical activities.

  - While reviewing the overall construction schedule, annotate work that must be coordinated with other trades.

Example: Although the heating system is furnished and installed by the mechanical contractor, the heating unit must be supplied with a power source, which will be connected by the electrical contractor. The electrical contractor should identify all of the equipment in the facility that will require an electrical connection, which they must provide.

  - While reviewing the overall construction schedule, annotate potential conflicts that will require coordination.

Example: Often, conflicts occur between the mechanical, plumbing and electrical piping, which must all fit in wall and/or ceiling space. Identify potential conflicts among systems that can be addressed before installation begins.

  - Develop and submit RFIs to resolve open questions about equipment wiring or conflicts among systems.

  - Request an initial (and a recurring) coordination meeting to identify and resolve schedule questions and conflicts before installation begins.

Note: Many contractors hold regularly weekly coordination meetings to discuss upcoming work and to identify, discuss and resolve conflicts among the various trades working on the jobsite. These meetings are usually effective at resolving issues expeditiously. However, if the contractor has not arranged regular coordination meetings, request that the meetings be held, including an initial meeting that might require more time to identify all potential conflicts and issues plus possible solutions.

##### Activity 35 - Review the work sequence and long-lead-time

  - Review the work sequence and long-lead-time material/ equipment delivery dates. Develop a rough draft of the electrical schedule from the sequence and installation plan.

Example: Table 4.27 provides several rules-of-thumb for developing the draft electrical schedule.

  - Verify the ordering and delivery dates of long-lead-time materials and equipment.

  - Perform three-way coordination between sequencing/installation plan, material/equipment delivery plan and the draft electrical schedule.

Note: Set aside adequate time to coordinate the deliveries, installation sequence and schedule.

Annotate discrepancies that must be resolved when developing the final draft schedule.

  - Modify the draft schedule and sequencing/installation plan to accommodate long-lead time deliveries.

Note: The modifications should be coordinated so that the sequencing/ installation plan matches the schedule.

##### Activity 36 - Coordinate electrical schedule with the customer’s schedule.

  - After coordinating the sequencing/installation plan, material/equipment delivery plan and the draft electrical schedule, coordinate the draft schedule with the customer’s schedule and adjust as necessary.

Note: A final coordination exercise between the electrical schedule and the customer’s (general contractor’s) schedule should identify any minor adjustments that might need to be made before producing the final electrical schedule.

  - Review the final electrical schedule with the customer, general contractor, other trades and suppliers to resolve any final conflicts.

  - Seek approval of the schedule from the customer and general contractor.

Example: Meeting minutes or a “sign off” sheet that documents the customer’s and general contractor’s review and approval of the electrical schedule is recommended. Simply sending the final schedule to the customer may be inadequate as acknowledgement of approval. Focus, instead, on a written signature or public verbal approval.

  - Seek integration of the electrical schedule into the customer/general contractor’s overall project schedule.

Example: General contractors (GC) often show a single line item for the electrical work. Ask the GC to add all of the electrical line items from your schedule into the overall project schedule, and provide the GC with a digital file, if available, to simplify the task.

##### Activity 37 - Create bar chart schedule (performance recommended)

  - In addition to the integration of the electrical schedule into the overall schedule, format the final electrical schedule into an independent bar chart for tracking and control.

  - Select the type of bar chart schedule to develop and track.

Example: The three most common bar chart schedules include simple bar chart schedule (which does not calculate the critical path), critical path method (CPM) schedule and resource-loaded schedule that associates materials, equipment, labor and cost with each schedule line item. Select the scheduling method that is most appropriate for the complexity of the project and skill of the scheduler.

  - Save the original approved schedule as the baseline so that progress can be tracked and delays can be documented.

Note: The baseline schedule should be the final electrical schedule that was approved by and distributed to the customer/general contractor. It should never be changed. Instead, schedule updates should be made routinely (weekly or monthly) which reflect the progress of the work and any accelerations, delays or other changes to the work sequence or duration. An accurate baseline and final schedule can be used to support time extensions, change orders and disputes.

  - Distribute the electrical bar chart schedule to the customer, general contractor, various subcontractors and suppliers.

Note: The reason for distributing the final approved electrical schedule is to provide official notification to all team members regarding how the electrical contractor intends to proceed with the work. It also provides suppliers with a tool for determining delivery dates; as a result, all updates to the schedule should also be distributed to team members. Tracking and Control

Tracking and control involves selecting the proper control tools and setting up the company computerized project management system to track progress. It also involves developing a labor and materials tracking report and creating other essential reports in the computer database.

### What Activities Should be Performed During Tracking and Control?

The tracking and control process consists of two activities. Table 4.28 provides the tracking and control activities in a checklist.

##### Activity 38 - Customize the computerized tracking and control system (database/schedule/etc.) for the current project.

  - Review the tracking and control best practices (Table 4.29).

  - Complete the Tracking and Control Tools Checklist (Table 4.30).

  - Select computerized tracking and control tools for the project.

Example: The tracking and control checklist identifies several control tools that can be used to monitor project progress. Use the best practices and the checklist to determine which tools are appropriate for the current project.

  - Modify the tracking and control tools for the current project.

Example: Use the generic computer tracking and control tools to input data about the current project. Then, format the control tools so that they can be used to track and control progress on the project.

#### Figure 4.12:  Standard Progress Update Procedure

TYPES OF UPDATES

Three types of submittals are commonly encountered in construction:

- shop drawings

- product data/cut sheets

- samples.

Shop drawings reflect the manufacturer’s or equipment designer’s technical details for the product specified in the plans and specifications and usually include dimensions and quantities. Product data/cut sheets provide information about the make, model, size, capacity, performance and finish of a product specified in the plans and specifications. Samples are physical representations of the specified product, such as paint color, brick finish, floor tile, metal roof style and color, and so on.

SUMMARY PROGRESS UPDATING PROCEDURE

- Summary progress reports can be accessed anytime through the accounting system. When the budget was developed, the estimated line item values were entered into the system. As labor, materials and other purchase orders are expended, these expenditures are entered into the system so that the actual values can be compared to the estimated values.

- Each week, timesheets are turned in and labor hours are recorded against various budget line items by the accounting department.

- As purchase orders are paid, the paid value is entered against their associated line items in the budget.

- The accounting system will automatically calculate the variance between the actual values and estimated values. A negative variance indicates the budgeted value has been exceeded.

- Variances greater than 5% should be investigated by the project manager, and actions should be taken to address problems, such as poor productivity or disruptions to the work flow.

LABOR PRODUCTIVITY UPDATING PROCEDURE

- When the budget was developed, labor and quantities of materials were estimated for each budget line item. The accounting system was, thus, able to establish estimated hours per unit and total cost per budget line item.

- Each week, timesheets are submitted to the accounting department, and labor hours are recorded against various budget line items.

- Furthermore, each week, the project manager and/or field supervisor should walk the jobsite to estimate the quantity of materials that have been installed. These values are entered into the accounting system by the project manager or accounting representative.

- Once the actual values are input into the system, the computer can calculate the actual productivity (hours per unit) versus the estimated.

- The project manager should then evaluate the variance and investigate differences that exceed 5%.

FORECASTING PROCEDURE

- Both the summary progress update report and labor productivity report can be modified to permit forecasting of future costs at completion.

- It is the project manager’s responsibility to input forecasted costs and hours into the computer, with input provided by the field supervisor.

- The project manager should review potential change orders, future equipment and material purchases, and expected labor productivity when preparing the forecast. The forecast must account for outstanding costs plus any additional adjustment made for better/worse productivity, higher/lower material costs, gain/loss on changed work, etc. The project manager should attempt to be as accurate and candid as possible.

- Once the forecast has been completed, the project manager should evaluate whether the project is within budget, under budget or over budget. Adjustments may be necessary to get the project back on track if it is over the estimated budget or labor hours.

##### Activity 39 - Develop labor and materials tracking report.

  - Review the cost estimate, associated budget and cost code scheme.

  - Match the cost estimate/budget work items to crew assignments so that labor and materials can be tracked easily.

Example: Using the estimate and budget as a guide, verify that labor and materials can be easily reported daily/weekly for each line item in the budget. If the reporting process is too complicated or detailed, consider revising the budget to simplify the tracking and control process. Table 4.3 provides a sample time card/labor reporting form that links daily labor to specific cost codes in the budget, which can then be tracked using a progress report, labor report or productivity report.

  - Select the reports to be created and used for monitoring progress.

Example: The two most common reports include a progress report (see Table 4.22, for a sample summary progress report) and a productivity report.

  - Develop the selected reports by inputting project data into the reporting system (database or accounting system).

Example: Once the tracking and control reports have been selected, project-specific data should be entered into the database to populate the reports. These reports can then be used to update progress and productivity on a daily, weekly or monthly basis. Figure 4.12 presents company standard project update procedures.

## Construction Execution Kickoff Meeting

The final step to pre-construction planning is to hold a construction execution kickoff meeting that calls together all internal team members in order to review communication processes, administrative procedures, reporting requirements, and project budgets and schedules immediately prior to executing the work. The purpose of the kickoff meeting is to ensure all pre-construction planning tasks have been completed and to prepare the team to execute the project.

### What Activities Should be Performed During a Construction Execution Kickoff Meeting?

The construction execution kickoff meeting should begin by selecting a date and location for the meeting, inviting those team members that attended the planning kickoff meeting and distributing the agenda (Table 4.33). The construction execution kickoff meeting consists of seven activities. Table 4.34 provides the kickoff meeting activities in a convenient checklist.

##### Activity 40 - Review meeting schedule

  - Review the schedule of weekly internal meetings associated with the project.

Example: Meetings that should be held include (as a minimum) a weekly on-site progress meeting (including a walk-around) and an in-office staff meeting that covers the progress on all projects being performed by the company. Other meetings that might be necessary are specialty subcontractor coordination meetings (if not conducted by the general contractor), look-ahead planning meetings and “toolbox talk” safety meetings.

  - Review the schedule of weekly project meetings conducted by the customer or general contractor.

Example: Typically, two types of meetings are held: progress meetings and coordination meetings. The purpose of progress meetings is to update the customer/general contractor on the progress of work and to discuss and resolve open RFIs, pending changes, submittals and other issues. The purpose of coordination meetings is to assemble all trades working on the jobsite to discuss upcoming work, potential conflicts and to identify solutions to the conflicts. Additional meetings that might be required include look-ahead scheduling meetings and safety meetings.

  - Identify the internal team members that will be responsible for attending the internal and external meetings.

##### Activity 41 - Review request for information (RFI) process.

  - Review the contract for a customer-mandated request for information (RFI) process.

Example: If the contract identifies a customer mandated RFI process, the electrical contractor will be bound to follow the process. If no RFI clause exists, the electrical contractor should convey their company standard procedures to the general contractor.

  - Review the company standard procedure for developing, processing, tracking and closing out a request for information.

Example: Activity 16 covers the setup of an RFI processes. Furthermore, Figure 4.4 provides a suggested company RFI process, Table 4.13 provides an RFI tracking form and Figure 4.5 presents an RFI request form.

  - Modify the company standard RFI procedure, as necessary, to conform to the contractually mandated process.

Note: Distribute the procedure so that all employees who might submit an RFI understand the submission process.

##### Activity 42 - Review change order process and field change management process.

  - Review the contract for a customer-mandated change order (CO) process and field change request process.

Example: The contract should be carefully reviewed for clauses that identify when compensation for changes will be awarded and the type of compensation permitted (time, cost or both). Many clauses have a “notice” requirement, and some clauses only permit time extension without financial compensation.

Table 4.7 provided a checklist to guide team members through the contract review process.

  - Review the company standard change order procedure and field change request/management process.

Example: Figure 4.1 present a company change order process as a written set of procedures. The company change management process should be reviewed so that the project manager and field superintendent are familiar with the process for documenting changes, requesting compensation and managing field change requests.

  - Discuss the process for documenting changes, delays and disruptions in the work flow and sequence.

Example: Using the company change order process as a guide, the team members should discuss how to accurately document impacts to the installation process in order to approach the customer or general contractor for compensation. Keeping accurate records will be essential to the recovery process and should be a top priority for the project manager, field supervisor and key foremen.

  - Discuss the process for tracking and following up on change order requests and payment for field change directives.

Example: Figure 4.2 and Table 4.13 present a change order request form and a change order log for tracking the progress of change order processing. Responsibility for managing change orders and following up on their approval is typically assigned to the project manager. Responsibility should be clearly assigned during the meeting, and the tracking process should be reviewed.

##### Activity 43 - Review submittal processing procedures

  - Review the contract documents for a customer-mandated submittal processing procedures.

Example: The specifications may provide a submittal log (either blank or populated with the required submittals) and a set of submission procedures that must be followed. Some contracts may require complete books with all submittals be processed as a whole, while other contracts may allow submittals to be processed individually. If no submittal process is identified in the contract documents, the electrical contractor should convey its company standard procedures to the general contractor.

  - Review the company standard procedure for developing, processing, tracking and receiving approval for project submittals.

Example: Activity 17 discusses the setup of a submittal processing and tracking procedure, and Activity 24 discusses the process for requesting submittals from suppliers.

Furthermore, Figure 4.6 provides a suggested company submittal process, Figure 4.7 presents a submittal transmission form, and Table 4.13 provides a submittal log.

  - Modify the company standard submittal procedure, as necessary, to conform to the contractually-mandated process.

##### Activity 44 - Review billing and invoicing procedures.

  - Review the customer/general contractor’s process and timeline for invoicing, lien waivers and payment.

Example: Identify the date each month that invoices must be submitted to the customer or general contractor in order to be processed during the regular pay cycle. Also, make sure to review the terms of payment, such as whether the invoice will be paid in 30, 60 or 90 days.

  - Review the internal billing cycle established by the accounting department.

Example: Activity 28 describes the budget development process, and Activity 29 describes the development of the schedule of values.

Furthermore, Table 4.23 presents a sample company schedule of values. The budget, schedule of values and company billing process (Figure 4.11) should be reviewed and compared to the customer’s invoicing cycle to make sure payments can be processed during the customer’s regular invoicing cycle.

  - If necessary, adjust the internal billing cycle to conform to the customer/ general contractor’s invoicing cycle.

Note: If the company billing cycle must be modified to conform to the customer’s invoicing cycle, be sure to document and distribute the changes to all internal team members who will be involved in the billing process. Also, notify all subcontractors, suppliers and vendors of the billing and payment process for the project.

  - Discuss the process for following up with the customer/general contractor on late unpaid invoices.

Example: Typically, the accounting department will request that the project manager assume responsibility for following up on late payment or unpaid invoices. The follow-up process should be discussed, and responsibility should be clearly assigned.

##### Activity 45 - Review project and field reporting and tracking procedures.

  - Discuss the process for reporting labor hours and submitting timecards to the accounting office.

Example: In a typical process, the crew foreman will record the hours worked by each of the crew members (see Table 4.31 for a sample labor reporting form). The foreman will submit the weekly hours to the field supervisor, who will forward them to the project manager. The project manager will review and approve the timecards and forward them to the accounting department for entry   into the accounting system. The accounting department will enter the hours, and the hours can then be tracked by the progress and productivity reports (Tables 4.22, and 4.32). The reporting process should be clarified in the meeting.

  - Discuss the process for reporting progress and percent complete.

Example: Typically, the project manager and field supervisor will establish the percent complete together. The process requires the project manager to understand how much work was supposed to be completed on a particular date and then walk around with the field supervisor to determine how much work has actually been completed. Since each work element should account for no more than 5% of the   total work, minor inaccuracies should not significantly skew the total percent complete.

  - Discuss the process for tracking material and equipment costs and purchase orders.

Example: Typically, the accounting department will enter payment information into the accounting database when purchase orders or invoices are paid. It is important that these payments are correctly allocated to the proper cost code so that the progress report accurately reflects how much has been spent for each line item in the budget. The P.O. payment entry process should be clarified in the meeting.

  - Review and discuss the tracking tools that will be used to monitor progress.

Example: Several possible tools that can be used to track progress include the progress report, productivity report, schedule and manpower loading chart. The company may have additional tools that are used routinely. The project manager should identify the tools that will be used and discuss the process for updating each control tool.

  - Review the monthly update process.

Example: Figure 4.12 identified a sample monthly progress update process. The company standard process should be reviewed during the meeting.

##### Activity 46 - Review electrical and customer schedules.

  - Review the electrical bar chart schedule;

Example: Activity 37 discusses the process for creating the electrical schedule. The final schedule should be reviewed so that all internal team members are familiar with the timeline and sequence of activities.

  - Review the customer/general contractor’s schedule and/or timeline.

Example: Activity 33 discusses the process for reviewing the customer/ general contractor’s schedule, and Table 4.26 provides a review checklist. A brief overview of the customer’s overall project schedule is sufficient so that all team members understand the general scope of the project and the completion timeline.

  - Discuss the process for updating the schedule.

Example: Typically, the schedule is updated by the project manager. At the end of each week, the project manager and field supervisor should walk around the jobsite to compare the actual work completed to the work that was expected to be completed. “Completion” can be determined by quantities of units installed (such as linear feet of conduit) or approximate percent of a system installed. The schedule can then be updated based on percent complete of the schedule line items or number of units installed (if the schedule is resource-loaded or entered in sufficient detail).

#### Table 4.1:  Checklist of Pre-Construction Planning Activities

| PRE-CONSTRUCTION PLANNING CHECKLIST |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACT. | COMPLETION DATE | ACTIVITY CATEGORY | ACT. NO. | ACTIVITY |
|  |  | Team Selection and Turnover | 1 | Finalize selection of project manager, field supervisor and other key team members. |
|  |  |  | 2 | Hold turnover meeting between estimator and project manager (when applicable). |
|  |  |  | 3 | Hold separate turnover meeting between project manager and field supervisor. |
|  |  |  | 4 | Hold pre-job (planning) kickoff meeting with internal team members to assign responsibilities. |
|  |  | Scope and Contract Review | 5 | Review contract for unfavorable or high risk clauses (recommended). |
|  |  |  | 6 | Project manager reviews plans, specifications, and schedule. |
|  |  |  | 7 | Field supervisor reviews plans, specifications, and schedule. |
|  |  |  | 8 | Create a list of issues that need to be resolved and begin the request for information (RFI) process. |
|  |  |  | 9 | Conduct site visit (recommended). |
|  |  |  | 10 | Compare estimated (bid) work activities and materials to planned performance. |
|  |  |  | 11 | Identify value engineering and prefabrication opportunities and how to simplify the work. |
|  |  |  | 12 | Prepare construction takeoff. |
|  |  | Administrative Setup | 13 | Set up project files and create contact list. |
|  |  |  | 14 | Set up computerized tracking and control system (forms, database, schedule, and tracking). |
|  |  |  | 15 | Initiate a change management system. |
|  |  |  | 16 | Initiate a request for information (RFI) tracking and processing system. |
|  |  |  | 17 | Initiate a submittal tracking and processing system. |
|  |  |  | 18 | Develop a “Labor Requirements/Expectations” letter (for background check, etc.) (recommended). |
|  |  | Buyout Process | 19 | Price and/or review subcontractor/supplier/vendor prices and qualifications. |
|  |  |  | 20 | Negotiate pricing and contract conditions, and select subcontractors/suppliers/vendors. |
|  |  |  | 21 | Develop and issue purchase orders and contracts for materials and equipment. |
|  |  |  | 22 | Order long-lead-time materials and equipment. |
|  |  |  | 23 | Request submittals, cut sheets and shop drawings. |
|  |  |  | 24 | Develop and process log and book of submittals, cut sheets and shop drawings. |
|  |  | Material Handling Plan | 25 | Develop material delivery and handling plan. |
|  |  |  | 26 | Develop material storage and staging plan. |
|  |  | Budget Preparation | 27 | Develop, review or expand cost code scheme. |
|  |  |  | 28 | Develop budget by breaking down labor, material, overhead and profit costs. |
|  |  |  | 29 | Develop schedule of values. |
|  |  | Layout and Sequencing Plan | 30 | Develop installation sequence and layout drawings. |
|  |  |  | 31 | Develop field instructions, including panel, pull or conduit schedules. |
|  |  |  | 32 | Develop prefabrication drawings for field use (when applicable). |
|  |  | Schedule Development Tracking and Control | 33 | Review customer’s schedule and timeline. |
|  |  |  | 34 | Identify work that impacts electrical activities. |
|  |  |  | 35 | Review the work sequence and long-lead-time material/equipment delivery dates. |
|  |  |  | 36 | Coordinate electrical schedule with customer schedule (recommended). |
|  |  |  | 37 | Create a bar chart schedule (recommended). |
|  |  |  | 38 | Customize the computerized tracking and control system (database/schedule/etc.) for the current project. |
|  |  |  | 39 | Develop labor and materials tracking report. |
|  |  | Construction Execution Kickoff Meeting | 40 | Review meeting schedule. |
|  |  |  | 41 | Review request for information (RFI) process. |
|  |  |  | 42 | Review change order process and field change management process. |
|  |  |  | 43 | Review submittal processing procedure. |
|  |  |  | 44 | Review billing and invoicing procedures. |
|  |  |  | 45 | Review project and field reporting and tracking procedures. |
|  |  |  | 46 | Review electrical and customer schedules. |

#### Table 4.2:  Team Selection and Turnover Checklist

#### Table 4.3:  Turnover Meeting Agenda

TURNOVER MEETING AGENDA

Review Items:

- Project overview

  - Project name

  - Location

  - Type of work

  - Estimated cost and estimated work hours

  - Profit goal

  - General scope of work

  - Identify potential opportunities and challenges of the project

- Review the plans and specifications.

  - Go page by page through the plans to discuss the quantities and costs.

  - Review each section of the specifications.

  - Discuss how the estimator assumed the work would be performed (materials and methods).

  - Review others’ work performance.

  - Identify discrepancies and ambiguities in the bid documents.

  - Identify design discrepancies or issues.

  - Identify potential errors in the bid documents.

  - Discuss information collected during a site visit.

  - Discuss information collected during a pre-bid meeting.

  - Identify potential cost savings from changes to materials and methods.

  - Identify potential prefabrication or internal value engineering opportunities.

  - Discuss alternative routing of conduits.

  - Identify any temporary power and lighting requirements.

- Review the cost estimate and bid price.

  - Review each bid line item and its cost.

  - Review overhead, profit and contingency funds.

  - Discuss wage rates.

  - Review the bid submission letter with clarifications and qualifications.

- Review subcontractor/vendor pricing and qualifications.

  - Review subcontractors and suppliers scope of work and qualifications.

  - Identify all pre-contract commitments and promises.

  - Verify minority business requirements.

- Review the schedule and milestones.

  - Review the owner-furnished schedule.

  - Review any preliminary schedule submitted with the bid.

  - Review work by others that will impact the electrical work.

  - Identify important material and equipment delivery dates.

  - Discuss holidays, vacations and potential weather events.

- Review manpower requirements and labor rates.

  - Review the manpower loading chart (if available).

  - Identify the estimated crew mix.

  - Identify any wage increases.

  - Review the potential for overtime.

- Review other items specific to this project:

#### Table 4.4:  Pre-Job Planning Kickoff Meeting Agenda

PRE-JOB PLANNING KICKOFF MEETING AGENDA

Agenda Items:

- Project overview

  - Project name

  - Location

  - Type of work

  - Contract cost

  - General scope of work

  - Identify potential opportunities and challenges of the project

- Introduce internal team members.

  - Project manager

  - Field supervisor/foreman

  - Estimator

  - Accounting representative

  - Other internal team members (i.e., CAD operator, purchasing agent, etc.)

- Identify external team members.

  - Owner/customer

  - Architect/engineer

  - General contractor/construction manager

  - Other specialty subcontractors

  - Vendors/suppliers

- Review the general scope of work.

  - Provide an overview of the project scope of work and the electrical scope.

  - Review major work performed by others.

- Review the contract cost.

  - Review direct costs and the contract cost.

  - Review overhead, profit and contingency funds.

- Review purchasing of materials, equipment and services from subcontractors/vendors.

  - Review subcontractors and suppliers scope of work and qualifications.

  - Identify all pre-contract commitments and promises.

  - Verify minority business requirements.

- Review the schedule and milestones.

  - Review the owner-furnished schedule.

  - Review any preliminary schedule submitted with the bid or construction schedule.

  - Review work by others that will impact the electrical work.

  - Identify important material and equipment delivery dates.

- Review manpower requirements and labor rates.

  - Review the manpower loading chart (if available).

  - Identify the estimated crew mix.

  - Identify any wage increases.

- Review the contract—identify any special clauses that require careful consideration.

- Review administrative procedures.

  - Administrative setup

  - Request for Information (RFI) procedures and setup

  - Submittal process and setting up the submittal tracking system

  - Change order procedures and setting up the change management system

  - Field reporting requirements

  - Budget preparation and billing procedures

  - Cost control and setting up the tracking system

- Review special safety issues.

- Review site logistics and material storage and staging.

  - Site access

  - Parking

  - Material delivery and movement procedures

  - Material storage locations

  - Trailer locations (if applicable)

  - Site cleanup requirements

  - Temporary power and lighting requirements

- Review bond, permit and certificate of insurance requirements

- Review other items specific to this project:

#### Table 4.5:  Scope and Contract Review Checklist

| SCOPE AND CONTRACT REVIEW CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| --- | --- | --- | --- |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 5. Review contract for unfavorable or high risk clauses (performance recommended). |  |  |  |
| ■ |  | 1 | Complete the Contract Review Checklist (Table 4.6). |
| ■ |  | 2 | Identify all required bonds, permits and certificates. |
| ■ |  | 3 | Review contractual billing requirements. |
| ■ |  | 4 | Review and understand procedures for requesting change orders. |
| ■ |  | 5 | Identify whether disputes must be resolved through alternative dispute resolution, such as mediation or arbitration. |
| 6. Project manager reviews plans, specifications and schedule. |  |  |  |
| ■ |  | 1 | Order extra sets of plans and specifications if necessary. |
| ■ |  | 2 | Complete the Scope and Schedule Review checklist (Table 4.7). |
| ■ |  | 3 | Compare the scope identified in the contract to the scope from the bid submission to verify that they match. |
| ■ |  | 4 | Compare the plans to the specifications to identify any discrepancies. |
| ■ |  | 5 | Review the customer-furnished schedule to determine whether the electrical work can be completed within the contractual timeframe. |
| 7. Field supervisor reviews plans, specifications and schedule. |  |  |  |
| ■ |  | 1 | Complete the Scope and Schedule Review checklist (Table 4.7). |
| ■ |  | 2 | Review best field practices or lessons learned. |
| ■ |  | 3 | Identify value engineering and prefabrication opportunities (see Activity 23). |
| ■ |  | 4 | Identify labor requirements and begin selecting foremen. |
| ■ |  | 5 | Identify special tools that will need to be purchased or assembled. |
| 8. Create a list of issues that need to be resolved and begin the request for information (RFI) process. |  |  |  |
| ■ |  | 1 | Establish a request for information (RFI) process (see Activity 16) and create a list of questions that require clarification. |
| ■ |  | 2 | Formalize the RFIs by assigning them a trackable number and submitting them to the owner/CM/GC. |
| 9. Conduct a site visit (performance recommended). |  |  |  |
| ■ |  | 1 | Complete the Site Visit Checklist (Table 4.8). |
| ■ |  | 2 | Examine site access and layout, including parking, material delivery points and material lay-down and storage. |
| ■ |  | 3 | Identify locations and availability of matieral and personnel lifts, elevators, cranes, scaffolding and forklifts. |
| ■ |  | 4 | Create a plan for installing temporary power (when applicable). |
| ■ |  | 5 | Verify existing conditions and compare them to the conditions shown on the plans and described in the specifications. |
| 10. Compare estimated (bid) work activities and materials to planned performance. |  |  |  |
| ■ |  | 1 | Compare the estimator’s concept of how to perform the work to typical field operations and document differences. |
| ■ |  | 2 | Discuss unclear methods or discrepancies with the estimator. |
| ■ |  | 3 | Determine the cost difference between the as-bid and planned performance of the work. |
| 11. Identify value engineering and prefabrication opportunities and how to simplify the work. |  |  |  |
| ■ |  | 1 | Review value engineering (VE) or prefabrication opportunities that were identified in the turnover meeting between the estimator and project manager. |
| ■ |  | 2 | Review procedures for formally requesting VE consideration if required. |
| ■ |  | 3 | Search for and identify additional VE and prefabrication items. |
| ■ |  | 4 | Identify additional ways to simplify the work. |
| ■ |  | 5 | Price out the cost difference between the as-bid and VE options. |
| 10. Compare estimated (bid) work activities and materials to planned performance. |  |  |  |
| ■ |  | 1 | Take off the materials, equipment and systems in the order they will be constructed. |
| ■ |  | 2 | Code each plan sheet as you take it off so that you can return to it later and immediately identify the quantity of various materials shown on the sheet. |
| ■ |  | 3 | The final quantities should be identified by the units in which they will be purchased. |
| ■ |  | 4 | All assumptions should be noted on the quantity takeoff sheets. |
| ■ |  | 5 | Be sure the quantities that are estimated include a waste factor. |
| ■ |  | 6 | Compare the construction takeoff to the bid takeoff to identify significant differences or discrepancies. |

#### Table 4.6:  Contract Review Items

| Completed | Date Completed | ITEM |
| --- | --- | --- |
| ■ |  | Check for ambiguous clauses and seek clarification. |
| ■ |  | Check for one-sided clauses that favor the other party. |
| ■ |  | Cross-reference clauses to understand the whole meaning of clauses. |
| ■ |  | Identify discrepancies and conflicting clauses and seek clarification. |
| ■ |  | Check for agreement between plans and specifications, and seek clarification if there is any discrepancy. |
| ■ |  | Identify any “killer clauses” that assign full responsibility for everything to the electrical contractor. |
| ■ |  | Determine whether the contract clearly favors the other party (owner/CM/ GC), and seek more equitable contract terms. |
| ■ |  | Review the Indemnification Clause, and ensure your insurance coverage can sufficiently cover the risk. |
| ■ |  | Evaluate the Coordination Clause to determine each party’s responsibility to coordinate the work. |
| ■ |  | Determine your rights and responsibilities if the sequence of work is changed or if out-of-sequence work impacts the project. |
| ■ |  | Carefully review all time-sensitive clauses that cover commencement, completion, milestones, accelerations, delays and progress. |
| ■ |  | Review and understand your rights to receive damages if the schedule is accelerated or delayed by other parties. |
| ■ |  | Determine whether there is a no-damages-for-delay clause, and review your rights and responsibilities. |
| ■ |  | Review and understand the clause that describes waivers. |
| ■ |  | Review the concealed conditions clause, and identify the circumstances that will entitle you to compensation. |
| ■ |  | Review the Force Majeure clause, and identify the circumstances that will entitle you to a time extension. |
| ■ |  | Evaluate clauses that identify procedures for seeking change orders. |
| ■ |  | Evaluate clauses that identify the compensation for extra work. |
| ■ |  | Identify payment provisions, especially a “pay when paid” clause and a “pay if paid” clause. |

#### Table 4.7:  Scope and Schedule Review Items

| SCOPE AND SCHEDULE REVIEW ITEMS |
| --- |
| Completed | Completed By | Date Completed | Item |  |  |
| ■ |  |  | Contract |  |  |
| ■ |  |  | Plans |  |  |
| ■ |  |  | Specifications |  |  |
| ■ |  |  | Cost estimate and bid breakdown |  |  |
| ■ |  |  | Referenced/applicable codes or regulations |  |  |
| ■ |  |  | Quality requirements |  |  |
| ■ |  |  | Safety requirements |  |  |
| ■ |  |  | Special conditions |  |  |
| ■ |  |  | Addendums |  |  |
| ■ |  |  | Temporary power and lighting requirements |  |  |
| ■ |  |  | Owner/CM/GC-furnished materials |  |  |
| ■ |  |  | Vendor pricing and qualifications |  |  |
| ■ |  |  | Owner/CM/GC schedule |  |  |
| ■ |  |  | Internal schedule submitted with bid |  |  |
| ■ |  |  | Work sequence and work by others |  |  |
| ■ |  |  | Required coordination with other trades |  |  |
| ■ |  |  | Material and equipment deliveries |  |  |
| ■ |  |  | Anticipated weather problems or holidays |  |  |
| ■ |  |  | Required labor |  |  |
| ■ |  |  | Labor rates and potential increases |  |  |
| ■ |  |  | Crew mix |  |  |
| ■ |  |  | Administrative procedures (submittals/RFIs/changes) |  |  |
| ■ |  |  | Other: |  |  |
| ■ |  |  | Other: |  |  |
| SCOPE AND SCHEDULE REVIEW ITEMS |
| Completed | Who furnishes? |  |  | Who installs? | What to review in the Plans and Specifications |
| ■ |  |  |  |  | Access doors |
| ■ |  |  |  |  | Asbestos abatement |
| ■ |  |  |  |  | Carpentry (miscellaneous) |
| ■ |  |  |  |  | Clean up |
| ■ |  |  |  |  | Conduit (sizes and quantities) |
| ■ |  |  |  |  | Crane |
| ■ |  |  |  |  | Cutting and patching |
| ■ |  |  |  |  | Demolition and removal |
| ■ |  |  |  |  | Electric motors |
| ■ |  |  |  |  | Electric starters |
| ■ |  |  |  |  | Excavation and backfill |
| ■ |  |  |  |  | Fire alarm wiring |
| ■ |  |  |  |  | Fire alarm devices |
| ■ |  |  |  |  | Hand dryers |
| ■ |  |  |  |  | Hoists for personnel |
| ■ |  |  |  |  | Hoists for materials |
| ■ |  |  |  |  | Interior layout |
| ■ |  |  |  |  | Painting |
| ■ |  |  |  |  | Panels |
| ■ |  |  |  |  | Scaffolding |
| ■ |  |  |  |  | Site access |
| ■ |  |  |  |  | Site surveying |
| ■ |  |  |  |  | Temporary power |
| ■ |  |  |  |  | Underground utilities |
| ■ |  |  |  |  | Wire (and/or pipe and wire) |
| ■ |  |  |  |  | Other: |
| ■ |  |  |  |  | Other: |
| ■ |  |  |  |  | Other: |

#### Table 4.8:  Site Visit Checklist

| SITE VISIT REVIEW ITEMS |  |  |
| --- | --- | --- |
| Completed | Item to Review | Notes |
| ■ | Access into and out of the site |  |
| ■ | Circulation throughout the site |  |
| ■ | Material and equipment delivery routes |  |
| ■ | Material storage and staging locations |  |
| ■ | Office trailer or office space |  |
| ■ | Temporary power and lighting locations |  |
| ■ | Existing underground utilities location |  |
| ■ | Existing above ground utility locations |  |
| ■ | Location of existing interior systems |  |
| ■ | Progress of the demolition |  |
| ■ | Progress of the site work |  |
| ■ | Progress of the site layout/surveying |  |
| ■ | Asbestos abatement has been completed |  |
| ■ | Work completed to date |  |
| ■ | Presence/location of the crane |  |
| ■ | Presence/location of the personnel lift |  |
| ■ | Presence/location of the materials lift |  |
| ■ | Potential coordination with others |  |
| ■ | Anticipated weather problems |  |
| ■ | Housekeeping conditions |  |
| ■ | Special site considerations |  |
| ■ | Safety issues or concerns |  |
| ■ | Other: |  |
| ■ | Other: |  |
| ■ | Other: |  |

#### Table 4.9:  Administrative Setup Checklist

| ADMINISTRATIVE SETUP CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| --- | --- | --- | --- |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 13. Set up project files and create contact list. |  |  |  |
| ■ |  | 1 | Use the File System Checklist (Table 4.11) to create paper files. |
| ■ |  | 2 | Create a contact sheet that lists all team members and their company contact information. |
| 14. Set up computerized tracking and control system (forms, database, schedule and tracking). |  |  |  |
| ■ |  | 1 | Verify the accounting department has assigned a project number and entered initial information in the cost control center. |
| ■ |  | 2 | Use the File System Checklist (Table 4.11) to create computer files. |
| ■ |  | 3 | If a separate project management software system is used, set up the project in the system. |
| ■ |  | 4 | If a separate project management software system is used, set up the project in the system. |
| 15. Initiate a change management system. |  |  |  |
| ■ |  | 1 | Review the contract to identify required change order, field change, and time-and-materials procedures. |
| ■ |  | 2 | Review your company’s standard procedures for initiating, requesting, and processing change orders and field changes. |
| ■ |  | 3 | Develop a log with sequential numbering to track all changes, including change orders, field changes and time-and-materials requests (Table 4.12). |
| 16. Initiate a request for information (RFI) tracking and processing system. |  |  |  |
| ■ |  | 1 | Develop a log with sequential numbering to track all requests for information (RFIs) (Table 4.13). |
| ■ |  | 2 | Determine whether RFIs will be submitted by e-mail, fax or postal mail. |
| ■ |  | 3 | Review your company’s standard procedures for processing RFIs, and use a company standard form for submitting RFIs. |
| ■ |  | 4 | Ensure each RFI also identifies a proposed solution. |
| 17. Initiate a submittal tracking and processing system. |  |  |  |
| ■ |  | 1 | Develop a log with sequential numbering to track all submittals, including those of vendors and subcontractors (Table 4.14). |
| ■ |  | 2 | Review your company’s standard procedures for processing submittals, and use a company standard form for submissions. |
| ■ |  | 3 | Verify that each submittal processing form identifies a respond-no- later-than date, which is associated with timely ordering and delivery of materials and equipment. |
| 18. Develop a “Labor Requirements/Expectation” letter (for background check, etc.) (performance recommended) |  |  |  |
| ■ |  | 1 | For projects that have special requirements such as drug testing, background check or special safety training, develop an “expectations” letter that must be reviewed and signed by crew members (see Figure 4.8). |
| ■ |  | 2 | For projects that will require hiring workers from the union hall, develop an “expectations” letter that must be reviewed and signed by crew members. |

#### Table 4.10:  File System Checklist

| SCOPE AND SCHEDULE REVIEW ITEMS |  |  |
| --- | --- | --- |
| Completed | File Number | File Description |
| ■ |  | Project Information and Contacts |
| ■ |  | Cost Estimate and Bid Submission |
| ■ |  | Contract Agreement |
| ■ |  | Contract Documents |
| ■ |  | Budget and Pay Requests |
| ■ |  | Purchase Orders |
| ■ |  | Subcontracts |
| ■ |  | Materials Folder (Fixtures, Switchgear, Fire Alarm, Low Voltage) |
| ■ |  | Requests for Information |
| ■ |  | Submittals |
| ■ |  | Change Orders—Pending |
| ■ |  | Change Orders—Approved |
| ■ |  | Correspondence |
| ■ |  | Meeting Minutes |
| ■ |  | Daily/Weekly Field Report |
| ■ |  | Progress Reports |
| ■ |  | Other: |
| ■ |  | Other: |
| ■ |  | Other: |

#### Figure 4.2: Change Order Proposal

#### Figure 4.3: Field Change Form

| FIELD AUTHORIZATION FORM |  |  |  |  |
| --- | --- | --- | --- | --- |
| DATE |  |  | FA No. |  |
| TO: | 0 |  |  |  |
|  | 0 |  |  |  |
|  | 0 |  |  |  |
|  |  |  | Sub Project No. | 0 |
| FROM: | GSL ELECTRIC, INC. |  | G.C. Project No. | 0 |
| PROJECT NAME: |  | 0 | Owner Project No. |  |
| YOU ARE AUTHORIZED TO PERFORM THE FOLLOWING: |  |  |  |  |
| SIGNATURE _____________________________________ TITLE ____________________ |  |  |  |  |
|  | THIS WORK IS TO BE COMPLETED: |  |  |  |
|  |  | ON A TIME AND MATERIAL BASIS |  |  |
|  |  | PURSUANT TO CHANGE ORDER QUOTATION # ____ |  |  |
|  |  | PURSUANT TO ARCHITECTURAL BULLETIN QUOTATION #____ |  |  |
|  |  | PURSUANT TO MODIFICATION QUOTATION # ____ |  |  |
|  |  | PURSUANT TO A PRICE TO BE NEGOTIATED WITHIN THE NEXT 7 DAYS |  |  |
|  |  | OTHER ___________________________ |  |  |

#### Table 4.11: Change Order Log

#### Table 4.12: Request for Information Log

#### Figure 4.5: Request for Information Form

#### Table 4.13: Submittal Log

#### Figure 4.7: Submittal Transmittal Form

| SUBMITTAL TRANSMITTAL FORM |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: |  |  |  |  |  |  |
| DATE: |  |  |  |  |  |  |
| PROJECT NAME: |  |  |  |  |  |  |
| CSI SECTION: |  |  |  |  |  |  |
| TO: |  | FROM: |  |  |  |  |
| QTY | SUBMITTAL DESCRIPTION | FOR YOUR REVIEW | FOR YOUR APPROVAL | FOR YOUR FILES | FOR INFORMATION ONLY | DATE REQ’D |

#### Figure 4.8: Requirements and Expectation Letter

#### Table 4.14:  Buyout Process Checklist

| BUYOUT PROCESS CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| --- | --- | --- | --- |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 19. Request and/or review subcontractor/supplier/vendor prices and qualifications. |  |  |  |
| ■ |  | 1 | Request subcontractor/supplier/vendor pricing if it was not requested or received during the bidding stage. |
| ■ |  | 2 | Compare actual subcontractor/supplier/vendor scope of work with the scope identified in the subcontractor/supplier/vendor bid submission. |
| ■ |  | 3 | Evaluate the subcontractor/supplier/vendor qualifications. |
| ■ |  | 4 | Compare priding and qualifications among the subcontractors/ suppliers/vendors. |
| 20. Negotiate pricing and contract conditions and select subcontractors/suppliers/vendors. |  |  |  |
| ■ |  | 1 | Discuss potential cost savings with potential subcontractors/ suppliers/vendors. |
| ■ |  | 2 | Review the contract or purchase order terms and conditions with potential subcontractors/suppliers/vendors prior to award. |
| ■ |  | 3 | Select all successful subcontractors/suppliers/vendors, and issue a letter of intent (if necessary). |
| 21. Develop and issue purchase orders and contracts for materials and equipment. |  |  |  |
| ■ |  | 1 | Develop the purchase orders or contracts for subcontractors/ suppliers/vendors. |
| ■ |  | 2 | Process and issue the purchase orders or subcontracts. |
| 22. Order long-lead-time materials and equipment. |  |  |  |
| ■ |  | 1 | Compare the sequence, schedule and materials/equipment to identify long-lead-time items. |
| ■ |  | 2 | Negotiate and issue purchase orders and subcontracts for long-lead time items before negotiating standard purchase orders and subcontracts. |
| ■ |  | 3 | Issue a letter of intent or purchase order immediately to release long-lead-time items for order and delivery. |
| 23. Request submittals, cut sheets and shop drawings. |  |  |  |
| ■ |  | 1 | Upon issuing the contract document, the subcontractor/supplier/ vendor should be requested to assemble and submit samples, cut sheets or shop drawings. |
| ■ |  | 2 | Identify a deadline by which the submittals, cut sheets, and shop drawings must be submitted to the electrical contractor. |
| 24. Develop and process log and book of submittals, cut sheets and shop drawings. |  |  |  |
| ■ |  | 1 | Develop a log, with sequential numbering, to track all submittals, including those of vendors and subcontractors (see also Activity 17 and Table 4.13). |
| ■ |  | 2 | Assemble two or more binders of all draft and approved submittals. |
| ■ |  | 3 | Submit and track required submittal items. |

#### Table 4.15:  Subcontractor/Supplier/Vendor Comparison Spreadsheet

#### Figure 4.9: Letter of Intent

#### Figure 4.10: Purchase Order Form

#### Table 4.16:  Material Handling Planning Process Checklist

| MATERIAL HANDLING PROCESS CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| --- | --- | --- | --- |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 25. Develop material delivery and handling plan. |  |  |  |
| ■ |  | 1 | Review the “Material Delivery/Storage and Site Logistics Best Practices” (see Table 4.18). |
| ■ |  | 2 | Establish and maintain a file of delivery receipts and packing slips. |
| ■ |  | 3 | Establish a material and equipment delivery and storage log |
| ■ |  | 4 | Create a material and equipment delivery schedule. |
| ■ |  | 5 | Establish standard procedures for receiving, handling and storage of materials and equipment. |
| 26. Develop material storage and staging plan. |  |  |  |
| ■ |  | 1 | Complete the site logistics review checklist (Table 4.20). |
| ■ |  | 2 | Review the “Material Delivery/Storage and Site Logistics Best Practices” (see Table 4.18). |
| ■ |  | 3 | Develop a storage site layout that identifies where the materials and equipment are stored. |

#### Table 4.17:  Material Delivery/Storage and Site Logistics Best Practices

| MATERIAL DELIVERY/STORAGE AND SITE LOGISTICS BEST PRACTICES |  |  |
| --- | --- | --- |
| Best Practice Number |  | BEST PRACTICE DESCRIPTION |
| 1 |  | Assign one person the responsibility of managing material and equipment delivery, handling storage and staging. |
| 2 |  | Establish a standard unloading crew that consists of laborers or apprentices. |
| 3 |  | Establish standard procedures for receiving, handling and storing materials, and strictly enforce the standard. |
| 4 |  | Develop a storage site layout that identifies where the materials and equipment are stored, and annotate the location on the material and equipment delivery and storage log. |
| 5 |  | Develop a storage site identification system that provides a method to document and track the location of all materials that have been delivered to the jobsite. |
| 6 |  | Establish storage space for each major material item or group (pipe, wire, boxes, etc.). |
| 7 |  | Sort and store the materials as soon as it is delivered to the site. |
| 8 |  | Allow storage space for waste or excess materials, and remove them as soon as possible. |
| 9 |  | Ensure the material and equipment is adequately secured and protected from the elements. |
| 10 |  | Make sure the materials manager is notified of pending deliveries. |
| 11 |  | Return all damaged, excess or incorrect materials to the vendor immediately in order to keep the site free from clutter. |
| 12 |  | Arrange to have materials delivered just before you need them so that storage and handling is kept to a minimum. |
| 13 |  | If materials are ordered in bulk, ask the vendor to store the materials at their office until you need them on the jobsite (also consider paying extra for this option). |
| 14 |  | Consider using a material consignment trailer, where the vendor inventories the trailer each week, restocks it and only charges you for the materials you use. |
| 15 |  | Try to place materials/equipment at the location where they will be used to improve access to the materials/equipment and minimize handling. |
| 16 |  | Arrange to have materials packaged for efficient unloading, handling and installation. |
| 17 |  | Determine ahead of time what equipment will be needed to unload and handle material deliveries. |
| 18 |  | Evaluate the capacity of material lifts, freight elevators and cranes to ensure they can safely move the materials and equipment. |
| 19 |  | Locate your toilet facilities as close to the work areas as possible. |
| 20 |  | Locate your break facilities and trash containers as close to the work areas as possible. |
| 21 |  | Develop a map of facility locations, and distribute it to workers and suppliers/vendors. |

#### Table 4.18:  Material and Equipment Delivery and Storage Log

#### Table 4.19:  Site Logistics Review Items

| SITE LOGISTICS REVIEW CHECKLIST |  |  |
| --- | --- | --- |
| Completed | Date Completed | ITEM |
| ■ |  | Review the site layout, and identify placement of materials and facilities to maximize productivity. |
| ■ |  | Identify site entry and exit points, and plan possible vehicle circulation. |
| ■ |  | Identify procedures for receiving materials and authorized personnel. |
| ■ |  | Identify material storage locations. |
| ■ |  | Determine and document equipment that will be needed to unload and move materials (cranes, fork lift, pallet jacks, etc.). |
| ■ |  | Evaluate material lifts, freight elevators and cranes to determine whether they can support the size and weight of the material items. |
| ■ |  | Determine and order special tools associated with material handling (box cutters, bar code readers, computers, etc.). |
| ■ |  | Establish a “receiving crew” that consists of laborers or apprentices who will unload trucks and move materials. |
| ■ |  | Select a worker to be in charge of material handling, including inspection and inventory of delivered items. |
| ■ |  | Establish standard procedures for receiving, logging, handling and storing materials and equipment on the jobsite or at an offsite location. |
| ■ |  | Establish delivery dates for all materials and develop a schedule of deliveries. |
| ■ |  | Evaluate purchasing options to ensure materials are ordered to promote efficient unloading, storage and installation. |
| ■ |  | Evaluate the benefits and pitfalls of prefabrication in terms of delivery, storage, handling and installation. |
| ■ |  | Review the material delivery, handling, storage and staging best prac- tices (see Table 4.18). |

#### Table 4.20:  Budget Preparation Checklist

| BUDGET PREPARATION CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| --- | --- | --- | --- |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 27. Develop, review or expand the cost code scheme. |  |  |  |
| ■ |  | 1 | Decide whether to use a cost code scheme based upon 16 specifications divisions or 48 specifications divisions. |
| ■ |  | 2 | Review the cost estimate to identify the existing cost code breakdown, and decide whether additional breakdown is necessary. |
| ■ |  | 3 | Review the company standard list of cost codes (or use Table 4.21), and decide which codes will be needed for breaking down the work for tracking and billing. |
| ■ |  | 4 | Add new codes for work items that are not on the standard list. |
| ■ |  | 5 | Assign additional codes to specify the costs associated with material, equipment, labor, subcontractors and other miscellaneous costs. |
| 28. Develop budget by breaking down labor, material, overhead and profit costs. |  |  |  |
| ■ |  | 1 | Create the budget in concert with the labor and materials tracking report. |
| ■ |  | 2 | Establish a budget with sufficient line items to identify potential problems yet enough simplicity to avoid complex, time-consuming data entry. |
| ■ |  | 3 | Verify that labor and materials can and will be reported according to the budget line items. |
| 29. Develop schedule of values |  |  |  |
| ■ |  | 1 | Review the contract to identify the contractual format and process for developing a schedule of values. |
| ■ |  | 2 | Create the schedule of values in concert with the billing process. |
| ■ |  | 3 | Consider “rolling up” the budget so that the schedule of values has the same summary line items but fewer sub-line items. |

#### Table 4.22:  Budget Breakdown and Tracking Spreadsheet

#### Table 4.23:  Company Schedule of Values

#### Table 4.24:  Layout and Sequencing Planning Checklist

| LAYOUT AND SEQUENCING CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| --- | --- | --- | --- |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 30. Develop installation sequence and layout drawings. |  |  |  |
| ■ |  | 1 | Organize the project by areas, floors or systems |
| ■ |  | 2 | Allocate sufficient time to mentally think through the sequencing of all work processes from start through completion. |
| ■ |  | 3 | Determine whether to create sequence and layout drawings by hand (marked-up drawings) or by creating new CAD drawings. |
| ■ |  | 4 | Create daily installation drawings at least one day prior to the date when the work needs to be performed so that the drawings can be distributed each morning to foremen and field crews. |
| ■ |  | 5 | Review the sequence daily or weekly to ensure the project is progressing as expected. |
| 31. Develop field instructions, including panel, pull or conduit schedules. |  |  |  |
| ■ |  | 1 | Review the sequence and installation process to identify any additional information that might minimize questions and improve productivity. |
| ■ |  | 2 | Create the panel, pull or conduit schedules in conjunction with the installation drawings so that they can be distributed as a package to the foremen or field crews. |
| ■ |  | 3 | When repetitive work is scheduled on a project, develop field instructions and drawings |
| 32. Develop prefabrication drawings for field use (when applicable). |  |  |  |
| ■ |  | 1 | For systems that are partially or completely prefabricated in a prefabrication shop, develop drawings that show how the prefabricated parts should be assembled and installed in the field. |
| ■ |  | 2 | For systems prefabricated in a shop, ensure the prefabricated parts are clearly labeled and that these labels correspond to an assembly and installation scheme identified on the drawings. |
| ■ |  | 3 | If on-site prefabrication is scheduled, the drawings should identify the step-by-step process of how each piece is assembled into the prefabricated system. |
| ■ |  | 4 | If on-site prefabrication is scheduled, separate drawings should also be created to identify how the prefabricated parts should be installed. |
| ■ |  | 5 | Distribute the prefabrication drawings to the foremen or field crews that will perform the work. |

#### Table 4.25:  Schedule Development Planning Checklist

| SCHEDULE DEVELOPMENT CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| --- | --- | --- | --- |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 33. Review customer’s (general contractor’s) schedule and timeline. |  |  |  |
| ■ |  | 1 | Complete the “Customer’s Schedule Review Items” checklist (see Table 4.26) |
| ■ |  | 2 | Initiate or attend a customer schedule review meeting to identify any special requirements and clarify any questions. |
| 34. Identify work that impacts electrical activities. |  |  |  |
| ■ |  | 1 | While reviewing the overall construction schedule, annotate work that must be coordinated with other trades. |
| ■ |  | 2 | While reviewing the overall construction schedule, annotate potential conflicts that will require coordination. |
| ■ |  | 3 | Develop and submit RFIs to resolve open questions about equipment wiring or conflicts among systems. |
| ■ |  | 4 | Request an initial (and a recurring) coordination meeting to identify and resolve schedule questions and conflicts before installation begins.. |
| 35. Review the work sequence and long-lead-time material/equipment delivery dates. |  |  |  |
| ■ |  | 1 | Develop a rough draft of the electrical schedule from the sequence and installation plan. |
| ■ |  | 2 | Verify the ordering and delivery dates of long-lead-time materials and equipment. |
| ■ |  | 3 | Perform a three-way coordination between the sequencing/ installation plan, material/equipment delivery plan and the draft electrical schedule. |
| ■ |  | 4 | Modify the draft schedule and sequencing/installation plan to accommodate long-lead-time deliveries. |
| 36. Coordinate electrical schedule with the customer’s schedule. |  |  |  |
| ■ |  | 1 | After coordinating the sequencing/installation plan, material/equipment delivery plan and the draft electrical schedule, coordinate the draft schedule with the customer’s schedule and adjust as necessary. |
| ■ |  | 2 | Review the final electrical schedule with the customer, general contractor, other trade contractors and suppliers to resolve any final conflicts. |
| ■ |  | 3 | Seek approval of the schedule from the customer and general contractor. |
| ■ |  | 4 | Seek integration of the electrical schedule into the customer/general contractor’s overall project schedule. |
| 24. Develop and process log and book of submittals, cut sheets and shop drawings. |  |  |  |
| ■ |  | 1 | In addition to the integration of the electrical schedule into the overall schedule, format the final electrical schedule into an independent bar chart for tracking and control. |
| ■ |  | 2 | Select the type of bar chart to develop and track. |
| ■ |  | 3 | Save the original approved schedule as the baseline so that progress can be tracked and delays can be documented. |
| ■ |  | 4 | Distribute the electrical bar chart schedule to the customer, general contractor, various subcontractors and suppliers. |

#### Table 4.26:  Customer’s Schedule Review Items

| CUSTOMER’S SCHEDULE REVIEW CHECKLIST |  |
| --- | --- |
| Completed | Item to Review |
| ■ | Identify the overall project start date: |
| ■ | Identify the electrical work start date: |
| ■ | Identify the overall project completion date: |
| ■ | Identify the electrical work completion date: |
| ■ | List any interim milestones: |
| ■ | Is the project divided into phases? |
| ■ | Identify the start and completion dates for each phase (if applicable): |
| ■ | Does the contract include a liquidated damages clause? |
| ■ | Does the contract include an incentive for early completion? |
| ■ | Can the electrical work be completed in the timeframe identified in the contract documents? |
| ■ | If the schedule must be compressed, create a plan for compressing the schedule and completing the work by the contractual completion date. |
| ■ | Identify unusual scheduling requirements (such as night work, second shift work, after-school work hours, escort required, etc.): |
| ■ | Will the owner furnish any items, such as materials or equipment? |
| ■ | Identify the “deliver no later than” dates that owner-furnished items must be delivered to the jobsite. |
| ■ | Will any portion of the work be installed by the owner’s own workforce or a separate contract? (example: automated shelving systems) |
| ■ | Identify the “install no later than” dates that owner-installed items must be completed. |
| ■ | Identify techniques that will speed up the completion of the work. |
| ■ | Review the sequencing/installation plan to determine how the electrical work fits into the overall project schedule. |
| ■ | Identify work that has already been completed: |
| ■ | Identify work in progress and percent complete: |
| ■ | Identify non-electrical activities that must be completed before the electrical portion of the work can begin. |
| ■ | Are you aware of any pending changes to the overall project or electrical work? |
| ■ | If yes, describe the pending changes: |
| ■ | Do you anticipate crowded site conditions? |
| ■ | If yes, consider scheduling some of the electrical work during a second shift to improve productivity. |

#### Table 4.27:  Schedule Development Best Practices and Rules-of-Thumb

| SCHEDULE DEVELOPMENT BEST PRACTICES AND RULES-OF-THUMB |  |
| --- | --- |
| Best Practice Number | BEST PRACTICE/RULE-OF-THUMB DESCRIPTION |
| 1 | Seek scheduling input from the field superintendent and foremen. They often understand how the work will be accomplished and how the installation method corresponds to the crew size and duration. |
| 2 | Develop the first draft schedule using actual durations to determine whether the electrical work can be completed by the contractual completion date. If the schedule must be compressed, build the compression into the second draft schedule. |
| 3 | Consider developing a resource-loaded schedule so that the expenditures from the schedule can be compared to the expenditures from the cost report. |
| 4 | Compare the estimated work hours for an activity (or work process) to the scheduled duration of that activity (or work process). Then, either adjust the duration based on estimated work hours and expected crew size, or adjust the crew size based on the estimated work hours and allowable duration. |
| 5 | Be sure the schedule takes into account the time of year when the work item will be performed and the possible weather that can be expected. Excessive heat, cold, humidity, rain or wind can significantly impact the progress of the work. |
| 6 | Understand when major materials and equipment items will be delivered to the jobsite. The schedule may need to be adjusted to accommodate the delivery of those items. |
| 7 | Be sure the schedule clearly documents the date when owner-furnished materials and equipment must be received. Also, make sure the owner knows when these items are required, and seek their acknowledgement in writing. |
| 8 | Review the schedule of other specialty contractors to identify work that will impact the electrical schedule. For example, if the air conditioning unit will require a power connection, completion of the connection must occur after the unit has been delivered and installed. Hence, the electrical work must be coordinated with the mechanical work. |
| 9 | The electrical schedule should incorporate the work of any electrical subcontractors, such as the fire alarm installer and tester. Review and incorporate your subcontractors’ work into your own schedule and be sure to provide updates if the schedule changes. |
| 10 | If crowded conditions or overmanning is expected on a jobsite (due to a small site or an acceleration of the work), consider scheduling some of the electrical work during a second shift to improve workflow and increase productivity. |
| 11 | Once the electrical schedule has been reviewed and approved by the customer/general contractor, document delays and changes to the sequence caused by others. Good documentation can improve your chances of receiving a time extension and financial compensation. |
| 12 | When developing work activities or elements for the schedule, review the budget, cost codes and installation sequence plan. Create work elements that comprise no more than 5% of the scope of work so that inaccuracy in tracking progress will not have a significant impact on the percent complete. |
| 13 | Consider creating a computerized bar chart schedule. Tracking and control will be greatly simplified if the updates can be made in a computer system. |
| 14 | Consider dividing the schedule into areas or systems, such as first floor, second floor, etc. This will simplify tracking and control, especially on larger projects. |
| 15 | If some of the work is repetitive (such as conduit and wire on the first floor, second floor, etc.), consider creating these activities in your computer scheduling software and simply cutting and pasting as many times as the work occurs. The dates and durations can then be modified for each area of work. |

#### Table 4.28:  Tracking and Control Planning Checklist

| TRACKING AND CONTROL CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| --- | --- | --- | --- |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 38. Customize the computerized tracking and control system (database/ schedule/etc.) for the current project. |  |  |  |
| ■ |  | 1 | Review the tracking and control best practices (Table 4.31). |
| ■ |  | 2 | Complete the tracking and control tools checklist (Table 4.32). |
| ■ |  | 3 | Select appropriate computerized tracking and control tools for the project. |
| ■ |  | 4 | Modify the tracking and control tools for the project. |
| 39. Develop labor and materials tracking report. |  |  |  |
| ■ |  | 1 | Review the cost estimate and associated budget and cost code scheme. |
| ■ |  | 2 | Match the cost estimate/budget work items to crew assignments so that labor and materials can be tracked easily. |
| ■ |  | 3 | Select the reports to be created and used for monitoring progress. |
| ■ |  | 4 | Develop the selected reports by inputting project data into the reporting system (database or accounting system). |

#### Table 4.29:  Tracking and Control Best Practices

| TRACKING AND CONTROL BEST PRACTICES |  |
| --- | --- |
| Best Practice Number | BEST PRACTICE/RULE-OF-THUMB DESCRIPTION |
| 1 | Remember that tracking and control involves a time-cost tradeoff. The more detailed the tracking and control system is, the more time must be spent on entering data and the greater the overhead costs will be. You must balance detail with simplicity. |
| 2 | Be sure to take into account the financial information needs of banks and bonding companies when setting up your control system. |
| 3 | If your company keeps track of historic costs, be sure the tracking and control system captures the right data in the proper format so that it can be added to the historic cost database. |
| 4 | Match budget/cost control line items with field work items so that labor hours can be easily reported and tracked. |
| 5 | Review the daily labor reporting procedures with the field supervisor and foremen. Be sure they understand how to code timecards so that the work performed can be directly associated with line items in the budget and tracking reports. |
| 6 | Deviations between actual and estimated costs and work hours should be discussed with the field supervisor each week to identify and correct problems immediately. |
| 7 | Seek feedback from the crew members about the causes of poor productivity and cost/labor hours overruns. |
| 8 | Work together with crews to improve productivity. Often, management actions or inactions contribute to productivity outcomes. For example, poor instructions can hinder productive work, while speedy responses to questions can help increase productivity. |
| 9 | If the crew members complete the work in fewer hours than estimated, provide a reward to thank them for their hard work, such as free lunch or special recognition. |
| 10 | Try using incentives regularly to improve productivity. |
| 11 | Make sure your data entries are as accurate as possible. Remember that cost reports should provide the project manager with a realistic financial overview of the project. |
| 12 | A negative variance between estimated and actual cost and work hours should be addressed through corrective action. One of the main benefits of monthly cost reporting is to identify problems early enough to take corrective action. |

#### Table 4.30:  Tracking and Control Tools Checklist

| TRACKING AND CONTROL TOOLS CHECKLIST |  |  |
| --- | --- | --- |
| Completed | Date Completed | ITEM |
| Identify the goals of your tracking and control system. Do you want to: |  |  |
| ■ |  | Monitor profitability? |
| ■ |  | Identify variations in costs and work hours? |
| ■ |  | Track productivity of the workforce? |
| ■ |  | Contribute to your historical costs database? |
| ■ |  | Document costs that are beyond the initial scope of work? |
| ■ |  | Track changes in cost and work hours? |
| ■ |  | Create contractually-mandated cost reports for the customer? |
| ■ |  | Evaluate the effectiveness of your management team? |
| ■ |  | Conduct risk analyses on future projects of a similar type? |
| ■ |  | Create a project schedule, and format it so that you can update the progress of all schedule line items (see Activity 37). Match schedule line items to budget line items to facilitate effective tracking. |
| ■ |  | As an alternative, create a resource-loaded schedule that will permit you to track cost and labor hours as you track schedule progress. |
| ■ |  | Create a manpower loading chart that identifies your crew size and composition for each week of the project (see Figure 4.13). |
| ■ |  | Customize the computerized project management program so that you can use it as a tool to track RFIs, submittals, purchase orders, deliveries and change orders. |
| ■ |  | Create a progress report to track variances in costs and labor hours. Your progress report should track budgeted line items. |
| ■ |  | Create a labor productivity report to compare estimated to actual productivity and identify solutions to problems. Daily time sheets should be coded to match budget line items. |
| ■ |  | Other: |
| ■ |  | Other: |

#### Figure 4.31: Daily Labor Time Report

#### Table 4.33:  Construction Execution Kickoff Meeting Agenda

CONSTRUCTION EXECUTION KICKOFF MEETING AGENDA

Agenda Items:

- Project overview

  - Project name

  - Location

  - Type of work

  - Contract cost

  - General scope of work

- Introduce internal team members and any changes in team members since planning meeting.

  - Project Manager

  - Field Supervisor

  - Foremen

  - Estimator

  - Accounting representative

  - Purchasing Agent

  - Director of Operations

  - Other internal team members

- Identify external team members and any changes in team members since planning meeting.

  - Owner/Customer

  - Architect/Engineer

  - General Contractor/Construction Manager

  - Other Specialty Subcontractors

  - Vendors/Suppliers

- Review the general scope of work.

  - Provide an overview of the project scope of work and the electrical scope

  - Review major work performed by others

- Review the meetings schedule.

  - Internal office and jobsite progress meetings

  - Jobsite safety and coordination meetings

  - Project progress and coordination meetings

  - Other meetings

- Review the Request for Information (RFI) Process.

  - Standard company RFI procedure

  - Contractual language regarding RFIs and the RFI process

  - Current outstanding RFIs

- Review the change order process.

  - Contract language regarding changes and the change order process

  - Standard company change order and field change processes

  - Documentation of changes, delays, disruptions and disputed work

- Review the submittal process.

  - Contract language regarding submittals and the submittal process

  - Standard company submittal processes

  - Following up on late submissions and approvals

- Review the billing process.

  - Contract language regarding billing and the payment process

  - Standard company billing processes

  - Subcontractor/supplier/vendor invoicing and payment

  - Following up on late payments or open accounts receivable

- Review the tracking and control process.

  - Labor reporting

  - Progress reporting and percent complete

  - The progress update timeline

  - Standard company progress update procedures

- Review the schedule and milestones.

  - Customer-furnished schedule

  - Electrical bar chart schedule

  - Work by others that will impact the electrical work

  - Important material and equipment delivery dates

  - Schedule updating to reflect percent complete

- Review site logistics and material storage and staging.

  - Site access

  - Parking

  - Material delivery procedures

  - Material storage locations

  - Trailer locations (if applicable)

  - Site cleanup requirements

  - Temporary power and lighting requirements

- Review special safety issues.

- Review other items specific to this project:

#### Table 4.34:  Construction Execution Kickoff Meeting Checklist

| CONSTRUCTION EXECUTION KICKOFF CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| --- | --- | --- | --- |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 40. Review meeting schedule. |  |  |  |
| ■ |  | 1 | Review the schedule of weekly internal meetings associated with the project. |
| ■ |  | 2 | Review the schedule of weekly project meetings conducted by the customer or general contractor. |
| ■ |  | 3 | Identify the internal team members that will be responsible for attending the internal and external meetings. |
| 41. Review request for information (RFI) process. |  |  |  |
| ■ |  | 1 | Review the contract for a customer-mandated request for information (RFI) process. |
| ■ |  | 2 | Review the company standard procedure for developing, processing, tracking and closing out a request for information. |
| ■ |  | 3 | Modify the company standard RFI procedure, as necessary, to conform to the contractually-mandated process. |
| 42. Develop prefabrication drawings for field use (when applicable). |  |  |  |
| ■ |  | 1 | Review the contract for a customer-mandated change order (CO) process and field change request process. |
| ■ |  | 2 | Review the company standard change order procedure and field change request/management process. |
| ■ |  | 3 | Discuss the process for documenting changes, delays and disruptions in the work flow and sequence. |
| ■ |  | 4 | Discuss the process for tracking and following up on change order requests and payment for field change directives. |
| 43. Review submittal processing procedures. |  |  |  |
| ■ |  | 1 | Review the contract documents for a customer-mandated submittal processing procedures. |
| ■ |  | 2 | Review the company standard procedure for developing, processing, tracking and receiving approval for project submittals. |
| ■ |  | 3 | Modify the company standard submittal procedure, as necessary, to conform to the contractually-mandated process. |
| 44. Review billing and invoicing procedures |  |  |  |
| ■ |  | 1 | Review the customer/general contractor’s process and timeline for invoicing, lien waivers and payment. |
| ■ |  | 2 | Review the internal billing cycle established by the accounting department. |
| ■ |  | 3 | If necessary, adjust the internal billing cycle to conform to the customer/general contractor’s invoicing cycle. |
| ■ |  | 4 | Discuss the process for following up with the customer/general contractor on late unpaid invoices. |
| 45. Review project and field reporting and tracking procedures. |  |  |  |
| ■ |  | 1 | Discuss the process for reporting labor hours and submitting timecards to the accounting office. |
| ■ |  | 2 | Discuss the process for reporting progress and percent complete. |
| ■ |  | 3 | Discuss the process for tracking material and equipment costs and purchase orders. |
| ■ |  | 4 | Review and discuss the tracking tools that will be used to monitor progress. |
| ■ |  | 5 | Review the monthly update process. |
| 46. Review electrical and customer schedules. |  |  |  |
| ■ |  | 1 | Review the electrical bar chart schedule. |
| ■ |  | 2 | Review the customer/general contractor’s schedule and/or timeline. |
| ■ |  | 3 | Discuss the process for updating the schedule. |

# Section 3: Planning Assessment and Best Practices

# The Planning Assessment Process

## Introduction to the Planning Assessment Process

Chapter 4 of this manual discusses, in detail, the model Pre-Construction planning process. This research discovered that projects that implemented a planning process similar to the model process tended to perform more successfully. Furthermore, there appeared to be 16 activities that had an especially strong influence on performance—and many of these activities were often overlooked during the planning process.

## Purpose of the Planning Assessment Process

Chapter 4 presents a series of instructions and easy-to-use checklists to guide electrical contractors through the pre-construction planning process. The purpose of this chapter is to present a scorecard that can be used to evaluate the effectiveness of the planning that was completed on a project that is about to be executed.

The chapter will begin by identifying the 16 activities that had an especially strong influence on performance in order to explain why these activities are weighted more heavily on the planning scorecard. Then, the planning effectiveness scorecard will be introduced, which includes all of the activities from the model planning process, and instructions will be provided on how to score the effectiveness of planning on a new project. Finally, a section on “score analysis” will present some rules-of-thumb and benchmark score values for projects that have various characteristics, such as large projects versus small projects, complex projects versus simple projects, and so on.

## Important and Influential Planning Activities

It is essential to note that each of the 46 preconstruction planning activities in the Model Pre-Construction Planning Process is an important part of the planning process. It is also worth noting that not every activity will require a great deal of time to complete. Indeed, many of the activities can be completed in a matter of a few minutes, particularly on smaller projects. The project manager will need to exercise skill and judgment when determining how much time to devote to each activity.

Many of the activities are clearly critical to an effective planning process. Such obvious activities as reviewing the plans and specifications, administratively setting up the project, and issuing purchase orders can directly impact the smooth execution of a project. Overall, 16 “influential activities” were identified through careful research, and these activities are identified in the next section. It is critical that the project manager understand the following:

However, 16 of those activities have a particularly strong influence on the outcome of a project.

### The 16 Influential Planning Activities

Sixteen of the pre-construction planning activities were identified as having an especially strong correlation to a successful project outcome. These activities include the following:

- Team Selection and Turnover

  - Activity 2:  Hold turnover meeting between estimator and project manager (when applicable).

  - Activity 3:  Hold separate turnover meeting between project manager and field supervisor.

- Scope and Contract Review

  - Activity 7:  Field supervisor reviews plans, specifications and schedule.

  - Activity 10: Compare estimated (bid) work activities and materials to planned performance.

  - Activity 11: Identify value engineering and prefabrication opportunities and how to simplify the work.

- Administrative Setup

  - Activity 16: Initiate a request for information (RFI) tracking and processing system.

  - Activity 17: Initiate a submittal tracking and processing system.

- Buyout Process

  - Activity 23: Request submittals, cut sheets and shop drawings.

- Material Handling Plan

  - Activity 25: Develop material delivery and handling plan.

  - Activity 26: Develop material storage and staging plan.

- Layout and Sequencing Plan

  - Activity 30: Develop installation sequence and layout drawings.

  - Activity 31: Develop field instructions, including panel, pull or conduit schedules.

  - Activity 32: Develop prefabrication drawings for field use (when applicable).

- Schedule Development

  - Activity 36: Coordinate electrical schedule with the customer's schedule.

- Construction Execution Kickoff Meeting

  - Activity 43: Review submittal processing procedure.

  - Activity 44: Review billing and invoicing procedures.

When performing pre-construction planning, extra care should be taken to include these activities in the planning process. Although it is recommended that all of the 46 activities be completed, under extraordinary circumstances, when the planning process must be abbreviated, these 16 activities should be among those that get completed.

## Planning Assessment Process

The planning assessment process provides a simple method for evaluating whether each of the 46 pre-construction planning activities has been completed and whether an activity was completed before or after a project was executed. Under ideal circumstances, all of the planning activities will be completed prior to executing the work. However, ideal circumstances are rare in the construction industry, and often, some of the planning activities must be completed after the project has been executed.

The purpose of this section is to introduce the planning effectiveness scorecard and to provide instructions on how to use the scorecard to evaluate the planning that has occurred on a new project.

### The Planning Effectiveness Scorecard

The planning effectiveness scorecard was developed as a tool to evaluate how closely a project’s actual planning process matches the Model Pre-Construction Planning Process. The scorecard, which is presented as Table 5.1 (pages 100-101), lists each of the 46 model pre-construction planning activities (Column C). Space is provided in Column D for contractors to identify whether or not the activity was performed and to assign a “performance score.”

The performance score is assigned based on whether an activity was performed or not performed and whether it was completed before or after execution using the following scale:

Using this scale, a higher summed performance score indicates that more of the pre-construction planning activities were completed before executing the work, which correlates strongly to better project performance.

Column E represents the weight assigned to each activity. As mentioned in the previous section, 16 of the activities have a stronger influence on performance, and as a result, these activities are assigned larger weights. To calculate a final score (Column F) for each activity, Column D (Performance Score) is multiplied by Column E (Weight). The planning effectiveness score is the sum of all of the total scores.

### Score Analysis

Projects that were investigated as part of the research had various characteristics. In particular, four characteristics were analyzed, including project size, initial uncertainty, bid accuracy and type of construction.

#### Project Size

Project Size is generally determined by three values: contract cost at award, original estimated total work hours and estimated peak number of electricians. Furthermore, estimated project duration is also strongly related to a project’s size.

#### Initial Uncertainty of the Project

Initial uncertainty of the project is generally determined by three values: perceived level of uncertainty (high, medium or low), percentage of the total design completed at bid and perceived level of complexity (high, medium or low).

#### Bid Accuracy

Bid Accuracy is generally determined by two concepts: a perceived accurate cost estimate and perceived accurate estimated work hours.

#### Type of Construction

Type of Construction is generally determined by classifying projects as:

- commercial,

- industrial,

- institutional

- other

# Pre-Construction Planning Best Practices

## Introduction to Pre-Construction Planning Best Practices

A significant element of the research project was the investigation of the planning practices used on several successful electrical projects. Ultimately, the planning activities that were performed on these successful projects were used to assemble a list of the best planning practices in the electrical construction industry. This section begins by defining best practices and then identifies the 25 pre-construction planning best practices that can lead to better project performance.

## What are Best Practices?

A best practice is a process or method that can lead to enhanced project performance when properly implemented.3    A best practice can also be identified as a practice that is better than one that is currently in use in a company.4    A major benefit of best practices is that they have already been implemented, tested and successfully adopted by other companies, which minimizes the uncertainty involved with executing a change in company procedures. A best practice essentially results in the sharing of a successful process rather than “reinventing the wheel.”

## The 25 Pre-Construction Planning Best Practices

Identified in the next few pages are 25 best practices arranged according to the categories of the Model Pre-Construction Planning Process. While the previous sections of this implementation guideline presented the activities that should be performed as part of a comprehensive pre-construction planning process, this section provides suggestions for further improvement to the planning activities by implementing specific best practices that have been tested by successful contractors.

### Team Selection and Turnover Best Practices

##### Best Practice 1: Select an effective project manager and field supervisor

##### Benefits:

##### Contractors reported that the two people they selected to run the job—the project manager and field supervisor—made the biggest difference in the outcome of the project; therefore, careful team selection can increase your chances of having a good job.

##### By matching up the skills of a project manager and field supervisor with the characteristics of the project, you can improve the project’s overall performance.

##### Early selection of your project team gives you time to make re-assignments in order to assemble the best team for the project.

##### Best Practice 2: Hold an extensive turnover meeting between the project manager and field supervisor

Benefits:

- Contractors reported that failure to hold a turnover meeting between the project manager and field supervisor—or a turnover that was too short—caused the project to get off to a poor start; in contrast, an extensive turnover process often resulted in a project that was well-organized and properly managed.

- For best results, assign the field supervisor to the project full-time at the initiation of the turnover meeting to ensure the field supervisor’s time and attention are devoted to the project.

##### Best Practice 3: Define the roles and responsibilities of the internal team members

- Benefits:

- A matrix or written charter that defines the team members’ roles can help eliminate duplication of effort and avoid confusion about responsibilities; this is especially important on projects that have multiple project managers, field supervisors or foremen.

- On projects with multiple project managers, clearly define the scope that each manager is responsible for; and if the project has multiple field supervisors, define the bounds of the work each must manage.

- Written roles and responsibilities provide a reference that can be used to clarify each person’s breadth of responsibility.

### Scope and Contract Review Best Practices

##### Best Practice 4:  Evaluate value engineering, prefabrication or repetitive work opportunities.

- Benefits:

- Contractors reported that even small amounts of prefabrication increased productivity and saved time and money.

- In hind sight, many contractors were able to identify value engineering or prefabrication opportunities that could have improved the performance of their bad jobs if they had planned for it ahead of time.

- In addition to prefabrication, work that could be done similar to an assembly line (one crew does the same task repeatedly, moving from area to area, with another crew following behind them) also experienced significant increases in productivity.

##### Best Practice 5: Conduct post-award field visit(s) to verify design and existing conditions.

- Benefits:

- The team can identify discrepancies between design drawings and existing conditions.

- The team can identify site issues, including access, storage, utilities, etc.

- For renovation work, the team can identify potential pitfalls and opportunities associated with existing systems and conditions.

- A site visit, especially to an existing facility, provides an early opportunity to begin sequencing the work.

- Site visits that were performed both before bid submission and after notification of award proved beneficial to the outcome of the project.

##### Best Practice 6: Hold a pre-construction meeting to clarify customer expectations.

- Benefits:

- Good communication among team members was reported as one of the primary reasons a job was viewed as a good job; therefore, a project can get off to a positive start by meeting with the customer to establish open lines of communication about each party’s expectations.

- Understanding the customer’s expectations can reduce frustration and eliminate misunderstandings throughout the construction process.

- A pre-construction kickoff meeting can provide the customer with an opportunity to explain their preferred procedures, which might not have been explicit in the contract documents.

##### Best Practice 7: Locate all underground utilities prior to execution.

- Benefits:

- Establishing the location of underground utilities during your site visit can help you determine whether any conflicts exist.

- Furthermore, if a substantial amount of site work is included in the scope, you will benefit from coordinating the new and existing utility locations among all of the trades (sewer, water, electrical, etc.).

- Laying out the utility locations prior to executing the work can improve productivity by resolving any conflicts or discrepancies.

##### Best Practice 8: Prepare a construction takeoff and estimate.

- Benefits:

- A construction takeoff can be used to verify that the original cost estimate and takeoff are correct and that the quantities of materials and labor are accurate.

- If the estimator is not the project manager, a construction takeoff will help the project manager become familiar with the details of the project.

- Likewise, the field supervisor is also encouraged to re-takeoff the job in order to understand the scope of work, the quantity of materials that will be needed and the number of crew members required.

- A construction takeoff can also help the project manager and field supervisor identify value engineering opportunities.

### Administrative Setup Best Practices

##### Best Practice 9: Develop a standardized efficient change management process.

Benefits:

- The key to a successful change management process is to have a standard written procedure that is implemented consistently by project management and field staff.

- It is also recommended that your change management process be explained to the customer in the pre-construction meeting in order to avoid tension among team members when a change situation arises.

An “open-books” method of sharing change order pricing tends to increase the trust of the customer and may speed up processing time.

##### Best Practice 10: Develop a standardized efficient request for information (RFI) process.

Benefits:

- The key to a successful request for information (RFI) process is to have a standard procedure that is implemented consistently by project management and field staff.

- It is also recommended that you discuss the RFI process with the customer to become familiar with their process and ensure they understand the importance of receiving timely answers.

##### Best Practice 11: Assign an administrative assistant to the project.

Benefits:

- An administrative assistant can handle administrative tasks, thus permitting the project manager and field supervisor to focus their attention on handling decision-making and management of the work.

- An administrative assistant can indirectly improve overall productivity by handling administrative tasks that might otherwise bog down the management team; hence, the management team can provide better support to the crews, resulting in better project productivity.

##### Best Practice 12: Develop a list of labor rules and requirements to attract quality workers.

Benefits:

- Several contractors reported a letter that was endorsed by the union, which outlined the requirements and expectations of the workforce, resulting in hiring higher quality workers.

- The letter outlined procedures for handling special drug testing, absences, tardiness, safety violations and dismissals.

- The letter was often used to hire workers from the union hall and ensured the workers understood the expectations; those workers who were not willing to abide by the “rules” were discouraged from working on the project.

### Buyout Process Best Practices

##### Best Practice 13: Order materials before execution rather than daily.

Benefits:

- Contractors reported that bulk buying could produce substantial savings.

- Furthermore, purchasing major materials ahead of time ensured that all materials were delivered on time to support progress on the job.

- The early ordering of long-lead-time materials and equipment was especially important to maintaining the schedule.

- Weekly or bimonthly ordering of standard materials also produced savings, whereas daily ordering often resulted in cost overruns because no bulk savings or discounts were recognized.

##### Best Practice 14: Order materials for efficient installation.

Benefits:

- It is strongly recommended that the purchaser (project manager, most likely) carefully review the plans and specifications to ensure that the materials that are ordered can be efficiently installed.

- For example, order cable tray or conduit in lengths that minimize cutting; or, when working in a confined space, order materials for efficient handling.

##### Best Practice 15: Arrange for a supply trailer on site to be stocked by the supplier.

Benefits:

- Contractors who used a “consignment” trailer that is stocked with daily-use materials by the supplier each week reported fewer problems with material shortages.

- An increase in productivity can be achieved by using a “consignment” trailer because the workers will not run out of materials as frequently, will not have to stop working to run to the hardware store and can work more consistently without material supply problems.

- Entrusting a supplier to provide weekly materials on “consignment” can also result in building stronger relationships with suppliers.

### Material Handling Plan Best Practices

##### Best Practice 16: Develop a material storage and staging plan.

Benefits:

- A material storage plan—which identifies whether materials and equipment are stored on-site or at an off-site location—can minimize congestion of the site and can reduce the number of times materials need to be relocated or handled.

- Projects located a long distance from the home office or located in rural areas or on interstate highways will need a storage “yard” that is located close to their work site; hence, locating and renting a suitable storage area can result in substantial time and cost savings.

##### Best Practice 17: Develop a material ordering and delivery plan.

Benefits:

- The first step to an efficient, cost-saving material purchasing process is to decide whether to order in bulk up front or order materials weekly as the need arises.

- Material ordering will likely be driven by the nature of the project; projects with repetitive work might benefit from bulk ordering and storage, whereas projects with a lot of small materials might require weekly ordering in order to avoid misplacing the small materials.

- By developing a strategy for ordering and receiving materials, the project manager can ensure that the materials are delivered on time to maintain the schedule.

- Projects that are located in downtown metropolitan cities will require a plan for delivering and receiving materials daily, since these sites rarely have the space to accommodate material storage.

### Layout and Sequencing Best Practices

##### Best Practice 18: Develop layout/installation drawings before execution.

Benefits:

- Several project managers and field supervisors identified layout as perhaps one of the most important activities they performed to ensure the success of their projects. Types of layout ranged from marking up the plans to show the sequence of work to developing complete CAD installation/design drawings. As part of the layout process, many project managers reported developing a pull schedule or conduit schedule. Clearly, a formal layout plan was important to success.

##### Best Practice 19: Develop CAD layout/installation drawings before execution.

Benefits:

- Although layout and sequencing, in any form, was important to the outcome of a project, contractors that prepared CAD installation/as-built plans strongly believed the preparation and use of CAD drawings was the key to their success.

- The CAD drawing process is also instrumental in documenting existing conditions and defining materials and methods that will be used to complete the work. Contractors that provided crews with daily installation drawings were able to remove a significant part of the uncertainty from the installation process, increasing productivity.

### Schedule Development Best Practices

##### Best Practice 20: Extensively plan the sequence of work.

Benefits:

- Sequencing is essential for determining weekly manpower loading. It can also be used to identify concurrent work, which might result in time and cost savings.

- Work should be sequenced by area and/or by floor for large projects. Furthermore, innovative manpower loading can be used to augment the sequencing plan, such as using an “assembly line” concept, where the same crew moves from area to area to perform the same tasks, or using multiple crews that engage in a productivity competition.

##### Best Practice 21: Prepare a separate bar chart schedule.

Benefits:

- In general, most contractors added line items to the general contractor/construction manager schedule. However, those contractors that developed their own bar chart schedule were better able to maintain progress, and when progress was impacted, they had documentation of the impact of delays and changes on their progress.

- A separate bar chart schedule will help a contractor track the progress of the work. Furthermore, it can be used to document delays, disruptions and changes to the work.

##### Best Practice 22: Prepare a resource-loaded schedule

Benefits:

- For a small amount of additional effort, a computerized bar chart schedule can be enhanced by associating specific material/equipment and labor hours to each line item. This helps project managers clearly see how each line item relates to the total cost of the project and to identify potential opportunities for “beating the budget.”

- The most effective resource-loaded schedules included both labor hours and material/equipment/other costs. Updates to the schedule provided project managers with immediate feedback about poor productivity, upcoming equipment needs, labor forecasts and many other problems and opportunities on the project.

### Tracking and Control Best Practices

##### Best Practice 23: Develop a labor, material and work hour tracking program.

##### Benefits:

##### A computerized tracking program provides a fast way to monitor progress after weekly work hours and purchase orders have been entered into the system.

##### The tracking program can also be used to compare estimated to actual manpower loading, crew ratios, and material costs using the earned value method (or similar method).

##### A tracking system can be used to identify

##### Over runs early in the project so that corrections or adjustments can be made to avoid losing money

##### Best Practice 24: Monitor/track labor productivity and plan for productivity improvement.

Benefits:

- High labor productivity is a primary factor that contributes to a successful project. Consequently, a significant benefit can be gained from planning the expected productivity and then comparing the actual to the planned.

- Although detailed productivity tracking, such as units per hour, might be impractical on a project, contractors can benefit from planning the expected daily or weekly progress and then tracking actual daily or weekly progress against the planned progress. Adjustments can then be made to improve productivity if expectations fall short of estimates.

##### Best Practice 25: Use a resource-loaded bar chart schedule to track progress

Benefits:

- Several contractors went beyond developing a bar chart schedule and developed a resource-loaded bar chart schedule, which was used to plan and track manpower, materials and costs.

# Reasons for Successful or Less-than-Successful Performance

## Introduction to the Performance Reasons

It has been clearly demonstrated that good preconstruction planning can improve a contractor’s chances of project success and poor planning may have a negative impact on performance. However, most contractors believe there are several other factors that contribute to good or poor performance. The purpose of this section is to identify the most common factors that contractors believe contribute to the performance on their projects.

### The Most Common Reasons Projects Performed Successfully

Nearly 50 project managers were interviewed about the performance of their electrical projects. These project managers were encouraged to identify all of the factors they believed contributed to the performance of their projects. The top reasons contractors believed projects performed successfully are as follows:

- The project manager and field supervisor did a good job scheduling and sequencing the work.

- The workforce achieved good labor productivity.

- The project achieved its targeted budget.

- The project manager and field supervisor did a good job planning the project.

- The project manager implemented an efficient material procurement process.

- The project manager implemented good project management practices.

- There was good communication among all project team members.

- The workforce developed/achieved an efficient installation process.

- The field supervisor did a good job managing the labor on the jobsite.

- The project manager was effective and efficient.

### The Most Common Reasons Projects Performed Less-than-Successfully

The top reasons contractors believed projects performed less-than-successfully are as follows:

- The workforce achieved poor labor productivity due to delays, disruptions, lack of information and other reasons.

- The project manager and field supervisor did an inadequate job scheduling and sequencing work.

- The project manager did an inadequate job managing the project.

- The design documents were poor or incomplete.

- The material procurement process was inefficient.

- The estimator made a bid mistake or the cost estimate overall was inaccurate and insufficient.

- The project exceeded its targeted budget.

- The project experienced poor communication among its internal and external team members.

- The field supervisor did an inadequate job managing the labor.

- The project manager was ineffective and inefficient.

- The project manager and field supervisor did an inadequate job planning the project.

| PLANNING EFFECTIVENESS SCORECARD |  |  |  |  |
| --- | --- | --- | --- | --- |
| (A) ACTIVITY CATEGORY | (B) ACT. NO. | (C) ACTIVITY |  | (D) SCORE |
| Team Selection and Turnover | 1 | Finalize selection of project manager, field supervisor and other key team members. |  |  |
|  | 2 | Hold turnover meeting between estimator and project manager (when applicable). |  |  |
|  | 3 | Hold separate turnover meeting between project manager and field supervisor. |  |  |
|  | 4 | Hold pre-job (planning) kickoff meeting with internal team members to assign responsibilities. |  |  |
| Scope and Contract Review | 5 | Review contract for unfavorable or high risk clauses. |  |  |
|  | 6 | Project manager reviews plans, specifications and schedule. |  |  |
|  | 7 | Field supervisor reviews plans, specifications and schedule. |  |  |
|  | 8 | Create a list of issues that need to be resolved, and begin the request for information (RFI) process. |  |  |
|  | 9 | Conduct site visit. |  |  |
|  | 10 | Compare estimated (bid) work activities and materials to planned performance. |  |  |
|  | 11 | Identify value engineering and prefabrication opportunities and how to simplify the work. |  |  |
|  | 12 | Prepare construction takeoff. |  |  |
| Administrative Setup | 13 | Set up project files, and create contact list. |  |  |
|  | 14 | Set up computerized tracking and control system (forms, database, schedule, and tracking). |  |  |
|  | 15 | Initiate a change management system. |  |  |
|  | 16 | Initiate a request for information (RFI) tracking and processing system. |  |  |
|  | 17 | Initiate a submittal tracking and processing system. |  |  |
|  | 18 | Develop a "Labor Requirements/Expectations" letter (for background check, etc.). |  |  |
| Buyout Process | 19 | Review subcontractor/supplier/vendor pricing and qualifications. |  |  |
|  | 20 | Negotiate pricing and contract conditions, and select subcontractors/suppliers/vendors. |  |  |
|  | 21 | Develop and issue purchase orders and contracts for materials and equipment. |  |  |
|  | 22 | Order long-lead-time materials and equipment. |  |  |
|  | 23 | Request submittals, cut sheets and shop drawings. |  |  |
|  | 24 | Develop and process log and book of submittals, cut sheets and shop drawings. |  |  |
| Material Handling Plan | 25 | Develop material delivery and handling plan. |  |  |
|  | 26 | Develop material storage and staging plan. |  |  |
| Budget Preparation | 27 | Develop, review or expand cost code scheme. |  |  |
|  | 28 | Develop budget by breaking down labor, material, overhead and profit costs. |  |  |
|  | 29 | Develop schedule of values. |  |  |
| Layout and Sequencing Plan | 30 | Develop installation sequence and layout drawings. |  |  |
|  | 31 | Develop field instructions, including panel, pull or conduit schedules. |  |  |
|  | 32 | Develop prefabrication drawings for field use (when applicable). |  |  |
| Schedule Development | 33 | Review customer's schedule and timeline. |  |  |
|  | 34 | Identify work that impacts electrical activities. |  |  |
|  | 35 | Review the work sequence and long-lead-time material/equipment delivery dates. |  |  |
|  | 36 | Coordinate electrical schedule with the customer's schedule. |  |  |
|  | 37 | Create a bar chart schedule. |  |  |
| Tracking and Control | 38 | Customize the computerized tracking and control system (database/schedule/etc) for the current project. |  |  |
|  | 39 | Develop labor and materials tracking report. |  |  |
| Construction Execution Kickoff Meeting | 40 | Review meeting schedule. |  |  |
|  | 41 | Review request for information (RFI) process. |  |  |
|  | 42 | Review change order process and field change management process. |  |  |
|  | 43 | Review submittal processing procedure. |  |  |
|  | 44 | Review billing and invoicing procedures. |  |  |
|  | 45 | Review project and field reporting and tracking procedures. |  |  |
|  | 46 | Review electrical and customer schedules. |  |  |
| PLANNING EFFECTIVENESS SCORE (sum of Column D) |  |  |  |  |
| 2 = Activity completed before executing the work |  |  |  |  |
| 1 = Activity completed after executing the work |  |  |  |  |
| 0 = Activity not completed |  |  |  |  |