## Best Practices
Table 4.17: Material Delivery/Storage and Site Logistics Best Practices (page 29)
Project Number: ________________________________________________________________________________
Project Name: ________________________________________________________________________________
Location: ________________________________________________________________________________
Project Manager: ________________________________________________________________________________
MATERIAL DELIVERY/STORAGE AND SITE LOGISTICS BEST PRACTICES
Best Practice Number | BEST PRACTICE DESCRIPTION
1 | Assign one person the responsibility of managing material and equipment delivery, handling storage and staging.
2 | Establish a standard unloading crew that consists of laborers or apprentices.
3 | Establish standard procedures for receiving, handling and storing materials, and strictly enforce the standard.
4 | Develop a storage site layout that identifies where the materials and equipment are stored, and annotate the location on the material and equipment delivery and storage log.
5 | Develop a storage site identification system that provides a method to document and track the location of all materials that have been delivered to the jobsite.
6 | Establish storage space for each major material item or group (pipe, wire, boxes, etc.).
7 | Sort and store the materials as soon as it is delivered to the site.
8 | Allow storage space for waste or excess materials, and remove them as soon as possible.
9 | Ensure the material and equipment is adequately secured and protected from the elements.
10 | Make sure the materials manager is notified of pending deliveries.
11 | Return all damaged, excess or incorrect materials to the vendor immediately in order to keep the site free from clutter.
12 | Arrange to have materials delivered just before you need them so that storage and handling is kept to a minimum.
13 | If materials are ordered in bulk, ask the vendor to store the materials at their office until you need them on the jobsite (also consider paying extra for this option).
14 | Consider using a material consignment trailer, where the vendor inventories the trailer each week, restocks it and only charges you for the materials you use.
15 | Try to place materials/equipment at the location where they will be used to improve access to the materials/equipment and minimize handling.
16 | Arrange to have materials packaged for efficient unloading, handling and installation.
17 | Determine ahead of time what equipment will be needed to unload and handle material deliveries.
18 | Evaluate the capacity of material lifts, freight elevators and cranes to ensure they can safely move the materials and equipment.
19 | Locate your toilet facilities as close to the work areas as possible.
20 | Locate your break facilities and trash containers as close to the work areas as possible.
21 | Develop a map of facility locations, and distribute it to workers and suppliers/vendors.