## 9.16

## MANAGEMENT DIRECTIVES FOR PURCHASING

Procurement is one of the most important activities in project management is to properly purchase the materials and to align the subcontractors on the project. Our ultimate goal is to procure the materials at the same value or less than what we had at bid day. By buying the project out 100% reduces the potential risk of material escalation. The following is a procedure that will help you understand what is expected of the PM and others that support the project management process.

## • The Purchasing Vision o Pre-planning Process

PM is to work with the Foreman that is assigned to the project and develop a take off reflecting the way they are going to stage and  build the job incorporating all of the Value Engineering, Pre-Fab, manufacturing ideas, and the re-routing of duct banks and conduit racks etc. After the take off is complete a bill of materials for commodities such as fittings, supports nuts bolts should be developed.

## o Master Purchase Orders

Quoted materials should be in•unediately re-quantified and verified and P.O.'s should be developed with the following information. (All of the points listed below need to be line items on the Purchase Order)

- Accurate quantities of materials

- Required Delivery information o Date Required on the site o Proper Address o Submittals that are required as well as a copy of the specifications that are needed to supply the right information on the submittal. Plus the date that the submittal is required along with the required number of copies

Include in the PO a list of all of the required spare parts and the O&M manuals if required.

All required start-up support that is required needs to be clearly stated in the Purchase order.

- The total cost of the purchase order needs to be verified as well as the cost of materials in the case additional material is required.

- Make sure that Sales Tax at the appropriate rate is included. If the job is tax-exempt the required tax-exempt number needs to be filed in the office.

- Make sure that the ancillary parts are included on the PO such as lamps, batteries, spare parts if applicable etc.

## Subcontracts

- If the contract is $10,000.00 or more a Subcontract needs to be prepared and executed.

- All sales tax or fees need to be included in their total contract amount or negotiated prior to contract execution.  The scope of work needs to be included in detail and assure that it is the same as or exceeds the expectation of the drawings and specification.

- A subcontractor is anyone performing work in behalf of GSL Electric on a project. i.e. Low voltage contractors, instrumentation, engineering and design, lightning protection. Etc.

## Commodities

- Conduit/ wire/ fittings/ support materials/ etc.

- All commodities need to be identified after the PM and foreman take-off is complete. A bill of materials needs to be established. At which time contact the vendor of choice to support an inventory control system in a conex to assure that we only buy what we need and return in good order what was overstocked.

- All quantities and unit prices as well as how long these prices are good for (possibly the duration of the project) needs to be stated in the purchase order.

## General Expenses and rental equipment

- Determine what equipment and tools that will be required for the project and the timing of when the tools and equipment will be needed based upon a working schedule. Issue a PO based on the needs stated above.

The submittal process o Scour through the specification and determine all of the items in each specifications section that need to be submitted on prior to finalizing the PO copy that portion of the specification entitled submittal in each section and submit this information with our purchase order to the vendor or the Subconfractor to assure a smooth tansition will occur during the submittal process. It is the PM's responsibility to assure and check each submittal prior to transmitting them to the General Confractor or the owner. With highly sophisticated engineers and owners it may be prudent to have a presubmittal review to create an atmosphere of cooperation and completeness.

- All submittals are to be logged in and tacked through the Viewpoint Software.

Every time a submittal is given to the GC or the owner a letter of transmittal is required to be attached with a signed copy returned to the project file.

- Always retain one copy for our records that reflect the approved submittal. o No item being submitted on is to be released for shipment or manufacturing until such time that the submittal is approved with no notations, if there are notations but approved all notations are to be tansmitted to the vendor to make such modifications prior to manufacturing or shipping.

- Issuing purchase orders o Attached are the procedures for dealing with purchase orders and entering them in to Viewpoint software.

o Philosophy of purchasing equipment.

Choose the most cost effective vendor.

Low price isn't always the cheapest or the most cost effective.  Verify that the bills of materials all as equal and meet the specification and the intent of the project.

- Re-assure that the O&M manuals spare parts etc. are not in addition to the quote.

- Prior to issuing PO's we need to make sure that we have completed the internal Value Engineering to assure that we are not purchasing parts that may be changed next week.  If at all possible we need to support the Vendors that support us on bid day. (Not at all costs but if they are close give them the benefit of the doubt) This is strictly a judgment call.

Insure that commodities such as wire, and conduit at times, that the terms and conditions and freight are allowed if at all possible. Obviously if it is a small job it will be local shipments.

0 VOLATILE MATERIALS WITH POTENTIAL ESCALATION

PROBLEMS NEED TO BE IMMEDIATELY DEALT WITH

AFTER AWARD OR A FIRM LETTER OF INTENT. THESE DECISIONS WILL NEED BRANCH MANAGEMENT APPROVAL AND m CASES CORPORATE APPROVAL.

Advantages of Pre-Buyout

PW Foreman can verify the cost of the materials vs. the estimate o The foreman can spend his or her time running the job rather than running for parts.

- PM can control the risk of escalation.

- Productivity of crew 	increase due to the availability of material.

- Less day to day planning required therefore more time for the foreman and the PM to improve and monitor field productivity.

- More time to sharpen the saw and develop new and better ways.

- Total Results o The PM can manage more work more effectively.

- Decrease the amount of stress and effort in the branch purchasing department.

- Smoother running projects.

- Decrease the number of schedule conflicts due to late material deliveries.

- o Have control of the budget. (Materials, Subs, and General Expenses.) o Higher profit margins.