## Pre-Construction Checklist
Table 4.1: Checklist of Pre-Construction Planning Activities (page 15)
Project Number: ________________________________________________________________________
Project Name: ________________________________________________________________________
Location: ________________________________________________________________________
Estimator: ________________________________________________________________________
Project Manager: ________________________________________________________________________
PRE-CONSTRUCTION PLANNING CHECKLIST
| COMPLETION DATE | ACTIVITY CATEGORY | ACT. NO. | ACTIVITY
☐ |  | Team Selection and Turnover | 1 | Finalize selection of project manager, field supervisor and other key team members.
☐ |  |  | 2 | Hold turnover meeting between estimator and project manager (when applicable).
☐ |  |  | 3 | Hold separate turnover meeting between project manager and field supervisor.
☐ |  |  | 4 | Hold pre-job (planning) kickoff meeting with internal team members to assign responsibilities.
☐ |  | Scope and Contract Review | 5 | Review contract for unfavorable or high risk clauses (recommended).
☐ |  |  | 6 | Project manager reviews plans, specifications, and schedule.
☐ |  |  | 7 | Field supervisor reviews plans, specifications, and schedule.
☐ |  |  | 8 | Create a list of issues that need to be resolved and begin the request for information (RFI) process.
☐ |  |  | 9 | Conduct site visit (recommended).
☐ |  |  | 10 | Compare estimated (bid) work activities and materials to planned performance.
☐ |  |  | 11 | Identify value engineering and refabrication opportunities and how to simplify the work.
☐ |  |  | 12 | Prepare construction takeoff.
☐ |  | Administrative Setup | 13 | Set up project files and create contact list.
☐ |  |  | 14 | Set up computerized tracking and control system (forms, database, schedule, tracking).
☐ |  |  | 15 | Initiate a change management system.
☐ |  |  | 16 | Initiate a request for information (RFI) tracking and processing system.
☐ |  |  | 17 | Initiate a submittal tracking and processing system.
☐ |  |  | 18 | Develop a "Labor Requirements/Expectations" letter (for background check, etc.) (recommended).
☐ |  | Buyout Process | 19 | Price and/or review subcontractor/supplier/vendor prices and qualifications.
☐ |  |  | 20 | Negotiate pricing and contract conditions, and select subcontractors/suppliers/vendors.
☐ |  |  | 21 | Develop and issue purchase orders and contracts for materials and equipment.
☐ |  |  | 22 | Order long-lead-time materials and equipment.
☐ |  |  | 23 | Request submittals, cut sheets and shop drawings.
☐ |  |  | 24 | Develop and process log and book of submittals, cut sheets and shop drawings.
☐ |  | Material Handling Plan | 25 | Develop material delivery and handling plan.
☐ |  |  | 26 | Develop material storage and staging plan.
☐ |  | Budget Preparation | 27 | Develop, review or expand cost code scheme.
☐ |  |  | 28 | Develop budget by breaking down labor, material, overhead and profit costs.
☐ |  |  | 29 | Develop schedule of values.
☐ |  | Layout and Sequencing Plan | 30 | Develop installation sequence and layout drawings.
☐ |  |  | 31 | Develop field instructions, including panel, pull or conduit schedules.
☐ |  |  | 32 | Develop prefabrication drawings for field use (when applicable).
☐ |  | Schedule Development Tracking and Control | 33 | Review customer's schedule and timeline.
☐ |  |  | 34 | Identify work that impacts electrical activities.
☐ |  |  | 35 | Review the work sequence and long-lead-time material/equipment delivery dates.
☐ |  |  | 36 | Coordinate electrical schedule with customer schedule (recommended).
☐ |  |  | 37 | Create a bar chart schedule (recommended).
☐ |  |  | 38 | Customize the computerized tracking and control system (database/schedule/etc.) for the current project.
☐ |  |  | 39 | Develop labor and materials tracking report.
☐ |  | Construction Execution Kickoff Meeting | 40 | Review meeting schedule.
☐ |  |  | 41 | Review request for information (RFI) process.
☐ |  |  | 42 | Review change order process and field change management process.
☐ |  |  | 43 | Review submittal processing procedure.
☐ |  |  | 44 | Review billing and invoicing procedures.
☐ |  |  | 45 | Review project and field reporting and tracking procedures.
☐ |  |  | 46 | Review electrical and customer schedules.