## Slide 1
BID PREPARATION PLANNING
PRE-CONSTRUCTION PLANNING
Team Selection
and Turnover
Administrative
Setup
Scope and
Contract Review
Layout and
Sequencing
Buyout Process
Schedule
Development
Budget
Preparation
Material
Handling Plan
Tracking and
Control
Construction
Execution Kickoff
JOBSITE MANAGEMENT PLANNING

## Slide 2
PRE-CONSTRUCTION PLANNING
Team Selection
and Turnover
1. Finalize selection of
project manager, field
supervisor, and other key
team members.
2. Hold turnover meeting
between estimator and
project manager.
3. Hold separate turnover
meeting between project
manager and field super-
visor.
4. Hold pre-job (planning)
kickoff meeting with
internal team members
to assign responsibilities.
Administrative
Setup
Scope and
Contract Review

## Slide 3
PRE-CONSTRUCTION PLANNING
Team Selection
and Turnover
Administrative
Setup
13. Set up project files and create
contact list.
14. Set up computer tracking and
control system.
15. Initiate a change management
system.
16. Initiate an RFI tracking and
processing system.
17. Initiate a submittal tracking and
processing system.
18. Develop a "Labor Requirements/
Expectations" letter
(recommended).
Scope and
Contract Review
5. Review contract for unfavorable
or high risk clauses (recommended).
6. Project manager reviews plans,
specifications, and schedule.
7. Field supervisor reviews plans,
specifications, and schedule.
8. Create a list of issues that need to
be resolved and begin the request
for information (RFI) process.
9. Conduct site visit (recommended).
10. Compare estimated (bid) work
activities and materials to
planned performance.
11. Identify value engineering and
prefabrication opportunities and
how to simplify the work.
12. Prepare construction takeoff.
Layout and
Sequencing
Budget
Preparation
Buyout
Process

## Slide 4
PRE-CONSTRUCTION PLANNING
Scope and
Contract Review
Layout and
Sequencing
30. Develop installation sequence
and layout drawings.
31. Develop field instructions,
including panel, pull or conduit
schedules.
32. Develop prefabrication drawings
for field use.
Schedule
Development
33. Review customer's schedule and
timeline.
34. Identify work that impacts
electrical activities.
35. Review the work sequence and
long-lead-time material/equipment
delivery dates.
36. Coordinate electrical schedule
with the customers schedule.
37. Create a bar chart schedule
(recommended).
Buyout
Process
19. Request/review subcontract/
supplier/vendor prices and
qualifications.
20. Negotiate pricing and contract
conditions and select
subcontractors.
21. Develop and issue purchase
orders and contracts for materials
and equipment.
22. Order long-lead-time materials
and equipment.
23. Request submittals, cut sheets
and shop drawings.
24. Develop and process log and
book of submittals, cut sheets,
and shop drawings.
Material Handling
Plan
25. Develop material delivery and
handling plan.
26. Develop material storage and
staging plan.
Budget
Preparation

## Slide 5
PRE-CONSTRUCTION PLANNING
Scope and
Contract Review
Budget
Preparation
27. Develop, review or expand
cost code scheme.
28. Develop budget by breaking
down labor, material, over-
head and profit.
29. Develop schedule of values.
Schedule
Development
Tracking and
Control
38. Customize the computerized
tracking and control system
for the current project.
39. Develop labor and materials
tracking report.
Construction
Execution Kickoff