## Pre-Job Kickoff Agenda
Table 4.4: Pre-Job Planning Kickoff Meeting Agenda (page 17)
Project Number: ________________________________________________________________________________
Project Name: ________________________________________________________________________________
Location: ________________________________________________________________________________
Estimator: ________________________________________________________________________________
Project Manager: ________________________________________________________________________________
PRE-JOB PLANNING KICKOFF MEETING AGENDA
Agenda Items:
1. | Project overview
| a. | Project name
| b. | Location
| c. | Type of work
| d. | Contract cost
| e. | General scope of work
| f. | Identify potential opportunities and challenges of the project
2. | Introduce internal team members.
| a. | Project manager
| b. | Field supervisor/foreman
| c. | Estimator
| d. | Accounting representative
| e. | Other internal team members (i.e., CAD operator, purchasing agent, etc.)
3. | Identify external team members.
| a. | Owner/customer
| b. | Architect/engineer
| c. | General contractor/construction manager
| d. | Other specialty subcontractors
| e. | Vendors/suppliers
4. | Review the general scope of work.
| a. | Provide an overview of the project scope of work and the electrical scope.
| b. | Review major work performed by others.
5. | Review the contract cost.
| a. | Review direct costs and the contract cost.
| b. | Review overhead, profit and contingency funds.
6. | Review purchasing of materials, equipment and services from subcontractors/vendors.
| a. | Review subcontractors and suppliers scope of work and qualifications.
| b. | Identify all pre-contract commitments and promises.
| c. | Verify minority business requirements.
7. | Review the schedule and milestones.
| a. | Review the owner-furnished schedule.
| b. | Review any preliminary schedule submitted with the bid or construction schedule.
| c. | Review work by others that will impact the electrical work.
| d. | Identify important material and equipment delivery dates.
8. | Review manpower requirements and labor rates.
| a. | Review the manpower loading chart (if available).
| b. | Identify the estimated crew mix.
| c. | Identify any wage increases.
9. | Review the contract—identify any special clauses that require careful consideration.
10. | Review administrative procedures.
| a. | Administrative setup
| b. | Request for Information (RFI) procedures and setup
| c. | Submittal process and setting up the submittal tracking system
| d. | Change order procedures and setting up the change management system
| e. | Field reporting requirements
| f. | Budget preparation and billing procedures
| g. | Cost control and setting up the tracking system
11. | Review special safety issues.
12. | Review site logistics and material storage and staging.
| a. | Site access
| b. | Parking
| c. | Material delivery and movement procedures
| d. | Material storage locations
| e. | Trailer locations (if applicable)
| f. | Site cleanup requirements
| g. | Temporary power and lighting requirements
13. | Review bond, permit and certificate of insurance requirements
14. | Review other items specific to this project:
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________