SOP 9.060.41 – Prepare Material Handling Plan

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs:

- 9.055.41 – Procurement of Large Feeder Wire

- 9.070.41 – Prepare Layout & Sequencing Plan

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.5 Project Superintendent

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To define the process for creating a job-specific Material Handling Plan that ensures efficient, safe, and cost-effective delivery, storage, movement, and installation of materials on-site.

Scope

Applies to all projects requiring material movement by hand, cart, equipment, or lift from delivery to final install. Targeted at PMs, Foremen, GSs, and warehouse personnel.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Leads development of the plan and ensures field team involvement. |
| General Superintendent | Reviews site conditions, labor plan, and equipment usage for material flow. |
| Foreman / Field Lead | Identifies install sequence, material delivery location, and staging needs. |
| Warehouse / Buyer | Confirms packaging and delivery method from vendor. |
| Safety Coordinator | Reviews for material handling risks and lifting compliance. |

Required Documents and Tools

- Construction drawings

- Delivery schedule

- Prefab plan (if applicable)

- Site logistics plan

- Material Handling Plan Template

- Equipment specs and lift plans (if required)

Procedure

Step 1: Review Site and Scope

- PM and GS review:

  - Material types and volume (conduit, feeders, devices, panels, etc.)

  - Delivery access and restrictions

  - Vertical transport needs (stairs, elevators, cranes)

  - Areas with manual handling concerns

Step 2: Develop Handling Strategy

- Define handling method by material type:

  - Hand carry

  - Carts / dollies

  - Pallet jacks / forklifts

  - Rigging or hoisting

- Identify where staging racks or temp storage will be used

- Assign receiving responsibilities by crew or shift

Step 3: Coordinate with Vendors and Warehouse

- Confirm packaging type (crates, bundles, loose, racked)

- Plan sequence of material release by prefab or warehouse

- Request custom labeling or grouping if beneficial

- Confirm timing to align with field manpower and sequence

Step 4: Incorporate Safety and Ergonomics

- Safety team reviews lifting practices, PPE, and ergonomic considerations

- Identify materials requiring 2-man carry, mechanical lift, or rigging

- Document procedures for long or awkward materials (e.g., pipe over 10’)

Step 5: Finalize and Share

- PM completes Material Handling Plan and reviews with field team

- Plan is posted in trailer and shared with warehouse team

- Updated throughout the project as site conditions evolve

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Material Handling Plan | Project Manager | Project Coordination Folder |
| Handling Method Matrix | Foreman / PE | Site Logistics Folder |
| Safety Review Checklist | Safety Coordinator | Safety Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Plan completed before first major material delivery | 100% |
| Safety approval before heavy lifting or rigging begins | 100% |
| Warehouse and field teams aligned on delivery format | 100% |

References

- Site Logistics & Safety Plan

- Prefab Plan and BOM

- Equipment Handling Guidelines

Appendix

- Material Handling Plan Template

- Sample Conduit Handling Diagram

- Lifting Risk Assessment Form