SOP 9.2.120 – Establish Tracking & Control Systems

Department: Project Management / Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting
Reference: GSL Pre-Construction Planning – Tracking & Control

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

- 7.4.4 Purchasing Manager

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To implement standardized systems for monitoring labor, materials, procurement, safety, and project performance, enabling accurate reporting and proactive management.

Scope

This SOP applies to Project Managers, Field Supervisors, Purchasing, and Branch Managers for all awarded projects.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Establishes and maintains all tracking systems; ensures data is accurate and current. |
| Field Supervisor | Reports daily manpower, progress, and field conditions. |
| Purchasing | Updates procurement log with material and vendor status. |
| Safety Coordinator | Submits safety inspection reports and compliance updates. |
| Branch Manager | Reviews project reports to monitor health and performance. |

Required Documents and Tools

- Labor tracking sheets

- Procurement log

- RFI and Submittal logs

- Safety inspection forms

- Weekly dashboard (Smartsheet, Excel, or equivalent)

Procedure

Step 1: Set Up Tracking Systems

- Establish standardized templates for labor, procurement, RFIs, submittals, and safety.

Step 2: Assign Update Responsibilities

- Define who updates each log and set update frequencies.

Step 3: Monitor Progress

- Review weekly updates against the baseline schedule and labor budget.

Step 4: Generate Reports

- Create weekly dashboard summarizing key metrics.

- Distribute to Branch Manager and project stakeholders.

Step 5: Adjust Plans

- Use tracking data to identify risks early.

- Implement corrective actions as required.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Labor Tracking Report | Field Supervisor / PM | Project Folder |
| Procurement Log | Purchasing | Procurement Subfolder |
| Weekly Dashboard | Project Manager | Shared Folder |
| Safety Reports | Safety Coordinator | Safety Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Tracking systems implemented before mobilization | 100% |
| Weekly updates maintained throughout project | ≥95% |
| Branch Manager reviews reports weekly | 100% |

References

- GSL Pre-Construction Planning – Section 4.9 Tracking & Control

Appendix

- Labor Tracking Template

- Procurement Log Template

- Weekly Dashboard Example