SOP: 9.2.060 - Create Issue List and Begin RFI Process

Department: Project Management

Related SOPs:

9.2.040 - PM Reviews Plans, Specifications & Schedule

9.2.050 - FS Reviews Plans, Specifications & Schedule

9.4.205 - Manage RFIs (Requests for Information)

Purpose

To establish a standardized process for documenting project issues identified during pre-construction review and initiating the Request for Information (RFI) process. This ensures timely resolution of design conflicts, ambiguities, and missing information before they impact construction activities. The RFI folder is initiated during estimating by the Estimator and handed off to the project team at turnover.

Scope

- Applies to all projects / situations where:

| SOP | Role / Title 1 | Role / Title 2 | Role / Title 3 | Role / Title 4 | Role / Title 5 | Role / Title 6 | Role / Title 7 | Role / Title 8 | Role / Title 9 | Role / Title 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| List Responsibility 1 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 2 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 3 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 4 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 5 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 6 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 7 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 8 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 9 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 10 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 11 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 12 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 13 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 14 |  |  |  |  |  |  |  |  |  |  |  |

Pre-construction reviews have identified issues requiring clarification

Contract document review by PM and Foreman is in progress

Design conflicts, errors, or ambiguities have been discovered

Scope clarification is needed from the design team

Roles & Responsibilities

Estimator

Initiates/creates the project RFI folder during estimating

Hands off the RFI folder to the project team at turnover

Project Manager

During contract document review, creates and maintains the RFI Issue List

Prioritizes issues and submits RFIs promptly to support planning

Maintains the RFI log and ensures filing in the project repository

Tracks RFI responses and follows up on overdue items

Assesses impact of responses on schedule/cost

Foreman

During contract document review, identifies constructability/field conflicts

Adds field issues to the RFI Issue List

Assists with clarifying and validating RFI questions with field perspective

Reviews RFI responses for field impact

General Superintendent

Validates issue priorities for major items

Reviews significant design clarifications

Requirements

Required inputs, tools, logs, templates, and references:

Contract documents (plans, specs, addenda)

Existing RFI folder (initiated during estimating)

RFI Issue List / RFI log template

Project document repository / project folder location

Contract RFI procedures and submission requirements

Design team contact information

Procedure

Step 1 - Confirm RFI Folder Exists (Estimator Handoff)

PM confirms the RFI folder exists from estimating. If missing, PM creates it immediately and notifies Estimator/Branch Manager. Verify folder location and access permissions are correct.

Step 2 - Build RFI Issue List During Contract Document Review

PM and Foreman review contract documents (plans, specs, addenda). Capture discrepancies, conflicts, missing info, and constructability issues in the RFI Issue List. Include drawing/spec references for each issue. Categorize by type and assign priority.

Step 3 - Prioritize and Draft RFIs

PM prioritizes issues affecting schedule, procurement, prefab, and layout/sequencing. Draft RFIs clearly with references and the exact clarification/decision needed. Use standard RFI format per contract requirements. Provide proposed solution if applicable.

Step 4 - Issue RFIs ASAP to Support Planning

PM submits RFIs as soon as possible (do not wait to bundle). Route through proper channels (GC if subcontractor). Log submission date and recipient. Track due dates and status. Escalate overdue items per project controls process.

Step 5 - File Responses and Update the Log

File RFIs, responses, and supporting exhibits in the RFI folder. Update the log with responses and impacts. Review responses for completeness. Assess impact on schedule/cost and initiate change process if needed. Distribute relevant answers to the team.

Appendix

Issue Log Template

Standard RFI Form

RFI Priority Matrix

Response Follow-up Checklist