SOP: 9.2.080 - Prepare Material Handling Plan

Department: Project Management / Field Operations

Related SOPs:

9.2.020 - Procurement of Large Feeder Wire

9.2.070 - Conduct Site Visit

9.2.100 - Prepare Layout & Sequencing Plan

Purpose

To establish a standardized process for developing a comprehensive material handling plan that addresses delivery, staging, storage, and distribution of materials throughout the project.

Scope

- Applies to all projects / situations where:

| SOP | Role / Title 1 | Role / Title 2 | Role / Title 3 | Role / Title 4 | Role / Title 5 | Role / Title 6 | Role / Title 7 | Role / Title 8 | Role / Title 9 | Role / Title 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| List Responsibility 1 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 2 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 3 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 4 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 5 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 6 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 7 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 8 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 9 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 10 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 11 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 12 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 13 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 14 |  |  |  |  |  |  |  |  |  |  |  |

Project site visit has been completed

Material lists and delivery schedules are available

Staging and laydown areas need to be planned

Coordination with other trades is required

Roles & Responsibilities

Project Manager

Coordinates development of material handling plan

Ensures plan aligns with project schedule

Communicates material delivery requirements to vendors

Foreman / Field Supervisor

Identifies field material handling requirements

Validates staging and storage locations

Plans material distribution to work areas

General Superintendent

Reviews and approves material handling plan

Coordinates equipment and resource needs

Requirements

Required inputs, tools, logs, templates, and references:

Site visit findings and documentation

Project plans and material lists

Delivery schedules and lead times

Site logistics plan from GC (if applicable)

Procedure

Step 1 - Identify Material Categories and Quantities

Review project material lists. Categorize materials by size, weight, and handling requirements. Identify long-lead items requiring early coordination.

Step 2 - Assess Site Logistics

Review site visit documentation. Identify delivery access points and restrictions. Determine staging and laydown areas. Assess storage requirements.

Step 3 - Develop Delivery Schedule

Coordinate deliveries with project schedule. Sequence deliveries to avoid congestion. Plan for just-in-time delivery where feasible.

Step 4 - Plan Material Distribution

Map material flow from receiving to installation areas. Identify equipment needs (forklifts, carts, etc.). Plan vertical distribution for multi-story projects.

Step 5 - Document and Communicate Plan

Complete material handling plan document. Distribute to project team and subcontractors. Update as project conditions change.

Appendix

Material Handling Plan Template

Delivery Schedule Template