SOP: 9.2.090 - Develop Labor Budget

Department: Project Management

Related SOPs:

9.2.080 - Prepare Material Handling Plan

9.2.110 - Develop Project Schedule

Purpose

To establish a standardized process for developing an accurate labor budget that supports project planning, resource allocation, and cost control.

Scope

Applies to all projects / situations where:

| SOP | Role / Title 1 | Role / Title 2 | Role / Title 3 | Role / Title 4 | Role / Title 5 | Role / Title 6 | Role / Title 7 | Role / Title 8 | Role / Title 9 | Role / Title 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| List Responsibility 1 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 2 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 3 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 4 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 5 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 6 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 7 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 8 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 9 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 10 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 11 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 12 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 13 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 14 |  |  |  |  |  |  |  |  |  |  |  |

Project estimate with labor hours is available

Material handling plan has been developed

Resource planning is required for scheduling

Cost control baseline needs to be established

Roles & Responsibilities

Project Manager

Develops and maintains labor budget

Validates labor hours against estimate

Monitors labor budget throughout project

General Superintendent

Reviews labor budget for accuracy

Validates productivity assumptions

Supports resource planning

Estimator

Provides estimate labor hours and assumptions

Clarifies scope and productivity factors

Requirements

Required inputs, tools, logs, templates, and references:

Project estimate with labor hours by phase/system

Material handling plan (9.2.080)

Historical productivity data

Project schedule milestones

Procedure

Step 1 - Review Estimate Labor Hours

Obtain labor hour breakdown from estimating. Review productivity assumptions. Identify any scope changes since estimate.

Step 2 - Validate Labor Quantities

Compare estimate quantities to takeoff. Adjust for field conditions identified in site visit. Factor in project-specific complexities.

Step 3 - Develop Phased Labor Budget

Allocate labor hours to schedule phases. Plan labor loading by week/month. Identify peak manpower requirements.

Step 4 - Establish Tracking Metrics

Set up labor tracking codes. Define reporting requirements. Establish productivity targets.

Step 5 - Review and Approve

Present labor budget to management. Incorporate feedback and adjustments. Finalize and distribute to project team.

Appendix

Labor Budget Template

Manpower Loading Chart Template