SOP: 9.2.110 - Develop Project Schedule

Department: Project Management

Related SOPs:

9.2.090 - Develop Labor Budget

9.2.100 - Prepare Layout & Sequencing Plan

Purpose

To establish a standardized process for developing a comprehensive project schedule that supports planning, resource allocation, and progress monitoring.

Scope

Applies to all projects / situations where:

| SOP | Role / Title 1 | Role / Title 2 | Role / Title 3 | Role / Title 4 | Role / Title 5 | Role / Title 6 | Role / Title 7 | Role / Title 8 | Role / Title 9 | Role / Title 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| List Responsibility 1 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 2 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 3 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 4 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 5 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 6 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 7 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 8 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 9 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 10 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 11 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 12 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 13 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 14 |  |  |  |  |  |  |  |  |  |  |  |

Labor budget and layout/sequencing plan are complete

GC master schedule is available

Contract milestones have been identified

Resource loading is required

Roles & Responsibilities

Project Manager

Develops and maintains project schedule

Coordinates schedule with GC master schedule

Monitors and updates schedule throughout project

Foreman / Field Supervisor

Provides input on activity durations

Validates installation sequences

Reports progress for schedule updates

General Superintendent

Reviews and approves project schedule

Validates resource loading

Supports schedule conflict resolution

Requirements

Required inputs, tools, logs, templates, and references:

GC master schedule

Labor budget (9.2.090)

Layout and sequencing plan (9.2.100)

Material delivery schedules

Contract milestones and deadlines

Procedure

Step 1 - Obtain and Review GC Schedule

Request GC master schedule. Identify milestone dates and constraints. Note coordination requirements.

Step 2 - Develop Activity List

Break project into schedulable activities. Define activity durations based on labor budget. Identify dependencies and constraints.

Step 3 - Build Schedule Logic

Establish predecessor/successor relationships. Apply resource loading and leveling. Identify critical path.

Step 4 - Align with Master Schedule

Coordinate milestones with GC schedule. Resolve conflicts and constraints. Validate overall duration.

Step 5 - Review and Baseline

Review schedule with project team. Incorporate feedback and adjustments. Establish baseline and distribute.

Appendix

Project Schedule Template

Milestone Checklist