SOP: 9.2.120 - Establish Tracking & Control Systems

Department: Project Management

Related SOPs:

9.2.110 - Develop Project Schedule

9.2.130 - Construction Execution Kickoff Meeting

9.2.140 - Develop Project Budget

Purpose

To establish the project's tracking and control systems early so cost, schedule, labor, procurement, RFIs/submittals, and change management can be monitored and controlled throughout project execution.

Scope

- Applies to all projects / situations where:

| SOP | Role / Title 1 | Role / Title 2 | Role / Title 3 | Role / Title 4 | Role / Title 5 | Role / Title 6 | Role / Title 7 | Role / Title 8 | Role / Title 9 | Role / Title 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| List Responsibility 1 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 2 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 3 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 4 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 5 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 6 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 7 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 8 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 9 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 10 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 11 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 12 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 13 |  |  |  |  |  |  |  |  |  |  |  |
| List Responsibility 14 |  |  |  |  |  |  |  |  |  |  |  |

Project has been awarded (LOI/NTP received)

Budget and schedule baselines are being established

Project controls need to be set up before kickoff

Reporting cadence needs to be defined

Roles & Responsibilities

Project Manager

Establishes project controls structure (cost codes, reporting, logs, filing)

Ensures systems are maintained and used consistently

Defines update frequency and responsible parties

Communicates expectations to the team

Project Engineer / Project Coordinator

Maintains logs (RFI, submittal, issue)

Supports document control

Updates trackers and reports

General Superintendent / Field Leadership

Provides field inputs for labor productivity tracking

Contributes to lookaheads and progress reporting

Reports on schedule progress and constraints

Branch Manager

Confirms required controls are in place

Supports escalation and resource needs

Requirements

Required inputs, tools, logs, templates, and references:

Project budget and cost codes (from 9.2.140)

Baseline project schedule (from 9.2.110)

Project folder / document repository structure

Standard logs/templates (RFI, submittal, issue, change, procurement logs)

Reporting cadence expectations

Procedure

Step 1 - Establish Project File Structure and Access

Confirm project repository/folder structure is created and permissions assigned. Define where controls/logs will live (single source of truth). Set up standard folder hierarchy per company standards.

Step 2 - Set Up Cost Tracking and Reporting Cadence

Confirm budget, cost codes, and cost reporting format. Define update frequency (e.g., weekly cost review) and responsible parties. Establish cost-to-complete and forecast procedures.

Step 3 - Set Up Schedule Tracking

Confirm baseline schedule is loaded/accessible. Define schedule update cadence and required inputs. Establish lookahead schedule process.

Step 4 - Set Up Core Logs and Trackers

Create/confirm: RFI log, submittal log, issue list, procurement log, change log. Assign owners for each log and define minimum required fields. Set up safety items tracker if used.

Step 5 - Establish Labor/Productivity Tracking Method

Define how labor hours, production quantities, and productivity will be tracked. Align with field reporting and superintendent inputs. Set up earned value or unit tracking as applicable.

Step 6 - Implement Controls and Communicate Expectations

Communicate the systems, cadence, and responsibilities to the project team. Confirm controls will be reviewed during kickoff (9.2.130). Document expectations and maintain through execution.

Appendix

RFI Log Template

Submittal Log Template

Issue Log Template

Change Log Template

Procurement Log Template

Weekly Cost Report Template