GSL ELECTRIC

Standard Operating Procedure (SOP)
Title: Procurement of Large Feeder Wire for Projects
Department: Operations / Purchasing
Effective Date: [Insert Date]
Approved By: [Insert Approving Authority]
Reviewed By: [Insert Reviewer Name]
Version: 1.1

1. PURPOSE

To define the standardized process for the planning, procurement, and delivery of large feeder wire to ensure that project cost, schedule, and quality targets are achieved in accordance with GSL Electric’s Management Directives.

2. SCOPE

This SOP applies to Project Managers, Foremen, Purchasing Department personnel, and any other staff involved in the planning and acquisition of electrical feeder wire for GSL projects.

3. ROLES AND RESPONSIBILITIES

| Role | Responsibility |
| --- | --- |
| Project Manager (PM) | Leads pre-planning, prepares bill of materials, issues PO, coordinates purchasing with vendors, and tracks delivery. |
| Foreman / Field Leadership | Supports material take-off and validates wire requirements based on installation layout and staging. |
| Purchasing Assistant / Department | Assists in issuing PO, ensures compliance with terms, logs PO, and tracks submittals. |

4. PROCEDURE

4.1 Pre-Planning and Take-Off

- PM and Foreman review project drawings and staging plans.

- Conduct a comprehensive take-off of large feeder wire, incorporating:

  - Value engineering strategies.

  - Routing alternatives (e.g., duct banks, conduit racks).

  - Pre-fabrication opportunities.

Priority 1: Secure Pricing Early

- Order large wire early in the project to minimize pricing risk and ensure wire costs are consistent with bid estimates.

- Delays in ordering may lead to increased costs due to market volatility or escalation of cost.

Priority 2: Validate Wire Lengths

- True tape conduit runs to verify wire lengths whenever feasible.

  - If that is not possible, rely on scaled drawings and planned routing.

  - Always document measurement sources and assumptions.

Preferred Option:

Minimizing Waste Through Wire Put-Ups and Pull Sequence Coordination

To reduce waste and potential reorders, coordinate wire cuts based on grouped pulls of the same type and size. Use the following logic:

Example Strategy:

- Pull A = 300 ft

- Pull B = 50 ft

- Pull G = 250 ft

- All use the same size and type of wire.

- Recommended Put-Up: Secure 600-ft reels for each conductor.

- Pull Sequence: Pull A and G first. Pull B last.

Rationale:

- If Pull A or G is slightly longer than expected, the shorter Pull B will be the one to fall short requiring only a small reorder.

- If the short pull is done first and a long pull is short, the cost impact is greater and will require a large re-purchase of wire.

- Prepare a Conduit / Wire Pull Schedule indicating the specific pulls committed to each reel.

- Prepare a Bill of Materials (BOM) detailing all wire types, sizes, estimated lengths, and accessories (e.g., terminations, labeling).

4.2 Vendor Engagement

- Contact vendors that supported bid-day pricing.

- Confirm:

  - Unit pricing

  - Freight terms

  - Sales tax applicability

  - Escalation risks

  - Put ups and storage impacts (if any)

- Document pricing duration and availability terms within the PO.

4.3 Purchase Order (PO) Creation

- Prepare PO with:

  - Itemized quantities and specifications

  - Jobsite delivery location and required delivery dates

  - Submittal requirements (see Section 4.4)

  - Freight and tax details

  - Verification that total cost aligns with the project budget

4.4 Submittal Process

- Identify submittal requirements per project specifications.

- Provide vendor with specification section(s) related to wire.

- Do not release materials for manufacture or delivery until submittals are approved.

4.5 Delivery and Inventory Control

- Schedule delivery to the designated jobsite Conex or staging area.

- We prefer not to have the wire on site until we are ready to install it, to minimize the risk of theft.

- Upon receipt, the Foreman must confirm:

  - Delivery is accurate and complete.

  - Material is undamaged.

  - Quantities match the PO.

- Implement tracking to monitor usage and facilitate returns of unused wire.

4.6 Change Control

- All deviations, such as alternate wire specifications or routing changes, must:

  - Be authorized by the PM.

  - Be reviewed with the PM if cost or scope is affected.

  - Be approved in writing by the contracting party.

5. COMPLIANCE & ACCOUNTABILITY

- All personnel must follow this SOP and associated directives.

- Any exception requires approval from Branch Management.

6. DOCUMENTATION REQUIREMENTS

- PO and vendor correspondence filed in the project folder (digital and/or physical).

- Delivery receipts and submittals documented.

7. RELATED POLICIES & DIRECTIVES

- Management Directives for Purchasing

- Project Management Procedures

- Field Leadership Requirements

- Submittal Procedures and Documentation Standards

Document Owner: [Insert Name]
Next Review Date: [Insert Review Cycle]