## Sheet1
1 - Project Turnover Meeting
Items to Review |  | Notes | Action Plan | Responsible Party | Status | Due Date |  | Notes
a. Narrative Description of the Project: | Review Complete | Estimator to Carefully and in Detail Describe the project - "Paint the Picture" | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Overall Description of Project and Estimate
b. Contract Status: | Review Complete | Review Project Contract Status and Note and Issues and if Necessary Develop Plan to Deal with Issues | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Notice to Proceed Received?
Contract Received?
Contract Reviewed?
Contract Signed?
Who Will Out Contract Be With?
Contract Problems, Issues, Concerns?
*List Issues Here
c. Form of Contract: | Check One | Make Any Notes Needed Below | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Custom
AIA
AGC
ASA
d. Type of Contract: | Check One | Make Any Notes Needed Below | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Lump-Sum
T&M
GMP
Other
e. Type of Project: | Check One | Make Any Notes Needed Below | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Plan-Spec
Design Build
Design Assist
Other
f. Contract Allowances: | Review Complete | List Any Allowances from Bid that are Included in Contract | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Allowances Here
*List Allowances Here
*List Allowances Here
*List Allowances Here
*List Allowances Here
g. Permits Needed: | Review Complete | Make Any Notes Needed Below | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Permits Needed Here (A)
*List Permits Needed Here (B)
*List Permits Needed Here (C)
*List Permits Needed Here (D)
*List Permits Needed Here (E)
h. Plans & Specs: | Review Complete | Make Any Notes Needed Below | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Do We Have Most Current Set of Plans/Specs?
Errors/Omissions in Plans and Specs?
*List Known Errors/Omissions Here
i. Addenda: | Review Complete | Make Any Notes Needed Below | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Addenda #'s Received To Date:
Which Addenda Afffect Our Work:
Last Addendum Received Prior to Bid Date:
Addenda Received After Bid Date:
j. Bid Alternates: | Review Complete | List All Alternates Submitted with Bid | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Alternates Here
*List Alternates Here
*List Alternates Here
*List Alternates Here
*List Alternates Here
k. Bid Proposal/Scope Letter: | Review Complete | In Detail, Review Proposal Letter for all Inclusions, Exclusions and Clarifications | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*Proposal Letter Issues/Items to Note
*Proposal Letter Issues/Items to Note
*Proposal Letter Issues/Items to Note
*Proposal Letter Issues/Items to Note
*Proposal Letter Issues/Items to Note
l. Low Voltage Systems & Fire Alarm: | Review Complete | Discuss in Detail our Scope Pertaining to all Systems and Fire Alarm Scope | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Fire Alarm Scope of Work:
*List LV Systems Scope Here
*List LV Systems Scope Here
*List LV Systems Scope Here
*List LV Systems Scope Here
*List LV Systems Scope Here
*List LV Systems Scope Here
*List LV Systems Scope Here
*List LV Systems Scope Here
m. Known Estimate Errors and Omissions: | Review Complete | Identify All Errors, Omissions and Problems with the Estimate | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Issues Here
*List Issues Here
*List Issues Here
*List Issues Here
*List Issues Here
n. Estimating Strategies: | Review Complete | Review Planned Construction Practices/Strategies and Materials Used in Estimate | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Notes Here:
*List Notes Here:
*List Notes Here:
*List Notes Here:
*List Notes Here:
o. Cost Saving Opportunities: | Review Complete | Identify Opportunities to Increase Productivity & Profitability. Evaluate and Identify Pre-Fab Opportunities | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Notes Here:
*List Notes Here:
*List Notes Here:
*List Notes Here:
*List Notes Here:
p. Project Labor: | Review Complete | Make Any Notes Needed Below | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Prevailing Wage Rates Required?
Identify Any Labor Factoring Used In Estimate:
*List Labor Factoring Used:
*List Labor Factoring Used:
*List Labor Factoring Used:
Total Man-Hours In Estimate:
Total Project Duration:
Estimated Avg. Crew Size: |  | (A)
Estimated Avg. Crew Configuration: |  | (B)
Estimated Peak Crew Configuration: |  | (C)
Overtime or Shiftwork:
Other Special Labor Issues or Concerns:
List of Labor Concerns or Issues
*List Labor Issues Here:
*List Labor Issues Here:
*List Labor Issues Here:
*List Labor Issues Here:
*List Labor Issues Here:
LV Systems Labor
*List LV Labor Issues Here:
*List LV Labor Issues Here:
*List LV Labor Issues Here:
*List LV Labor Issues Here:
*List LV Labor Issues Here:
q. Subcontractors: | Review Complete | List All Subcontractors by Trade. Discuss Scope of Work. Attach Copy of Quotes as Needed | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Subcontractors Here (A):
*List Subcontractors Here (B):
*List Subcontractors Here (C):
*List Subcontractors Here (D):
*List Subcontractors Here (E):
*List Subcontractors Here (F):
*List Subcontractors Here (G):
*List Subcontractors Here (H):
*List of Sub Issues/Concerns:
*List Subcontractors Issues Here:
*List Subcontractors Issues Here:
*List Subcontractors Issues Here:
*List Subcontractors Issues Here:
*List Subcontractors Issues Here:
*List Subcontractors Issues Here:
*List Subcontractors Issues Here:
*List Subcontractors Issues Here:
r. Quoted Material and Vendors: | Review Complete | List of All Quoted Materials and Vendors Used and Attach Copy of Quotes as Needed | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
List Quoted Material Here:
List Vendor Used:
Lead Time:
Expedited Delivery Needed?
List Quoted Material Here:
List Vendor Used:
Lead Time:
Expedited Delivery Needed?
List Quoted Material Here:
List Vendor Used:
Lead Time:
Expedited Delivery Needed?
List Quoted Material Here:
List Vendor Used:
Lead Time:
Expedited Delivery Needed?
List Quoted Material Here:
List Vendor Used:
Lead Time:
Expedited Delivery Needed?
List Quoted Material Here:
List Vendor Used:
Lead Time:
Expedited Delivery Needed?
List Quoted Material Here:
List Vendor Used:
Lead Time:
Expedited Delivery Needed?
List of Quoted Material Issues/Concerns:
*List Quoted Material Issues Here
*List Quoted Material Issues Here
*List Quoted Material Issues Here
*List Quoted Material Issues Here
*List Quoted Material Issues Here
*List Quoted Material Issues Here
*List Quoted Material Issues Here
s. Project Schedule: | Review Complete | Make Any Notes Needed Below | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Start Date:
Completion Date:
Liquidated Damages:
Early Completion Incentives:
Project Milestone Dates:
*List Milestone Dates Here
*List Milestone Dates Here
*List Milestone Dates Here
*List Milestone Dates Here
*List Milestone Dates Here
Review or Create Rough Project Schedule:
Are We Required to Submit Our Schedule?
Plan and Date to Submit Our Schedule?
t. Pre-Fab Opportunities: | Review Complete | Make Any Notes Needed Below | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Items Estimated as Pre-Fabricated:
*List Items Here:
*List Items Here:
*List Items Here:
*List Items Here:
*List Items Here:
Items That Cannot be Pre-Fabricated:
*List Items Here:
*List Items Here:
*List Items Here:
*List Items Here:
*List Items Here:
Items Identified or to be Evaluated for Pre-Fabrication:
*List Items Here:
*List Items Here:
*List Items Here:
*List Items Here:
*List Items Here:
u. Safety: | Review Complete | Make Note of Any Project Specific Safety Concerns or Requirements | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
Drug Testing:
Background Checks:
Asbestos:
Hazardous Material:
Project Specific Safety Issues:
*List Safety Issues Here (A):
*List Safety Issues Here (B):
*List Safety Issues Here (C):
*List Safety Issues Here (D):
*List Safety Issues Here (E):
Project Specific Safety Training:
*List Safety Training Here (A):
*List Safety Training Here (B):
*List Safety Training Here (C):
*List Safety Training Here (D):
*List Safety Training Here (E):
v. Tool Requirements: | Review Complete | Make List of Any Project Specific Tool Requirements | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Tools Here (A):
*List Tools Here (B):
*List Tools Here (C):
*List Tools Here (D):
*List Tools Here (E):
w. Equipment Requirements: | Review Complete | Make List of Any Project Specific Equipment Requirements | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Equipment Here (A):
*List Equipment Here (B):
*List Equipment Here (C):
*List Equipment Here (D):
*List Equipment Here (E):
x. Testing Requirements: | Review Complete | Make List of Any Project Specific Testing Requirements | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Test Requirements Here:
*List Test Requirements Here:
*List Test Requirements Here:
*List Test Requirements Here:
*List Test Requirements Here:
y. Misc/Other: | Review Complete | Make Note of All Project Specific Requirements or Issues | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Misc/Other Requirements Here:
*List Misc/Other Requirements Here:
*List Misc/Other Requirements Here:
*List Misc/Other Requirements Here:
*List Misc/Other Requirements Here:
z. Project Risks, Opportunities, etc: | Review Complete | Make Note of All Project Specific Risks and/or Opportunities | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
*List Risk/Opportunity Here:
*List Risk/Opportunity Here:
*List Risk/Opportunity Here:
*List Risk/Opportunity Here:
*List Risk/Opportunity Here:
aa. Project Close-Out Requirements: | Review Complete | Make Note of All Project Specific Risks and/or Opportunities | List Action Items Below | Responsible Party | Status | Due Date | Pre-Fab Opportunity | Notes
As-Builts:
O&M's:
Punch List:
Warranty Letters:
Turnover to Service Dept:
*List Other Requirements Here:
*List Other Requirements Here:
*List Other Requirements Here: