SOP 9.055.190 – Procurement of Large Feeder Wire

Department: Project Management / Purchasing
Created by: Tom Ewing
Effective Date: [Insert Date] Version: 1.0
Related SOPs: SOP 9.056.190 – Release of Large Feeder Wire; SOP 9.057.190 – Feeder Wire Procurement & Release Log; GSL Wire Release Conditions

1. Overview

This SOP defines the process for procuring and releasing large feeder wire to ensure timely pricing lock, submittal preparation, coordination with vendors, and Just-In-Time (JIT) delivery. It also outlines GSL’s release conditions to minimize waste, ensure usable spool lengths, and align procurement with project schedules.

2. Scope

This procedure applies to all projects requiring feeder wire (typically #1 AWG and larger), both for temporary and permanent installations. It is intended for Project Managers (PMs), Assistant Project Managers (APMs), Project Coordinators (PCs), Purchasing staff, and Field Leadership.

3. Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager (PM) | Confirms feeder quantities and schedule with the PE/APM or Project Coordinator. Approves final procurement decisions. |
| Assistant Project Manager (APM) / Project Coordinator | Verifies feeder sizes and lengths from drawings, validates quantities, and prepares submittals. |
| Purchasing / Buyer | Issues RFQs, compares vendor quotes, reviews vendor history, confirms terms, and places purchase orders. |
| Field Leadership | Confirms spool sizes and provides delivery timing preferences. |

4. Requirements

- Cable sizes, types, and footage are required at the estimating stage.

- Preplanning takeoff lengths with BIM modeling (if available) may be used later to verify conduit paths, but are not required for procurement.

- Required documents and tools include:

  - Large Wire / Cable BOM Form

  - Approved submittals (verify wire sizes against approved gear)

  - Feeder schedule or riser diagram

  - Project schedule

  - RFQ template and vendor contact list

  - Delivery tracking spreadsheet

5. Process

Step 1 – Feeder Procurement & Release Log populated

Upon Notice of Award or Letter of Intent, the PM exports feeder information from the Accubid file and loads it into the Feeder Wire Procurement & Release Log (see SOP 9.057.190).

- PM, APM/PC, and Foreman confirm:

  - Submittal requirements

  - Feeder size, quantity, and length

  - Conductor Material (CU, AL)

  - Color coding, labeling, and insulation type (if applicable)

Step 2 – 2+ vendor quotes documented and archived

Purchasing issues RFQs including details such as wire type/size, quantity, delivery terms, reel specifications, freight, taxes, and reel return policy.

- RFQ response time: 2–3 business days

- Vendors must acknowledge and agree to GSL Wire Release Conditions.

Step 3 – PO with pricing lock and lead times

PM reviews quotes and selects vendors based on best value.  Including: price per foot, availability, lead time, spool sizes, approved manufacturers, and vendor performance.

- PM signs off on selected quote; Purchasing issues purchase order.

- Billed upon release, not procurement

Step 4 – Submittal Preparation

- PM/APM/PC assembles the submittal package per project specifications.

- No wire releases may occur until submittals are approved.

Step 5 – Pre-Planning with Field Supervision

- PM collaborates with Field Supervision to define site logistics, routing, material handling, and installation timelines.

- BOM and Conduit/Wire Pull Schedule are prepared using scaled drawings.

Step 6 – Storage and Release Conditions

- Vendors must store all procured wire at their warehouse until GSL issues a release notice.

- Submittal approval before release: mandatory

- Upon release, vendors cut and bundle feeders onto single spools (or coils for short runs), including:

  - Colored phase and neutral conductors

  - Ground conductor (spooled separately if size differs)

- Vendors should use standard inventory stock when possible to minimize waste and ensure usable lengths.

- Vendors are expected to manage spool usage responsibly, ensuring practical lengths are available for releases.

- Wire and cable are billed to GSL upon release, not upon initial procurement.

Appendix:

- Feeder Wire Procurement & Release Log1.xlsx