SOP 9.020.41 – PM Reviews Plans, Specs & Schedule

Department: Project Management / Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs:

- 9.010.41 – Project Turnover Meeting

- 9.030.41 – PM Creates Draft Schedule
Reference: GSL Pre-Construction Planning Process

Purpose

To ensure that the Project Manager thoroughly reviews all contract documents to identify scope issues, technical requirements, and coordination risks prior to procurement, prefab planning, or field mobilization.

Scope

Applies to all awarded projects after the project turnover meeting and before initial submittals or vendor buyout begins.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Conducts detailed review of drawings and specifications. Documents findings and open issues. |
| Project Engineer | Assists in markups, spec interpretations, and comparison to estimate scope. |
| Estimator | Provides clarification on bid assumptions or scope decisions. |
| Prefab Lead | Coordinates early identification of prefab opportunities. |
| Safety Coordinator | Reviews drawings for hazards or risks requiring mitigation. |

Required Documents and Tools

- Contract Drawings

- Project Specifications

- Estimate / Bid Package

- Project Turnover Notes

- Scope Matrix Template (if available)

Procedure

Step 1: Assemble Project Documents

- The PM collects the latest set of IFC (Issued for Construction) drawings, specifications, and bid clarifications.

- All documents are saved in the appropriate project folder or document management system.

Step 2: Conduct Drawing Review

- The PM and PE mark up key drawing sets, noting:

  - Major equipment and layout references

  - Riser diagrams, load centers, switchgear

  - Fire alarm, lighting, and life-safety overlaps

  - Coordination needs with other trades

- Prefab lead reviews for opportunities in feeders, branch racks, or panel assemblies.

Step 3: Conduct Specification Review

- PM reviews Division 01 and electrical spec sections (typically Division 26).

- Look for:

  - Submittal requirements and deadlines

  - Required manufacturers and substitutions

  - Testing, startup, and warranty obligations

  - Temporary power or safety provisions

Step 4: Compare Plans vs. Estimate

- PM compares estimate inclusions/exclusions against drawings/specs.

- Escalate discrepancies (scope gaps, missing materials) to Estimator and Branch Manager for resolution.

Step 5: Document Findings

- PM logs all questions, risks, and discrepancies in a tracking log.

- Issues needing RFIs or clarification are flagged for resolution.

- Risk items are discussed in next planning/scheduling meeting.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Marked-Up Drawings (PDF or hardcopy) | Project Manager | Project Folder |
| Specification Summary Notes | Project Manager | Shared Technical Review |
| Scope Comparison Log | PM / Estimator | Estimating Review Folder |
| RFI Draft List | Project Engineer | RFI Tracker |

Compliance & Review

| KPI | Target |
| --- | --- |
| Plans/specs reviewed within 3 business days of turnover | 100% |
| All issues logged and tracked | 100% |
| Estimating scope validated against construction docs | 100% |

References

- Estimating to Operations Handoff Documents

- Award Clarification Sheet

- Scope Matrix (if used)

Appendix

- Drawing Review Checklist

- Sample Scope Validation Log

- Markup & Note-Taking Legend