SOP: 9.2.055 - Compare Estimated vs. Planned Performance

Department: Project Management / Estimating

Related SOPs:

- 9.2.015 - Project Turnover Meeting

- 9.2.090 - Develop Labor Budget

- 9.2.140 - Develop Project Budget

============================================================

PURPOSE

============================================================

To establish a standardized process for comparing estimated bid values against planned project performance, identifying variances and adjusting expectations before construction begins.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Project has been awarded

- Estimate turnover has occurred

- Labor budget development is underway

- Baseline planning requires validation

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Leads comparison analysis; Documents variances; Develops mitigation plans |

| Estimator (C) | Explains bid assumptions; Clarifies estimate breakdowns; Validates productivity targets |

| General Superintendent (C) | Validates field labor assumptions; Confirms crew productivity expectations |

| Branch Manager (I) | Informed of significant variances; Approves risk mitigation plans |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Original bid estimate and labor summary

- Bid assumptions and qualifications

- Planned labor budget (SOP 9.2.090)

- Project schedule

- Productivity targets by system/phase

- Historical project performance data

============================================================

PROCEDURE

============================================================

STEP 1 - Obtain Estimate Breakdown

--------------------------------------

PM obtains from Estimator:

- Detailed labor hours by system/phase

- Material pricing assumptions

- Productivity rates used

- Bid qualifications and exclusions

- Risk contingencies included

- Value engineering assumptions

STEP 2 - Compare Labor Hours

--------------------------------------

Compare estimated vs. planned labor:

- By system (lighting, power, fire alarm, etc.)

- By phase (underground, rough, trim)

- By area or floor

- Identify significant variances (>10%)

STEP 3 - Analyze Variances

--------------------------------------

For each significant variance, determine:

- Root cause of difference

- Is estimate or plan more accurate?

- Impact on project profitability

- Required corrective action

STEP 4 - Validate Assumptions

--------------------------------------

Review key assumptions with team:

- Productivity targets achievable?

- Prefab plan incorporated correctly?

- Crew sizes appropriate?

- Schedule allows adequate time?

- Material quantities accurate?

STEP 5 - Document Comparison Results

--------------------------------------

Create comparison report showing:

- Line-by-line estimate vs. plan

- Variance analysis and explanations

- Risk areas identified

- Mitigation strategies proposed

- Revised profit projection

STEP 6 - Communicate and Adjust

--------------------------------------

Share findings with team:

- Present at planning meetings

- Adjust labor budget if needed

- Update schedule if required

- Inform Branch Manager of significant risks

- Establish tracking baseline

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| Comparison completed before kickoff | 100% |

| Variances >10% analyzed and documented | 100% |

| Mitigation plans developed for risks | 100% |

| Branch Manager informed of significant variances | 100% |

============================================================

APPENDIX

============================================================

- Estimate vs. Plan Comparison Template

- Variance Analysis Worksheet

- Historical Productivity Database

- Risk Mitigation Plan Template

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.040 â€“ Compare Estimated vs. Planned

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee