SOP 9.090.41 – Prefab Plan Created

Department: Project Management / Prefabrication
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs:

- 9.080.41 – Initial Submittals Created and Sent

- 9.100.41 – Initial Coordination Drawings Started
Reference: GSL Pre-Construction Planning Process

Purpose

To define the process for identifying, developing, and documenting the project’s prefabrication strategy, allowing for improved planning, efficiency, and field execution through the use of off-site construction.

Scope

Applies to all projects with opportunities for prefabricated assemblies or materials. Involves coordination between the PM, Prefab Lead, GS, Estimator, and Design Team.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Prefab Lead | Leads development of the prefab plan. Coordinates scope, sequencing, and delivery logistics. |
| Project Manager | Supports prefab planning and ensures alignment with schedule and submittals. |
| General Superintendent | Validates site readiness and receiving capabilities. |
| Estimator | Confirms prefab elements included in the bid and identifies VE opportunities. |
| Project Engineer | Assists with documentation and submittal dependencies. |

Required Documents and Tools

- Project drawings and specifications

- Prefab scope summary from estimator (if available)

- Prefab Planning Template

- Initial submittals and vendor lead times

- Field logistics layout and receiving plan

Procedure

Step 1: Identify Prefab Opportunities

- Prefab Lead reviews:

  - Riser diagrams

  - Conduit routing

  - Panelboard, lighting, feeder configurations

  - Typical branch devices

- Estimate or bid package reviewed for included prefab scope

Step 2: Conduct Prefab Planning Session

- PM schedules internal meeting including:

  - Prefab Lead

  - PM and PE

  - General Superintendent

  - Estimator (as needed)

- Discuss:

  - What assemblies can be prefabbed

  - Delivery strategy and schedule impacts

  - Submittal dependencies and approval timelines

Step 3: Draft Prefab Plan

- Prefab Lead completes Prefab Planning Template including:

  - Scope and quantity of prefabricated items

  - Material sources and BOMs

  - Assembly timeline and location (shop or field)

  - Delivery logistics and staging on site

Step 4: Align with Schedule and Submittals

- PM confirms all items required for prefab are submitted/approved

- Schedule is reviewed to ensure prefab activities support project milestones

- Long-lead items are flagged in procurement log

Step 5: Finalize and Distribute

- Final Prefab Plan is reviewed and approved by PM and GS

- Uploaded to project folder

- Summary shared with field foreman and procurement team

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Prefab Plan | Prefab Lead | Prefab Coordination Folder |
| Prefab BOM / Cut Sheets | Project Engineer | Submittals / Procurement Docs |
| Prefab Planning Meeting Notes | PM / Prefab Lead | Project Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Prefab plan developed before mobilization | 100% |
| All prefab assemblies identified and documented | 100% |
| Prefab aligned with submittals and delivery schedule | 100% |

References

- Estimating Prefab Scope Summary

- GSL Prefab Planning Template

- Procurement & Submittal Logs

Appendix

- Prefab Plan Template (fillable)

- Prefab Opportunity Checklist

- Sample Prefab BOM & Delivery Tracker