SOP: 9.2.060 - Create List of Issues and Begin RFI Process

Department: Project Management

Related SOPs:

- 9.2.040 - PM Reviews Plans, Specifications & Schedule

- 9.2.050 - FS Reviews Plans, Specifications & Schedule

- 9.4.205 - Manage RFIs (Requests for Information)

============================================================

PURPOSE

============================================================

To establish a standardized process for documenting project issues identified during pre-construction review and initiating the Request for Information (RFI) process to resolve them before construction begins.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Pre-construction reviews have identified issues

- Clarification is needed from design team

- Design conflicts or errors have been discovered

- Scope ambiguities require resolution

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Manages overall issue resolution; Prioritizes RFIs; Tracks responses |

| Assistant PM/Project Coordinator (R) | Creates and submits RFIs; Maintains issue log; Follows up on responses |

| Field Supervisor (C) | Contributes constructability issues; Reviews RFI responses for field impact |

| General Superintendent (C) | Validates issue priorities; Reviews significant design clarifications |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Issue lists from PM and FS reviews

- RFI log template

- Contract RFI procedures

- Drawing and specification references

- Design team contact information

- RFI tracking system access

============================================================

PROCEDURE

============================================================

STEP 1 - Compile Issue Lists

--------------------------------------

Gather issues identified during reviews:

- PM plan/spec review issues

- FS constructability concerns

- Coordination conflicts

- Specification ambiguities

- Missing information

- Code compliance questions

STEP 2 - Categorize and Prioritize

--------------------------------------

Organize issues by:

- Category (design, coordination, scope, clarification)

- Priority (critical, high, medium, low)

- Timing (immediate, before mobilization, before phase)

- Responsible party for response

STEP 3 - Determine Resolution Method

--------------------------------------

For each issue, determine if it requires:

- Formal RFI submission

- Informal clarification

- Submittal clarification

- Coordination meeting

- No action (informational only)

STEP 4 - Create RFIs

--------------------------------------

For issues requiring formal RFI:

- Use standard RFI format

- Reference specific drawings/specs

- Clearly state the question

- Provide proposed solution if applicable

- Attach relevant sketches or photos

- Assign tracking number

STEP 5 - Submit and Track RFIs

--------------------------------------

Submit RFIs per contract requirements:

- Route through proper channels (GC if subcontractor)

- Log submission date and recipient

- Set expected response date

- Follow up on overdue responses

- Distribute responses to affected parties

STEP 6 - Incorporate Responses

--------------------------------------

When responses received:

- Review for completeness

- Assess impact on schedule/cost

- Initiate change process if scope affected

- Update drawings/plans as needed

- Communicate to field team

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| All review issues documented | 100% |

| RFIs submitted within 5 days of issue identification | 95% |

| RFI responses tracked and followed up | 100% |

| Critical RFIs resolved before affected work begins | 100% |

============================================================

APPENDIX

============================================================

- Issue Log Template

- Standard RFI Form

- RFI Priority Matrix

- Response Follow-up Checklist

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.030 â€“ Create Issue List & Begin RFI Process

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee