SOP: 9.2.070 - Conduct Site Visit

Department: Project Management / Field Operations

Related SOPs:

- 9.2.050 - FS Reviews Plans, Specifications & Schedule

- 9.2.080 - Prepare Material Handling Plan

- 9.3.010 - Setup Office Trailer

- 9.3.470 - Develop Site-Specific Safety Plan

============================================================

PURPOSE

============================================================

To establish a standardized process for conducting pre-construction site visits to assess existing conditions, identify logistical requirements, and validate planning assumptions before mobilization.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Project has been awarded

- Pre-construction planning is underway

- Site access is available for inspection

- Physical site assessment is needed

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Coordinates site visit; Documents findings; Integrates into project planning |

| Field Leadership (R) | Conducts physical site inspection; Identifies constructability and logistics issues |

| Safety Coordinator (R) | Assesses site safety conditions; Identifies hazards and requirements |

| General Superintendent (C) | Provides oversight; Validates logistics assumptions |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Site access authorization

- Personal protective equipment (PPE)

- Site visit checklist

- Camera/phone for documentation

- Measuring tools

- Project drawings for reference

- Safety assessment form

============================================================

PROCEDURE

============================================================

STEP 1 - Schedule Site Visit

--------------------------------------

PM coordinates with owner/GC for access:

- Confirm site access requirements

- Schedule appropriate attendees

- Obtain any required badges/permits

- Confirm PPE requirements

- Allow adequate time for thorough review

STEP 2 - Prepare for Visit

--------------------------------------

Before arriving on site:

- Review project drawings and specifications

- Prepare site visit checklist

- Identify specific areas to inspect

- Bring necessary equipment and PPE

- Review any existing as-built information

STEP 3 - Assess Site Logistics

--------------------------------------

Evaluate site conditions for:

- Office/trailer placement locations

- Material laydown and storage areas

- Equipment staging locations

- Parking availability

- Site access routes

- Delivery and unloading areas

- Temporary power availability

- Sanitary facilities locations

STEP 4 - Evaluate Existing Conditions

--------------------------------------

Document existing conditions:

- Existing electrical infrastructure

- Panel locations and routing paths

- Ceiling heights and access

- Structural conditions

- Coordination with other trades already on site

- As-built vs. drawing discrepancies

STEP 5 - Conduct Safety Assessment

--------------------------------------

Safety Coordinator evaluates:

- Site-specific hazards

- Fall protection requirements

- Confined space areas

- Overhead hazards

- Traffic and pedestrian patterns

- Emergency access and egress

- Environmental conditions

STEP 6 - Document and Communicate Findings

--------------------------------------

After site visit:

- Complete site visit report with photos

- Update material handling plan (SOP 9.2.080)

- Incorporate findings into PEP

- Distribute report to project team

- Update safety plan as needed (SOP 9.3.470)

- Identify any RFIs needed (SOP 9.2.060)

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| Site visit completed before mobilization | 100% |

| Site visit report documented with photos | 100% |

| Safety assessment completed | 100% |

| Findings incorporated into project planning | 100% |

============================================================

APPENDIX

============================================================

- Site Visit Checklist

- Site Safety Assessment Form

- Photo Documentation Guidelines

- Site Logistics Template

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.035 â€“ Conduct Site Visit

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee