SOP 9.070.41 – Prepare Layout & Sequencing Plan

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs:

- 9.065.41 – Develop Labor Budget

- 9.075.41 – Develop Project Schedule

Purpose

To establish a clear plan for installation layout and work sequencing that ensures productive field execution, optimal material flow, and minimal rework or congestion during installation.

Scope

Applies to all awarded projects. Must be completed before field mobilization and after completion of the labor budget and initial project schedule.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Leads development of the plan and integrates it with project logistics and schedule. |
| General Superintendent | Provides field input on work sequencing and layout feasibility. |
| Foreman / Field Lead | Reviews routing logic and confirms constructability. |
| Project Engineer | Supports layout diagram creation and notes detailed plan elements. |
| Safety Coordinator | Ensures sequence does not conflict with site access, lifts, or safety barriers. |

Required Documents and Tools

- Construction drawings and project schedule

- Labor budget

- Site logistics plan

- GSL Layout & Sequencing Plan Template

- Coordination or shop drawings

- Safety plan

Procedure

Step 1: Identify Critical Work Areas and Systems

- PM and GS identify high-impact areas:

  - Main corridors

  - Utility rooms

  - Equipment pads

  - Areas requiring sequencing with other trades

- Focus on systems like gear, feeders, lighting, and racks

Step 2: Establish Installation Sequence

- Define logical flow of installation for:

  - Conduit rough-in

  - Racks and prefab assemblies

  - Gear and switchboards

  - Lighting and devices

- Identify overlapping or concurrent trade work and plan around them

Step 3: Create Layout Diagrams

- PE or Field Foreman marks up floor plans with:

  - Routing paths

  - Mounting elevations

  - Equipment and box locations

  - Rack install zones and clearances

- Use coordination drawings as background if available

Step 4: Align with Schedule and Labor Plan

- PM aligns sequencing plan with labor curve

- Adjust field manpower levels to match phase complexity

- Sequence phases by area (e.g., Level 1 → Level 2 → Roof)

Step 5: Final Review and Distribution

- GS and Foreman review for install feasibility

- Safety Coordinator verifies clearances and lift access

- Final plan uploaded to project folder and shared with field team

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Layout & Sequencing Plan | Project Manager | Project Coordination Folder |
| Marked-Up Layout Sheets | PE / Field Lead | Coordination Folder |
| Safety Review Sign-Off | Safety Coordinator | Safety Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Plan complete before first rough-in or layout start | 100% |
| Layout approved by GS and Safety | 100% |
| Aligned with labor plan and installation flow | 100% |

References

- Project Schedule

- Labor Budget (SOP 9.065.41)

- Safety Plan & Lift Strategy

- Prefab Plan

Appendix

- Layout & Sequencing Template

- Sample Rack Routing Sheet

- Phased Floor Diagram Examples