SOP: 9.3.040 - Setup Temporary Power

Department: Field Operations

Related SOPs:

- 9.3.010 - Setup Office Trailer

- 9.3.070 - Setup Temporary Lighting

- 9.3.470 - Develop Site-Specific Safety Plan

============================================================

PURPOSE

============================================================

To establish a standardized process for installing temporary electrical power distribution, ensuring safe and adequate power for construction operations, trailers, and equipment.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Temporary construction power is required

- Power distribution to work areas is needed

- Trailers and equipment need electrical service

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Field Supervisor (A) | Oversees installation; Ensures code compliance |

| Foreman/Journeyman (R) | Installs temporary power system; Makes connections |

| Safety Coordinator (C) | Reviews safety requirements; Verifies GFCI protection |

| Project Manager (C) | Coordinates with utility company; Approves power plan |

| Electrical Subcontractor (R) | Installs if subcontracted; Provides main service |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Temporary power plan/layout

- Utility company coordination

- Temporary power panels and distribution

- GFCI protection devices

- Extension cords (proper gauge/rating)

- Lockout/tagout equipment

- Inspection requirements

============================================================

PROCEDURE

============================================================

STEP 1 - Plan Power Distribution

--------------------------------------

FS and PM plan system:

- Determine power requirements (load calculation)

- Identify main service location

- Plan distribution panel locations

- Map power runs to work areas

- Coordinate with utility company for service

STEP 2 - Coordinate Utility Service

--------------------------------------

PM coordinates:

- Request temporary service from utility

- Schedule meter installation

- Confirm service size adequate

- Obtain required permits

- Schedule inspections

STEP 3 - Install Main Distribution

--------------------------------------

Install primary equipment:

- Set temporary power pole or panel

- Install main disconnect

- Mount distribution panel(s)

- Install GFCI protection

- Ground system properly

STEP 4 - Run Distribution to Work Areas

--------------------------------------

Extend power throughout site:

- Install spider boxes at work areas

- Run temporary feeders

- Install receptacle stations

- Ensure proper cord protection

- Label all circuits

STEP 5 - Connect Trailers and Equipment

--------------------------------------

Provide power to facilities:

- Connect office trailer

- Connect storage (if lighting needed)

- Power tool charging stations

- Temporary lighting circuits

- Equipment connections

STEP 6 - Inspect and Document

--------------------------------------

Complete installation:

- Perform internal inspection

- Schedule required AHJ inspection

- Test all GFCI devices

- Document system with photos

- Create temporary power map

- Brief crew on safety procedures

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| Temporary power operational before work | 100% |

| All GFCI protection functional | 100% |

| Required inspections passed | 100% |

| System documented and mapped | 100% |

============================================================

APPENDIX

============================================================

- Temporary Power Layout Template

- Load Calculation Worksheet

- GFCI Testing Log

- Inspection Checklist

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.105 - Setup Temporary Power

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Field Operations | Approver: Executive Committee