SOP 9.41.135 – Setup Laydown Area

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.095 – Setup Storage Trailer; 9.41.100 – Setup Site Fencing and Access Control
Reference: GSL Project Manager Procedures – Mobilization

Purpose

To establish a designated laydown area for material storage and staging to support efficient project operations and site safety.

Scope

This SOP applies to Project Managers and Field Supervisors during mobilization.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Approves laydown area per site logistics plan. |
| Field Supervisor | Sets up and manages the laydown area. |
| Safety Coordinator | Reviews for compliance with safety standards and traffic flow. |

Required Documents and Tools

- Site logistics plan

- Laydown area setup checklist

- Material handling plan (SOP 9.41.060)

Procedure

- Select Location – Identify flat, accessible ground close to work zones, ensuring crane/hoist access if required.

- Prepare Site – Clear debris, grade if necessary, install ground protection for heavy loads.

- Organize Layout – Separate storage by material type, mark access lanes for forklifts and deliveries.

- Secure Area – Fence or barrier as required; provide lighting if in use after hours.

- Safety Review – Confirm materials are stacked properly, compliant with fire/hazardous material requirements.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Laydown Area Setup Checklist | Field Supervisor | Project Folder |
| Updated Site Logistics Plan | PM | Project Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Laydown area established before first delivery | 100% |
| Access lanes clear and maintained | 100% |
| Weekly inspections performed | 100% |

References

- GSL Project Manager Procedures – Mobilization

Appendix

- Laydown Area Layout Example

- Inspection Checklist Template