SOP: 9.6.020 - Manage Punch Lists

Department: Project Management / Field Operations

Related SOPs:

- 9.6.005 - Prepare for Turnover (Field Perspective)

- 9.6.010 - Conduct Closeout Meetings

- 9.4.240 - Manage Inspections

============================================================

PURPOSE

============================================================

To establish a standardized process for managing punch lists, ensuring all deficiencies are documented, tracked, and resolved prior to project closeout.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Punch list items have been identified

- Owner/GC walkthroughs have occurred

- Final completion is being pursued

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Manages punch list process; Tracks completion |

| Field Supervisor (R) | Assigns work; Verifies corrections; Coordinates access |

| Foreman (R) | Executes punch work; Reports completion |

| Site Administrator (R) | Maintains punch list log; Documents status |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Punch list log/tracking system

- Access to work areas

- Materials for corrections

- Labor availability

- Photo documentation capability

- Verification process

============================================================

PROCEDURE

============================================================

STEP 1 - Document Punch Items

--------------------------------------

Capture all punch items:

- Record from owner walkthrough

- Document from GC punch list

- Include internal quality items

- Note location, description, priority

- Take photos of each item

- Enter in tracking system

STEP 2 - Review and Validate Items

--------------------------------------

PM/FS review punch list:

- Verify items are valid GSL scope

- Challenge items outside contract

- Prioritize by area/system

- Identify materials needed

- Assess labor requirements

STEP 3 - Assign and Schedule Work

--------------------------------------

FS assigns punch work:

- Distribute to foremen by area

- Schedule based on priority

- Coordinate access requirements

- Ensure materials available

- Set target completion dates

STEP 4 - Execute Corrections

--------------------------------------

Complete punch items:

- Perform corrections per list

- Document completion with photos

- Note any issues encountered

- Report completion to FS

- Update tracking system

STEP 5 - Verify Corrections

--------------------------------------

FS verifies completions:

- Physically inspect each item

- Confirm meets requirements

- Take verification photos

- Mark complete in log

- Identify any re-work needed

STEP 6 - Obtain Sign-off

--------------------------------------

Close out punch list:

- Request owner/GC re-walk

- Address any new items

- Obtain written sign-off

- Document final status

- Archive punch list records

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| All punch items logged | 100% |

| Items completed within schedule | 95% |

| Verification performed | 100% |

| Owner sign-off obtained | 100% |

============================================================

APPENDIX

============================================================

- Punch List Log Template

- Punch Item Photo Standards

- Verification Checklist

- Sign-off Form

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.560 - Manage Punch Lists

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee