SOP: 9.6.050 - Manage Warranties

Department: Project Management

Related SOPs:

- 9.6.040 - Manage O&M Manuals

- 9.6.060 - Manage Closeout Documentation

- 9.4.200 - Manage Submittals

============================================================

PURPOSE

============================================================

To establish a standardized process for managing warranty documentation, ensuring proper collection, compilation, and submission of all warranties prior to project closeout.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Warranty documentation is required

- Equipment/material warranties must be transferred

- Subcontractor warranties are required

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Manages warranty compilation; Submits final package |

| Site Administrator (R) | Collects and organizes warranty documentation |

| Purchasing (C) | Coordinates vendor warranty certificates |

| Subcontractors (R) | Provide warranty certificates for their work |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Contract warranty requirements

- Manufacturer warranty certificates

- Subcontractor warranty letters

- Extended warranty documentation

- Start date verification

- Warranty tracking log

============================================================

PROCEDURE

============================================================

STEP 1 - Identify Warranty Requirements

--------------------------------------

Review contract for:

- Standard warranty period

- Extended warranty requirements

- Specific equipment warranties

- Subcontractor warranty requirements

- Format/documentation requirements

STEP 2 - Create Warranty Tracking Log

--------------------------------------

Establish tracking system:

- List all items requiring warranties

- Identify warranty periods

- Note special requirements

- Track collection status

- Set deadlines for collection

STEP 3 - Collect Warranty Documentation

--------------------------------------

Gather all warranties:

- Request from manufacturers

- Obtain from subcontractors

- Collect extended warranty certificates

- Verify coverage periods

- Confirm start dates

STEP 4 - Verify Warranty Information

--------------------------------------

Review collected warranties:

- Confirm coverage meets requirements

- Verify start/end dates

- Check equipment identification

- Validate signatures/authorizations

- Identify missing items

STEP 5 - Compile Warranty Package

--------------------------------------

Organize warranties:

- Create warranty summary sheet

- Organize by system/equipment

- Include contact information

- Add claim procedures

- Bind per requirements

STEP 6 - Submit and Archive

--------------------------------------

Complete warranty submission:

- Submit to owner/GC

- Obtain receipt acknowledgment

- Archive copy in project files

- Note warranty expiration dates

- Set up warranty tracking reminders

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| All warranties collected | 100% |

| Warranty periods verified | 100% |

| Submitted before closeout | 100% |

| Owner acknowledgment received | 100% |

============================================================

APPENDIX

============================================================

- Warranty Tracking Log Template

- Warranty Summary Sheet

- Warranty Request Letter Template

- Standard Warranty Certificate Form

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.575 - Manage Warranties

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee