SOP: 9.6.060 - Manage Closeout Documentation

Department: Project Management

Related SOPs:

- 9.6.010 - Conduct Closeout Meetings

- 9.6.030 - Manage As-Built Drawings

- 9.6.040 - Manage O&M Manuals

- 9.6.050 - Manage Warranties

============================================================

PURPOSE

============================================================

To establish a standardized process for managing all closeout documentation, ensuring complete and organized project records are submitted and archived.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Project closeout is in progress

- Final documentation must be compiled

- Project records must be archived

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Manages overall closeout documentation; Final approval |

| Site Administrator (R) | Compiles documents; Maintains organization |

| Field Supervisor (C) | Provides field documentation; Verifies completeness |

| Branch Manager (C) | Reviews final package; Approves archive |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Contract closeout requirements

- Closeout checklist

- All project documentation

- Filing/archive standards

- Electronic file organization

- Final turnover package requirements

============================================================

PROCEDURE

============================================================

STEP 1 - Review Closeout Requirements

--------------------------------------

Identify all requirements:

- Contract documentation requirements

- Owner/GC specific requirements

- Company archive standards

- Retention period requirements

- Format requirements

STEP 2 - Create Closeout Checklist

--------------------------------------

Develop comprehensive checklist:

- As-built drawings

- O&M manuals

- Warranties

- Test reports

- Inspection certificates

- Lien waivers

- Final pay applications

- Correspondence files

STEP 3 - Compile All Documentation

--------------------------------------

Gather required documents:

- Collect from all sources

- Verify completeness

- Organize by category

- Check against checklist

- Identify missing items

STEP 4 - Organize Final Package

--------------------------------------

Prepare closeout package:

- Organize per specification

- Create table of contents

- Include required copies

- Bind appropriately

- Prepare transmittal

STEP 5 - Submit to Owner/GC

--------------------------------------

Deliver closeout package:

- Submit per contract

- Obtain receipt

- Address any deficiencies

- Resubmit as needed

- Obtain final acceptance

STEP 6 - Archive Project Records

--------------------------------------

Complete internal archive:

- Organize project files

- Separate current from archived

- Maintain electronic copies

- Store per retention policy

- Create archive index

- Document lessons learned

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| All closeout items on checklist | 100% |

| Documentation submitted on time | 100% |

| Owner/GC acceptance obtained | 100% |

| Project properly archived | 100% |

============================================================

APPENDIX

============================================================

- Closeout Documentation Checklist

- Archive Index Template

- File Organization Standards

- Retention Policy Reference

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.580 - Manage Closeout Documentation

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee