SOP 9.186.41 - Monthly Project Manager Review Meetings

Department: 
Created by: 
Effective Date: [Insert Date]
Version: 
Related SOPs: 
Reference:

1. Purpose

To ensure consistent and thorough oversight of all active projects, this SOP establishes the structure, responsibilities, and documentation requirements for monthly project reviews between the Project Manager (PM), Business Manager (BM), and Branch Manager (BrM).

2. Scope

Applies to all GSL Electric Project Managers and involves participation by Branch Managers and Business Managers. This procedure covers projects at all stages of construction, from initiation through closeout.

3. Roles & Responsibilities

Project Manager (PM):

- Lead project review preparation.

- Maintain accurate cost projections, job plans, and documentation.

- Submit all updates prior to the review meeting.

Business Manager (BM):

- Validate financial documentation and compliance with contract terms.

- Identify discrepancies in billing, contract values, and executed change orders.

Branch Manager (BrM):

- Lead the review meeting.

- Provide strategic oversight on billing, manpower, and project health.

- Ensure alignment with GSL directives and KPIs.

4. Review Schedule

- Frequency: Monthly

- Participants: PM, BM, BrM

- Preparation Deadline: PM must submit required documentation at least 48 hours before the scheduled review.

5. Review Agenda

5.1 Business Manager Review

a. Review the following:

- GSL Job # Request Form

- Contract File Audit Reconciliation

- GSL RFI to General Contractor

- Fully Executed Change Order Documents

- A/R Ledger and Contract Summary Printout

5.2 Joint Review – Branch Manager & Business Manager

a. Financial Analysis:

- Over/Under Billings

- Collections Status

- Costs vs. Budget

- Job Responsibility Form Review

5.3 Branch Manager Review

a. Project Health Check:

- Submittals and Buyout Status

- Contract Value and CO Reconciliation:

  - Confirm budget equals contract value

  - Compare budgeted vs. actual hourly labor rate

- Pending Change Orders and Cost Type Projections:

  - Review PO’s, subcontracts, and anticipated costs

  - Validate cost projections in ViewPoint

- Job Plan & Labor Hour Review:

  - Match budgeted vs. expended hours

  - Balance of hours to complete

  - Labor productivity analysis

- Weekly Letters Review:

  - Outstanding issues and required follow-up

5.4 PM Discussion Items with Branch Manager

a. Pending Items:

- Pending Change Orders for Approval

- Potential Change Orders

- Labor/Material Issues

- Equipment Needs

- Closeout Status (as applicable)

6. Documentation Requirements

- All documentation must be stored and updated in ViewPoint.

- Meeting minutes shall be prepared by the Project Manager and reviewed by the Branch Manager within 48 hours of the meeting.

7. Compliance & Performance Review

- Failure to adhere to this SOP will be escalated per GSL’s Management Directives for Project Management.

- Repeated non-compliance may result in review by the Executive Committee and potential disciplinary action.

8. Related SOPs & References

- SOP 9.5 – Project Management Directives

- SOP 9.13 – Business Manager Directives

- SOP 9.6 – Branch Management Directives

- ViewPoint SOPs and data input guidelines