SOP 9.41.045 – Identify Value Engineering & Prefabrication Opportunities

Department: Project Management / Prefabrication
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.050 – Prepare Construction Takeoff
Reference: GSL Pre-Construction Planning – Value Engineering & Prefabrication

Purpose

To identify and evaluate opportunities for value engineering (VE) and prefabrication to reduce cost, improve efficiency, and simplify work without compromising project scope or quality.

Scope

This SOP applies to Project Managers, Field Supervisors, and Prefabrication Leads during the pre-construction planning phase of all awarded projects.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Facilitates identification of VE/prefab opportunities; integrates approved options into PEP. |
| Prefabrication Lead | Reviews drawings for prefab potential; develops prefab strategy sheet. |
| Field Supervisor | Validates constructability and field feasibility of proposals. |
| Estimator | Confirms VE proposals align with bid assumptions and budget. |

Required Documents and Tools

- Current drawings and specifications

- Prefab shop capabilities catalog

- VE proposal log template

- PEP (Project Execution Plan)

Procedure

Step 1: Review Drawings and Specs

- Identify repetitive, modular, or offsite-constructible components.

- Note materials or assemblies that may have VE alternatives.

Step 2: Analyze Opportunities

- Evaluate cost savings, labor efficiency, and schedule benefits.

- Confirm prefab shop capacity and logistics feasibility.

Step 3: Document Proposals

- Record each opportunity in a VE/Prefab Proposal Log.

- Provide cost/benefit analysis and schedule impact notes.

Step 4: Approve and Integrate

- Present opportunities at turnover or planning meetings.

- Integrate approved items into PEP, budget, and procurement plan.

Step 5: Monitor Execution

- Track implementation of approved VE/prefab opportunities.

- Update logs and share with project team.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| VE/Prefab Proposal Log | Project Manager | Project Folder |
| Prefab Strategy Sheet | Prefab Lead | Prefab Subfolder |
| Updated PEP | PM | Project Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of projects reviewed for VE/prefab | 100% |
| Documented proposals with cost/schedule impact | 100% |
| Approved opportunities integrated into PEP | 100% |

References

- GSL Pre-Construction Planning – Section 4.3 VE & Prefabrication

Appendix

- VE/Prefab Proposal Log (sample)

- Prefab Strategy Sheet Template

- Example Cost/Benefit Analysis