SOP 9.41.050 – Prepare Construction Takeoff

Department: Project Management / Estimating
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.055 – Procurement of Large Feeder Wire
Reference: GSL Pre-Construction Planning – Construction Takeoff

Purpose

To prepare a detailed construction takeoff that validates estimated quantities and provides the basis for procurement, labor budgeting, and execution planning.

Scope

This SOP applies to Project Managers and Estimators for all awarded projects before procurement buyout.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Oversees the takeoff process and ensures alignment with PEP. |
| Estimator | Provides bid takeoff for reference and comparison. |
| Field Supervisor | Reviews quantities for constructability and logistics accuracy. |
| Purchasing | Uses takeoff results for vendor negotiations and procurement. |

Required Documents and Tools

- Project drawings and specifications

- Estimator’s bid takeoff

- Takeoff software or worksheets

- Project Execution Plan (PEP)

Procedure

Step 1: Collect Reference Data

- Obtain drawings, specs, and bid takeoff from estimating.

Step 2: Perform Detailed Takeoff

- Generate quantities of labor and materials.

- Compare against estimator’s bid to confirm accuracy.

Step 3: Validate Results

- Review quantities with Field Supervisor.

- Confirm integration of VE/prefab opportunities.

Step 4: Finalize and Save

- Document takeoff results.

- Upload to project folder for use in procurement and manpower forecasting.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Final Construction Takeoff | Project Manager | Project Folder |
| Takeoff Notes | PM / Estimator | Pre-Construction Binder |
| Procurement Input File | Purchasing | Procurement Subfolder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Takeoff completed prior to procurement buyout | 100% |
| Quantities validated against bid assumptions | 100% |
| Takeoff uploaded to project folder | 100% |

References

- GSL Pre-Construction Planning – Section 4.3 Construction Takeoff

Appendix

- Sample Takeoff Worksheet

- Procurement Input Template

- Takeoff Validation Checklist